## Sheet1
Subcontractor: | Saddam Contractor
State: | Uttar Pradesh |  | Saddam Contractor |  |  |  |  | PIPE LINE WORK
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount | Final_Amount | PAYMENT NOTE No. | Payment_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10%
60066 | khorsama village RR work | 2023-11-06 | 1 | 299359.5 | 64075 | 235284.5 | 42351 | 277635.5 | 2352.845 | 11764.225 | 23528.45 | 23528.45 | 42351 | 0 | 174111 |  |  | 174108 | 05-12-2023 NEFT/AXISP00449670536/RIUP23/3562/SADDAM CONTRACTOR/PUNB0166010 174108.00
60066 | GST |  | 1 | 42351 | [10 empty] | 42351 |  |  | 42351 | 27-12-2023 NEFT/AXISP00455698581/RIUP23/3754/SADDAM CONTRACTOR/PUNB0166010 42351.00
60066
[15 empty] | 216462 |  |  | 216459
3
[6 empty] | ITEM | DPR | CUM | EXCESS | RATE | AMOUNT
[6 empty] | DISM. BOE | 0 | 208.86 | 208.86 | 50 | 10443
[6 empty] | Dism.C C | 203.33 | 461.92 | 258.59 | 250 | 64647.5
[6 empty] | RR. BOE | 0 | 119.41 | 119.41 | 200 | 23882
[10 empty] | Hold amt | 98972.5