## Sheet1
Subcontractor: | AP Enterprises
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
| Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | GST SD (18%) | Hold the Amount because the Qty. is more then the DPR | TDS in tally | Final Amount |  | Total Amount Paid | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18%
57724
57724 | Kasoli Village OHT 375KL 16M staging Work | 2023-09-23 | 14, 16 | 703125 | 0 | 703125 | 126562.5 | 829687.5 | 7031 | 35156 |  |  | 126562.5 | 0 | 134615 | 660938 | tds-134615 | 198000 | 06-06-2023 NEFT/AXISP00395970528/RIUP23/536/A P ENTERPRISES 198000.00
57724 | GST Release Note |  | 14, 16 | 126562.5 | [11 empty] | 126562.5 |  | 65938 | 11-10-2023 NEFT/AXISP00433253775/RIUP23/2503/A P ENTERPRISES/IDIB000M779 65938.00
57724 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 126563 | 19-07-2024 NEFT O/W-YESIG42010144963-IDIB000M779-A P ENTERPRISES -RIUP24/1201 RS 1,26,563.00
[5 empty] | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | 0% |  |  | 0 | 57723
57723 | NIYAMU Village OHT 325 KL 12M Work |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 198000 | 06-06-2023 NEFT/AXISP00395970529/RIUP23/535/A P ENTERPRISES 198000.00
57202
57202 | Badakali Village OHT 150KL 12M staging Work | 2023-09-23 | 15 | 123750 | 0 | 123750 | 22275 | 146025 | 1238 | 6188 |  |  | 22275 | 0 | 23750 | 116324 | tds-23750 | 99000 | 25-05-2023 NEFT/AXISP00392601989/RIUP23/396/A P ENTERPRISES 99000.00
57202 | GST Release Note |  | 15 | 22275 | [11 empty] | 22275 |  | 17324 | 13-10-2023 NEFT/AXISP00434019639/RIUP23/2502/A P ENTERPRISES/IDIB000M779 17324.00
57202 | [17 empty] | 22275 | 19-07-2024 NEFT O/W-YESIG42010143589-IDIB000M779-A P ENTERPRISES-RIUP24/1200 RS 22,275.00
57201 | [16 empty] | 57201
57201 | BANNAGAR Village OHT 175KL 12 MTR STAGING Work | [15 empty] | 57724 | 99000 | 23-05-2023 NEFT/AXISP00392088476/RIUP23/355/A P ENTERPRISES 99000.00
57200
57200 | BADHAI KHURD Village OHT 200KL 12 MTR STAGING Work | [15 empty] | 57724 | 99000 | 23-05-2023 NEFT/AXISP00392088475/RIUP23/354/A P ENTERPRISES 99000.00
57200 | [17 empty] | 297000 | 27-09-2024 NEFT/AXISP00545360699/RIUP24/1985/A P ENTERPRISES/IDIB000M779 297000.00
57199
57199 | ROHANA KHURD Village OHT 225KL 12 MTR STAGING Work | [15 empty] | 57724 | 99000 | 25-05-2023 NEFT/AXISP00392601988/RIUP23/395/A P ENTERPRISES 99000.00
57199 | [17 empty] | 198000 | 27-09-2024 NEFT/AXISP00545360698/RIUP24/1984/A P ENTERPRISES/IDIB000M779 198000.00
54234
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2022-12-24 | 5 | 534736 | 0 | 534736 | 96252 | 630988 | 5347.36 | 26736.8 | 53473.6 | 53473.6 | 96252 | 43129 |  | 352576 |  | 352575 | 06-01-2023 NEFT/AXISP00352522093/RIUP22/1797/A P ENTERPRISES 352575.00
54234 | GST Release Note | 2023-01-16 | 5 | 96252 | 0 | 96252 | 0 | 96252 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96252 |  | 96252 | 21-01-2023 NEFT/AXISP00356444712/RIUP22/1906/A P ENTERPRISES ₹ 96,252.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2023-01-31 | 7 | 605360 | 39560.4 | 565799.6 | 101844 | 667643.6 | 5657.996 | 28289.98 | 56579.96 | 56579.96 | 101844 | 62783 |  | 355909 |  | 198000 | 23-01-2023 NEFT/AXISP00356693749/RIUP22/1957/A P ENTERPRISES ₹ 1,98,000.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2023-04-08 | 1 | 303939 | 0 | 303939 | 54709 | 358648 | 3039.39 | 15196.95 | 15196.95 | 30393.9 | 54709 |  |  | 240112 |  | 157909 | 08-02-2023 NEFT/AXISP00361822157/RIUP22/2121/A P ENTERPRISES 157909.00
54234 | GST Release Note | 2023-02-18 | 7 | 101844 | [11 empty] | 101844 |  | 101844 | 21-02-2023 NEFT/AXISP00364594735/RIUP22/2235/A P ENTERPRISES 101844.00
54234 | GST Release Note | 2023-05-23 | 1 | 54709 | [11 empty] | 54709 |  | 198000 | 13-04-2023 13-04-2023 NEFT/AXISP00381797403/SPUP23/0121/A P ENTERPRISES 198000.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2023-04-08 | 9, 10 | 282452 | 1480 | 280972 | 50574.96 | 331546.96 | 2809.72 | 14048.6 | 14048.6 | 28097.2 | 50574.96 |  | 56195 | 221967.88 | tds-56195 | 42112 | 02-05-2023 NEFT/AXISP00386671975/RIUP23/056/A P ENTERPRISES ₹ 42,112.00
54234 | GST Release Note |  | 9, 10 | 50574.96 | [11 empty] | 50574.96 |  | 54709 | 21-06-2023 NEFT/AXISP00399842955/RIUP23/747/A P ENTERPRISES 54709.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2024-05-13 | 4 | 678566 |  | 678566 | 122141.88 | 800707.88 | 6785.66 | 33928.3 | 67856.6 | 67856.6 | 122141.88 |  |  | 502138.84 |  | 196000 | 24-08-2023 NEFT/AXISP00418043570/RIUP23/1686/A P ENTERPRISES/IDIB000M779 196000.00
54234 | [17 empty] | 25968 | 07-09-2023 NEFT/AXISP00422860734/RIUP23/1856/A P ENTERPRISES/IDIB000M779 25968.00
54234 | [17 empty] | 49500 | 05-02-2024 NEFT/AXISP00468456762/RIUP23/4602/A P ENTERPRISES/IDIB000M779 49500.00
54234 | [17 empty] | 49500 | 16-02-2024 NEFT/AXISP00472106410/RIUP23/4732/A P ENTERPRISES/IDIB000M779 49500.00
54234 | [17 empty] | 400328 | 11-07-2024 NEFT/AXISP00517806262/RIUP24/1086/A P ENTERPRISES/IDIB000M779 400328.00
54234 | [17 empty] | 49500 | 29-08-2024 NEFT/AXISP00533190148/RIUP24/1562/A P ENTERPRISES/IDIB000M779 49500.00
54217
54217 | BHaisani Village Pipe laying Work | 2022-12-24 | 4 | 448841 | 0 | 448841 | 80791 | 529632 | 4488 | 22442 | 44884 | 44884 | 80791 | 33952 |  | 298191 |  | 200000 | 06-01-2023 NEFT/AXISP00352522094/RIUP22/1791/A P ENTERPRISES 200000.00
54217 | GST Release Note |  | 4 | 80791 |  | 80791 | 0 | 80791 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80791 |  | 80791 | 23-01-2023 NEFT/AXISP00356693741/RIUP22/1907/A P ENTERPRISES ₹ 80,791.00
54217 | BHaisani Village Pipe laying Work | 2023-08-19 | 8, 9 | 438425 |  | 438425 | 78916.5 | 517341.5 | 4384 | 21921 | 21921 | 43843 | 78916.5 |  | 87685 | 346356 | tds-87685 | 98191 | 06-03-2023 NEFT/AXISP00369190886/RIUP22/2484/A P ENTERPRISES 98191.00
54217 | GST Release Note |  | 8, 9 | 78916.5 | [11 empty] | 78916.5 |  | 346356 | 31-08-2023 NEFT/AXISP00419854902/RIUP23/1807/A P ENTERPRISES/IDIB000M779 ₹ 3,46,356.00
54217 | [17 empty] | 74250 | 05-02-2024 NEFT/AXISP00468456765/RIUP23/4599/A P ENTERPRISES/IDIB000M779 74250.00
52830
52830 | Panchenda Kallan Village Pipe laying Work. | 2022-11-15 | 1 | 2016203.5 | 58442 | 1957762 | 352397.16 | 2310159.16 | 19578 | 97888 | 97888 | 195776 | 352397.16 | 516724 |  | 1029908 |  | 495000 | 20-10-2022 NEFT/AXISP00330252341/RIUP22/1062/A P ENTERPRISES 495000.00
52830 | GST Release Note |  | 1 | 352397.16 |  | 352397.16 | 0 | 352397.16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 352397 |  | 534908 | 22-11-2022 NEFT/AXISP00339521128/RIUP22/1311/A P ENTERPRISES 534908.00
52830 | Hold amount release note | 2022-12-03 |  | 450000 |  | 450000 |  | 450000 | [7 empty] | 450000 |  | 450000 | 03-12-2022 NEFT/AXISP00343125334/RIUP22/1399/A P ENTERPRISES 450000.00
52830 | Pancheda Kallan Village Pipe laying Work. | 2023-01-10 | 6 | 1047594 | 17982 | 1029612 | 185330.16 | 1214942.16 | 10296 | 51481 | 102961 | 102961 | 185330.16 | 0 |  | 761913 |  | 352396 | 21-12-2022 NEFT/AXISP00347813404/RIUP22/1593/A P ENTERPRISES 352396.00
52830 | GST Release Note |  | 6 | 185330 |  | 185330 | 0 | 185330 | 0 | 0 |  |  | 0 |  |  | 185330 |  | 198000 | 18-01-2023 NEFT/AXISP00355710810/RIUP22/1897/A P ENTERPRISES ₹ 1,98,000.00
52830 | Pachenda Kalan Village Pipe Laying Work | 2023-08-08 | 7,8 | 600724.53 | 77323 | 523401.53 | 94212.2754 | 617613.8054 | 5234.0153 | 26170.0765 | 0 | 0 | 94212.2754 | 43786 | 64680 | 448211.4382 | tds-64680 | 495000 | 23-02-2023 NEFT/AXISP00365243860/RIUP22/2284/A P ENTERPRISES 495000.00
52830 | Pachenda Kalan Village Pipe Laying Work | 2023-08-26 | 12,13 | 1119282.75 | 885 | 1118397.75 | 201311.595 | 1319709.345 | 11183.9775 | 55919.8875 | 0 | 0 | 201311.595 | 109074 | 223680 | 942219.885 | tds-223680 | 49500 | 13-04-2023 NEFT/AXISP00381797401/SPUP23/0119/A P ENTERPRISES 49500.00
52830 | GST Release Note |  | 7&8 12&13 | 295523.8704 | [11 empty] | 295523.8704 |  | 19413 | 10-05-2023 10-05-2023 NEFT/AXISP00389200590/SPUP23/0300/A P ENTERPRISES 19413.00
52830 | [17 empty] | 185330 | 12-05-2023 NEFT/AXISP00389894115/RIUP23/202/A P ENTERPRISES 185330.00
52830 | [17 empty] | 198000 | 15-06-2023 NEFT/AXISP00398797334/RIUP23/681/A P ENTERPRISES 198000.00
52830 | [17 empty] | 250212 | 28-08-2023 NEFT/AXISP00418849234/RIUP23/1635/A P ENTERPRISES/IDIB000M779 250212.00
52830 | [17 empty] | 942220 | 31-08-2023 NEFT/AXISP00419716234/RIUP23/1806/A P ENTERPRISES/IDIB000M779 942220.00
52830 | [17 empty] | 24750 | 05-02-2024 NEFT/AXISP00468456763/RIUP23/4601/A P ENTERPRISES/IDIB000M779 24750.00
52830 | [17 empty] | 295524 | 19-07-2024 NEFT O/W-YESIG42010143588-IDIB000M779-A P ENTERPRISES -RIUP24/1203 RS 2,95,524.00
52830 | [17 empty] | 99000 | 29-08-2024 NEFT/AXISP00533190154/RIUP24/1563/A P ENTERPRISES/IDIB000M779 99000.00
53075
53075 | Pachenda Khurd Village Pipe laying Work | 2022-12-24 | 3 | 817552 | 80919 | 736633 | 132594 | 869227 | 7366.33 | 36831.65 | 73663.3 | 73663.3 | 132594 | 216163 |  | 328945 |  | 148500 | 08-11-2022 NEFT/AXISP00335609453/RIUP22/1208/A P ENTERPRISES 148500.00
53075 | GST Release Note | 2023-01-16 | 3 | 132594 | 0 | 132594 | 0 | 132594 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132594 |  | 180446 | 07-01-2023 NEFT/AXISP00353064335/RIUP22/1742/A P ENTERPRISES 180446.00
53075 | Pachenda Khurd Village Pipe laying Work | 2023-04-10 | 2 | 461312.48 | 0 | 461312.48 | 83036 | 544348.48 | 4613.1248 | 23065.624 | 23065.624 | 46131.248 | 83036 | 33987 |  | 330450 |  | 132594 | 18-01-2023 NEFT/AXISP00355697030/RIUP22/1883/A P ENTERPRISES ₹ 1,32,594.00
53075 | GST Release Note | 2023-05-23 | 2 | 83036 |  | 83036 | 0 | 83036 | 0 | 0 |  |  | 0 |  |  | 83036 |  | 198000 | 23-01-2023 NEFT/AXISP00356620188/RIUP22/1937/A P ENTERPRISES ₹ 1,98,000.00
53075 | Pachenda Khurd Village Pipe laying Work | 2023-08-19 | 10, 11 | 694130 |  | 694130 | 124943.4 | 819073.4 | 6941.3 | 34706.5 | 34706.5 | 69413 | 124943.4 | 70108 | 89326 | 478254.7 | tds-89326 | 99000 | 14-03-2023 NEFT/AXISP00371304701/RIUP22/2570/A P ENTERPRISES 99000.00
53075 | GST Release Note |  | 10, 11 | 124943.4 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | 124943.4 |  | 148500 | 13-04-2023 13-04-2023 NEFT/AXISP00381797402/SPUP23/0120/A P ENTERPRISES 148500.00
53075 | [17 empty] | 83036 | 21-06-2023 NEFT/AXISP00399842954/RIUP23/748/A P ENTERPRISES 83036.00
53075 | [14 empty] | 49500 |  | TDS-49500 | 198000 | 28-07-2023 NEFT/AXISP00410084836/RIUP23/1264/A P ENTERPRISES 198000.00
53075 | [17 empty] | 297000 | 28-08-2023 NEFT/AXISP00418870939/RIUP23/1757/A P ENTERPRISES/IDIB000M779 297000.00
53075 | [17 empty] | 99000 | 05-02-2024 NEFT/AXISP00468456764/RIUP23/4600/A P ENTERPRISES/IDIB000M779 99000.00
53075 | [17 empty] | 297000 | 23-08-2024 NEFT/AXISP00531577842/SKUP24/160/A P ENTERPRISES/IDIB000M779 297000.00
55800
55800 | Bhoop Khedi Village pipe laying Work | 2023-06-01 | 7 | 989955.27 | 0 | 989955 | 178191.9 | 1168146.9 | 9900 | 49498 | 49498 | 98996 | 178191.9 | 136068.82 |  | 645994 |  | 198000 | 02-05-2023 NEFT/AXISP00386712950/SPUP23/0355/A P ENTERPRISES ₹ 1,98,000.00
55800 | Bhoop Khedi Village pipe laying Work | 2023-08-19 | 11, 12 | 223424 | 162280 | 61144 | 11005.92 | 72149.92 | 611 | 3057 | 3057 | 6114 | 11005.92 | 0 | 12229 | 48305 | tds-12229 | 447994 | 15-06-2023 NEFT/AXISP00398738898/RIUP23/643/A P ENTERPRISES 447994.00
55800 | GST Release Note |  | 7 | 178191.9 | [11 empty] | 178191.9 |  | 48305 | 31-08-2023 NEFT/AXISP00419854901/RIUP23/1808/A P ENTERPRISES/IDIB000M779 ₹ 48,305.00
55800 | GST Release Note |  | 11, 12 | 11005.92 | [11 empty] | 11005.92 |  | 178192 | 01-02-2024 NEFT/AXISP00467277204/RIUP23/4400/A P ENTERPRISES/IDIB000M779 178192.00
55800 | Bhoop Khedi Village pipe laying Work | 2024-10-15 | 8 | 176276 | 0 | 176276 | 31729.68 | 208005.68 | 1763 | 8814 | 17627.6 | 17628 | 31729.68 | 0 | 0 | 130443 |  | 49500 | 29-08-2024 NEFT/AXISP00533190151/RIUP24/1559/A P ENTERPRISES/IDIB000M779 49500.00
59119
59119 | Morkooka Village pipe laying Work | 2023-08-29 | 13, 14 | 670996 | 0 | 670996 | 120779.28 | 791775.28 | 6710 | 33550 | 33550 | 67100 | 120779.28 | 0 | 134199 | 530086 | tds-134199 | 530086 | 06-09-2023 NEFT/AXISP00422274697/RIUP23/1858/A P ENTERPRISES/IDIB000M779 530086.00
59119 | Morkooka Village pipe laying Work | 2024-01-19 | 24 | 460940 |  | 460940 | 82969.2 | 543909.2 | 4609 | 23047 | 23047 | 46094 | 82969.2 | 100150 |  | 263993 |  | 148500 | 05-02-2024 NEFT/AXISP00468190239/RIUP23/4584/A P ENTERPRISES/IDIB000M779 148500.00
59119 | GST Release Note |  | 13, 14 | 120779.28 | [11 empty] | 120779.28 |  | 247500 | 05-02-2024 NEFT/AXISP00468456761/RIUP23/4598/A P ENTERPRISES/IDIB000M779 247500.00
59119 | GST Release Note |  | 24 | 82969.2 | [11 empty] | 82969.2 |  | 99000 | 16-02-2024 NEFT/AXISP00472106411/RIUP23/4733/A P ENTERPRISES/IDIB000M779 99000.00
59119 | [17 empty] | 82969 | 24-06-2024 NEFT/AXISP00511368166/RIUP24/0947/A P ENTERPRISES/IDIB000M779 82969.00
59578 | [16 empty] | 59578
59578 | Sikandarpur Village OHT 200KL 14M staging Work | 2023-09-23 | 13,15 | 442500 | 0 | 442500 | 79650 | 522150 | 4425 | 22125 | 0 | 0 | 79650 |  | 86500 | 415950 | tds-86500 | 217950 | 11-10-2023 NEFT/AXISP00433203146/RIUP23/2583/A P ENTERPRISES/IDIB000M779 217950.00
59578 | GST Release Note |  | 15 | 79650 | [11 empty] | 79650 |  | 49500 | 20-07-2024 NEFT/AXISP00520155444/RIUP24/1210/A P ENTERPRISES/IDIB000M779 49500.00
59578 | [17 empty] | 247500 | 29-08-2024 NEFT/AXISP00533190152/RIUP24/1558/A P ENTERPRISES/IDIB000M779 247500.00
59709
59709 | Seemli Village Pipe laying Work | 2023-10-09 | 15, 16, 18 | 986968.4 | 24871.2 | 962097.2 | 173177.496 | 1135274.696 | 9620.972 | 48104.86 | 48104.86 | 96209.72 | 173177.496 | 178264 | 192419 | 581793 | tds-192419 | 581792 | 17-10-2023 NEFT/AXISP00435127245/RIUP23/2656/A P ENTERPRISES/IDIB000M779 581792.00
59709 | GST Release Note |  | 15, 16, 18 | 173177.496 | [11 empty] | 173177.496 |  | 99000 | 02-05-2024 NEFT/AXISP00496215186/RIUP24/0359/A P ENTERPRISES/IDIB000M779 99000.00
59709 | [17 empty] | 297000 | 30-04-2024 NEFT/AXISP00495097365/RIUP24/0357/A P ENTERPRISES/IDIB000M779 297000.00
59709 | [17 empty] | 173177 | 26-06-2024 NEFT/AXISP00511923118/RIUP24/0946/A P ENTERPRISES/IDIB000M779 173177.00
59709 | [17 empty] | 99000 | 18-09-2024 NEFT/AXISP00541733393/RIUP24/1838/A P ENTERPRISES/IDIB000M779 99000.00
59864
59864 | Rohana Khurd Village Pipe laying Work | 2023-10-11 | 15, 17,19 | 1100033 | 265241 | 834792 | 150262.56 | 985054.56 | 8347.92 | 41739.6 | 41739.6 | 83479.2 | 150262.56 | 58144 | 166958 | 601342 | tds-166958 | 601341 | 02-11-2023 NEFT/AXISP00439799501/RIUP23/2902/A P ENTERPRISES/IDIB000M779 601341.00
59864 | Rohana Khurd Village Pipe laying Work | 2024-01-06 | 19, 21 | 388928 |  | 388928 | 70007.04 | 458935.04 | 3889.28 | 19446.4 | 38892.8 | 38892.8 | 70007.04 | 35597 |  | 252210 |  | 148500 | 04-01-2024 NEFT/AXISP00459277739/RIUP23/4105/A P ENTERPRISES/IDIB000M779 148500.00
59864 | GST Release Note |  | 19, 21 | 220269.6 | [11 empty] | 220269.6 |  | 165371 | 22-03-2024 NEFT/AXISP00483444832/RIUP23/5207/A P ENTERPRISES/IDIB000M779 165371.00
59864 | Rohana Khurd Village Pipe laying Work | 2024-05-13 | 6, 3 | 158400 |  | 158400 | 28512 | 186912 | 1584 | 7920 | 15840 | 15840 | 28512 |  |  | 117216 |  | 148500 | 02-05-2024 NEFT/AXISP00496215185/RIUP24/0360/A P ENTERPRISES/IDIB000M779 148500.00
59864 | [17 empty] | 99000 | 20-07-2024 NEFT/AXISP00520155441/RIUP24/1211/A P ENTERPRISES/IDIB000M779 99000.00
59864 | [17 empty] | 99000 | 29-08-2024 NEFT/AXISP00533190150/RIUP24/1560/A P ENTERPRISES/IDIB000M779 99000.00
60067
60067 | MUSTAFABAD Village BALANCE PIPE LAYING Work | 2023-11-06 | 20,22 | 1043683 | 78762 | 964921 | 173685.78 | 1138606.78 | 9649.21 | 48246.05 | 96492.1 | 96492.1 | 173685.78 |  |  | 714042 |  | 346500 | 04-01-2024 NEFT/AXISP00459277738/RIUP23/4106/A P ENTERPRISES/IDIB000M779 346500.00
60067 | GST Release Note |  | 20, 22 | 173685.78 | [11 empty] | 173685.78 |  | 367541 | 12-01-2024 NEFT/AXISP00462196165/RIUP23/4237/A P ENTERPRISES/IDIB000M779 367541.00
60067 | [17 empty] | 173686 | 22-03-2024 NEFT/AXISP00483612633/RIUP23/5227/A P ENTERPRISES/IDIB000M779 173686.00
60069
60069 | Kutubpur Village CONSTRUCTION OF PIPELINE Work | 2023-11-06 | 18, 20 | 747459 | 4060 | 743399 | 133811.82 | 877210.82 | 7433.99 | 37169.95 | 74339.9 | 74339.9 | 133811.82 | 15444 |  | 534671 |  | 247500 | 04-01-2024 NEFT/AXISP00459277737/RIUP23/4107/A P ENTERPRISES/IDIB000M779 247500.00
60069 | GST Release Note |  | 18, 20 | 133811.82 | [11 empty] | 133811.82 |  | 287171 | 12-01-2024 NEFT/AXISP00462196164/RIUP23/4235/A P ENTERPRISES/IDIB000M779 287171.00
60069 | Kutubpur Village CONSTRUCTION OF PIPELINE WORK | 2024-02-12 | 25 | 809672 | 292245 | 517427 | 93136.86 | 610563.86 | 5174.27 | 25871.35 | 51742.7 | 51742.7 | 93136.86 | 148246 |  | 234650 |  | 234650 | 31-03-2024 NEFT/AXISP00486642367/RIUP23/5110/A P ENTERPRISES/IDIB000M779 234650.00
60069 | GST Release Note |  | 25 | 93136.86 | [11 empty] | 93136.86 |  | 133812 | 31-03-2024 NEFT/AXISP00486642366/RIUP23/5226/A P ENTERPRISES/IDIB000M779 133812.00
60069 | [17 empty] | 100000 | cash given as per Tally ledger
60069 | [17 empty] | 99000 | 29-08-2024 NEFT/AXISP00533190149/RIUP24/1561/A P ENTERPRISES/IDIB000M779 99000.00
60090
60090 | NIYAMU Village BALANCE PIPE LAYING Work | 2002-11-06 | 21,23 | 802210 |  | 802210 | 144397.8 | 946607.8 | 8022.1 | 40110.5 | 80221 | 80221 | 144397.8 | 19725 |  | 573910 |  | 297000 | 04-01-2024 NEFT/AXISP00459277736/RIUP23/4108/A PENTERPRISES/IDIB000M779 297000.00
60090 | GST Release Note |  | 21,23 | 144397.8 | [11 empty] | 144397.8 |  | 200000 | 15-03-2024 NEFT/AXISP00481321981/RIUP23/4939/A P ENTERPRISES/IDIB000M779 200000.00
60090 | [17 empty] | 144398 | 06-04-2024 NEFT/AXISP00489186679/RIUP23/5244/A P ENTERPRISES/IDIB000M779 144398.00
60090 | [17 empty] | 49500 | 29-08-2024 NEFT/AXISP00533190153/RIUP24/1557/A P ENTERPRISES/IDIB000M779 49500.00
[6 empty] | 20153787.72 | 3379208.7664 |  | 187733.6156 | 938670.078 | 1180397.694 | 1586222.228 | 3379208.7664 | 1821344.82 | 1321736 | 16705844.6296 |  | 18498649 | Total Paid
[18 empty] | -1792804.3704 | Balance payable

## Sheet2
A P Enterprises
S.No. | PMC No- | Advance
1 | 57724 | 300000
2 | 54234 | 400000
3 | 52830 | 200000
| Total | 900000
|  | Amount | issue no.
not enter in tally-GST release note |  | 415950 | 59119
|  | 22575 | 57202
|  | 0 | 59706
|  | 93137 | 60069
Total amount |  | 531662
Basic amount | bais amt | 6608680
TDS in tally | 1321736 | 66086.8 | 1255649.2

## Cement
| Date Of Issue | Issue Slip No | Name of Party | QTY (BAG) | IN TON | RATE (PER TON) |  | GST (28%) | Amount (In Rs.) | ISSUE FOR | DEBIT NOTE NO. | CONTRACTOR INVOICE DETAIL
311 | 15.06.2023 | 4266 | A.P ENTERPRISES | 440 | 22 | 5625 | 123750 | 34650 | 158400 | For CC work | 741/ 19.08.2023 | BILL BHOOPKHERI 19.08.2023
312 | 15.06.2023 | 4266 | A.P ENTERPRISES | 200 | 10 | 5625 | 56250 | 15750 | 72000 | For CC work |  | RETURNABLE BASIS
351 | 04.07.2023 | 4197 | A.P ENTERPRISES | 150 | 7.5 | 5625 | 42187.5 | 11812.5 | 54000 | KheriDudhadhari |  | RETURNABLE BASIS
361 | 16.07.2023 | 4220 | A.P ENTERPRISES | 130 | 6.5 | 5625 | 36562.5 | 10237.5 | 46800 | Pachendakalan |  | RETURNABLE BASIS
512 | 18.10.2023 | 5662 | A.P ENTERPRISES | 200 | 10 | 5781.25 | 57812.5 | 16187.5 | 74000 | Kheri Duddahari
514 | 18.10.2023 | 5664 | A.P ENTERPRISES | 100 | 5 | 5781.25 | 28906.25 | 8093.75 | 37000 | Kheri Duddahari
541 | 02.11.2023 | 5823 | A.P ENTERPRISES | 200 | 10 | 5781.25 | 57812.5 | 16187.5 | 74000 | Kheri Duddahari
558 | 16.11.2023 | 5610 | A.P ENTERPRISES | 55 | 2.75 | 5781.25 | 15898.4375 | 4451.5625 | 20350 | Kheri Duddahari
560 | 17.11.2023 | 5612 | A.P ENTERPRISES | 200 | 10 | 5859.38 | 58593.8 | 16406.264 | 75000.064 | Kheri Duddahari

## Diesel
S.NO. | Date Of Issue | Issue Slip No | Name of Party | FUEL (In Ltr) | Petrol Pump Slip No. | Latest Rate | Amount (In Rs.) | Vehicle No. | Remarks | ISSUE FOR | DEBIT NOTE NO. | Tax Invocies On PMC
26 | 30.10.2022 | 1122 | A.P Enterprieses | 250 | 2068 | 89.91 | 22477.5 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Khurd Village | 149/23.12.2022 | 03/23.12.2022
27 | 30.10.2022 | 1123 | A.P Enterprieses | 200 | 2069 | 89.91 | 17982 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Kalan Village | 85/15.11.2022 | 01/15.11.2022
277 | 20.11.2022 | 1295 | A.P Enterprieses | 200 | 2372 | 89.91 | 17982 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Kalan Village | 163/09.01.2023 | 06/.09.01.2023
278 | 20.11.2022 | 1296 | A.P Enterprieses | 250 | 2372 | 89.91 | 22477.5 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Khurd Village | 149/23.12.2022 | 03/23.12.2022
279 | 20.11.2022 | 1297 | A.P Enterprieses | 440 | 2372 | 89.91 | 39560.4 |  | Debit to M/s. A.P Enterprises | Pipeline work at Bhaisani Village | 150/23.12.2022 | 04/23.12.2022
381 | 16.12.2022 | 2167 | A.P Enterprieses | 420 | 1869 | 89.91 | 37762.2 |  | Debit to M/s. A.P Enterprises | Pipeline work at Bhaisani Village | 725/07.08.2023 | 07/07.08.2023
709 | 05.12.2022 | 2025 | A.P Enterprieses | 660 | 2345 | 89.91 | 59340.6 |  | Debit to M/s. A.P Enterprises | Pipeline work at Bhaisani Village | 150/23.12.2022 | 04/23.12.2022
715 | 05.11.2022 | 670 | A.P Enterprieses | 200 | 2097 | 89.91 | 17982 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Khurd Village | 149/23.12.2022 | 03/23.12.2022
716 | 05.11.2022 | 671 | A.P Enterprieses | 250 | 2098 | 89.91 | 22477.5 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Kalan Village | 85/15.11.2022 | 01/15.11.2022
745 | 04.10.2022 | 1024 | A.P Enterprieses | 200 | 1027 | 89.91 | 17982 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Kalan Village | 85/15.11.2022 | 01/15.11.2022
746 | 04.10.2022 | 1025 | A.P Enterprieses | 200 | 1028 | 89.91 | 17982 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachenda Khurd Village | 149/23.12.2022 | 03/23.12.2022
877 | 01.01.2023 | 2451 | A.P Enterprieses | 440 | 1800 | 89.91 | 39560.4 |  | Debit to M/s. A.P Enterprises | Pipeline work at Khedidudhadhari Village | 190/31.01.2023 | 07/31.01.2023
1176 | 05.05.2023 | 4058 | A.P Enterprieses | 210 | 4853 | 89.91 | 18881.1 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachendakala Village | 725/07.08.2023 | 07/07.08.2023
1177 | 05.05.2023 | 4058 | A.P Enterprieses | 230 | 4854 | 89.91 | 20679.3 |  | Debit to M/s. A.P Enterprises | Pipeline work at Pachendakala Village | 725/07.08.2023 | 07/07.08.2023
1522 | 05.10.2023 | 3736 | A.P Enterprieses | 60 | 2147 | 89.91 | 5394.6 |  | DEBIT TO A.P ENTERPRISES | ROHANA KHURD | 818/ 09.10.2023 | BILL SEEMLI 09.10.2023
1528 | 07.10.2023 | 3742 | A.P Enterprieses | 60 | 3064 | 89.91 | 5394.6 |  | DEBIT TO A.P ENTERPRISES | ROHANA KHURD | 818/ 09.10.2023 | BILL SEEMLI 09.10.2023
1529 | 08.10.2023 | 3743 | A.P Enterprieses | 60 | 3065 | 89.91 | 5394.6 |  | DEBIT TO A.P ENTERPRISES | ROHANA KHURD | 818/ 09.10.2023 | BILL SEEMLI 09.10.2023
1536 | 12.10.2023 | 3750 | A.P Enterprieses | 80 | 3080 | 89.91 | 7192.8 |  | DEBIT TO A.P ENTERPRISES | ROHANA KHURD | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1544 | 18.10.2023 | 3758 | A.P Enterprieses | 60 | 3907 | 89.91 | 5394.6 |  | DEBIT TO A.P ENTERPRISES | MUSTAFABAD | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1546 | 19.10.2023 | 3760 | A.P Enterprieses | 60 | 3914 | 89.91 | 5394.6 |  | DEBIT TO A.P ENTERPRISES | MUSTAFABAD | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1550 | 21.10.2023 | 3764 | A.P Enterprieses | 60 | 3925 | 89.91 | 5394.6 |  | DEBIT TO A.P ENTERPRISES | MUSTAFABAD | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1555 | 25.10.2023 | 3769 | A.P Enterprieses | 100 | 3937 | 89.91 | 8991 |  | DEBIT TO A.P ENTERPRISES | ROHANA KHURD | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1559 | 27.10.2023 | 3773 | A.P Enterprieses | 100 | 3950 | 89.91 | 8991 |  | DEBIT TO A.P ENTERPRISES | ROHANA KHURD | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1563 | 29.10.2023 | 3777 | A.P Enterprieses | 200 | 3961 | 89.91 | 17982 |  | DEBIT TO A.P ENTERPRISES | KUTUBPUR | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1567 | 01.11.2023 | 3781 | A.P Enterprieses | 200 | 3970 | 89.91 | 17982 |  | DEBIT TO A.P ENTERPRISES | KUTUBPUR | 864/ 04.11.2023 | BILL MUSTAFABAD 04.11.2023 | DEBIT NOTE TRANSFER TO PERFECT INNOVATION
1574 | 04.11.2023 | 3788 | A.P Enterprieses | 300 | 3983 | 89.91 | 26973 |  | DEBIT TO A.P ENTERPRISES | MORKUKKA | 927/21.12.2023 | BILL MUTHURA 21.12.2023 | DEBIT TRANSFER TO PERFECT INNOVATION
1577 | 05.11.2023 | 3791 | A.P Enterprieses | 200 | 3992 | 89.91 | 17982 |  | DEBIT TO A.P ENTERPRISES | MAHRAIPUR | 927/21.12.2023 | BILL MUTHURA 21.12.2023 | DEBIT TRANSFER TO PERFECT INNOVATION
1583 | 10.11.2023 | 3797 | A.P Enterprieses | 400 | 4012 | 89.91 | 35964 |  | DEBIT TO A.P ENTERPRISES | MUTHURA | 927/21.12.2023 | BILL MUTHURA 21.12.2023 | DEBIT TRANSFER TO PERFECT INNOVATION
1598 | 24.11.2023 | 3812 | A.P Enterprieses | 200 | 4952 | 89.91 | 17982 |  | DEBIT TO A.P ENTERPRISES | MUTHURA | 927/21.12.2023 | BILL MUTHURA 21.12.2023 | DEBIT TRANSFER TO PERFECT INNOVATION
1619 | 13.12.2023 | 3833 | A.P Enterprieses | 50 | 5030 | 89.91 | 4495.5 |  | DEBIT TO A.P ENTERPRISES | MUTHURA | 927/21.12.2023 | BILL MUTHURA 21.12.2023 | DEBIT TRANSFER TO PERFECT INNOVATION

## Sheet3
Subcontractor: | AP Enterprises
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
| Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | GST SD (18%) | Hold the Amount because the Qty. is more then the DPR | TDS in tally | Final Amount |  | Total Amount Paid | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 18%
57724
57724 | Kasoli Village OHT 375KL 16M staging Work | 2023-09-23 | 14, 16 | 703125 | 0 | 703125 | 126562.5 | 829687.5 | 7031 | 35156 |  |  | 126562.5 | 0 | 134615 | 660938 | tds-134615 | 198000 | 06-06-2023 NEFT/AXISP00395970528/RIUP23/536/A P ENTERPRISES 198000.00
57724 | GST Release Note |  | 14, 16 | 126562.5 | [11 empty] | 126562.5 |  | 65938 | 11-10-2023 NEFT/AXISP00433253775/RIUP23/2503/A P ENTERPRISES/IDIB000M779 65938.00
57724 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 126563 | 19-07-2024 NEFT O/W-YESIG42010144963-IDIB000M779-A P ENTERPRISES -RIUP24/1201 RS 1,26,563.00
[5 empty] | 0 | 0 | 0% | 0 | 0% | 0% | 0% | 0% | 0% |  |  | 0 | 57723
57723 | NIYAMU Village OHT 325 KL 12M Work |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 198000 | 06-06-2023 NEFT/AXISP00395970529/RIUP23/535/A P ENTERPRISES 198000.00
57202
57202 | Badakali Village OHT 150KL 12M staging Work | 2023-09-23 | 15 | 123750 | 0 | 123750 | 22275 | 146025 | 1238 | 6188 |  |  | 22275 | 0 | 23750 | 116324 | tds-23750 | 99000 | 25-05-2023 NEFT/AXISP00392601989/RIUP23/396/A P ENTERPRISES 99000.00
57202 | GST Release Note |  | 15 | 22275 | [11 empty] | 22275 |  | 17324 | 13-10-2023 NEFT/AXISP00434019639/RIUP23/2502/A P ENTERPRISES/IDIB000M779 17324.00
57202 | [17 empty] | 22275 | 19-07-2024 NEFT O/W-YESIG42010143589-IDIB000M779-A P ENTERPRISES-RIUP24/1200 RS 22,275.00
57201 | [16 empty] | 57201
57201 | BANNAGAR Village OHT 175KL 12 MTR STAGING Work | [15 empty] | 57724 | 99000 | 23-05-2023 NEFT/AXISP00392088476/RIUP23/355/A P ENTERPRISES 99000.00
57200
57200 | BADHAI KHURD Village OHT 200KL 12 MTR STAGING Work | [15 empty] | 57724 | 99000 | 23-05-2023 NEFT/AXISP00392088475/RIUP23/354/A P ENTERPRISES 99000.00
57200 | [17 empty] | 297000 | 27-09-2024 NEFT/AXISP00545360699/RIUP24/1985/A P ENTERPRISES/IDIB000M779 297000.00
57199
57199 | ROHANA KHURD Village OHT 225KL 12 MTR STAGING Work | [15 empty] | 57724 | 99000 | 25-05-2023 NEFT/AXISP00392601988/RIUP23/395/A P ENTERPRISES 99000.00
57199 | [17 empty] | 198000 | 27-09-2024 NEFT/AXISP00545360698/RIUP24/1984/A P ENTERPRISES/IDIB000M779 198000.00
54234
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2022-12-24 | 5 | 534736 | 0 | 534736 | 96252 | 630988 | 5347.36 | 26736.8 | 53473.6 | 53473.6 | 96252 | 43129 |  | 352576 |  | 352575 | 06-01-2023 NEFT/AXISP00352522093/RIUP22/1797/A P ENTERPRISES 352575.00
54234 | GST Release Note | 2023-01-16 | 5 | 96252 | 0 | 96252 | 0 | 96252 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96252 |  | 96252 | 21-01-2023 NEFT/AXISP00356444712/RIUP22/1906/A P ENTERPRISES ₹ 96,252.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2023-01-31 | 7 | 605360 | 39560.4 | 565799.6 | 101844 | 667643.6 | 5657.996 | 28289.98 | 56579.96 | 56579.96 | 101844 | 62783 |  | 355909 |  | 198000 | 23-01-2023 NEFT/AXISP00356693749/RIUP22/1957/A P ENTERPRISES ₹ 1,98,000.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2023-04-08 | 1 | 303939 | 0 | 303939 | 54709 | 358648 | 3039.39 | 15196.95 | 15196.95 | 30393.9 | 54709 |  |  | 240112 |  | 157909 | 08-02-2023 NEFT/AXISP00361822157/RIUP22/2121/A P ENTERPRISES 157909.00
54234 | GST Release Note | 2023-02-18 | 7 | 101844 | [11 empty] | 101844 |  | 101844 | 21-02-2023 NEFT/AXISP00364594735/RIUP22/2235/A P ENTERPRISES 101844.00
54234 | GST Release Note | 2023-05-23 | 1 | 54709 | [11 empty] | 54709 |  | 198000 | 13-04-2023 13-04-2023 NEFT/AXISP00381797403/SPUP23/0121/A P ENTERPRISES 198000.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2023-04-08 | 9, 10 | 282452 | 1480 | 280972 | 50574.96 | 331546.96 | 2809.72 | 14048.6 | 14048.6 | 28097.2 | 50574.96 |  | 56195 | 221967.88 | tds-56195 | 42112 | 02-05-2023 NEFT/AXISP00386671975/RIUP23/056/A P ENTERPRISES ₹ 42,112.00
54234 | GST Release Note |  | 9, 10 | 50574.96 | [11 empty] | 50574.96 |  | 54709 | 21-06-2023 NEFT/AXISP00399842955/RIUP23/747/A P ENTERPRISES 54709.00
54234 | Kedi Dhudha Dhari Village Pipe laying Work | 2024-05-13 | 4 | 678566 |  | 678566 | 122141.88 | 800707.88 | 6785.66 | 33928.3 | 67856.6 | 67856.6 | 122141.88 |  |  | 502138.84 |  | 196000 | 24-08-2023 NEFT/AXISP00418043570/RIUP23/1686/A P ENTERPRISES/IDIB000M779 196000.00
54234 | [17 empty] | 25968 | 07-09-2023 NEFT/AXISP00422860734/RIUP23/1856/A P ENTERPRISES/IDIB000M779 25968.00
54234 | [17 empty] | 49500 | 05-02-2024 NEFT/AXISP00468456762/RIUP23/4602/A P ENTERPRISES/IDIB000M779 49500.00
54234 | [17 empty] | 49500 | 16-02-2024 NEFT/AXISP00472106410/RIUP23/4732/A P ENTERPRISES/IDIB000M779 49500.00
54234 | [17 empty] | 400328 | 11-07-2024 NEFT/AXISP00517806262/RIUP24/1086/A P ENTERPRISES/IDIB000M779 400328.00
54234 | [17 empty] | 49500 | 29-08-2024 NEFT/AXISP00533190148/RIUP24/1562/A P ENTERPRISES/IDIB000M779 49500.00
54217
54217 | BHaisani Village Pipe laying Work | 2022-12-24 | 4 | 448841 | 0 | 448841 | 80791 | 529632 | 4488 | 22442 | 44884 | 44884 | 80791 | 33952 |  | 298191 |  | 200000 | 06-01-2023 NEFT/AXISP00352522094/RIUP22/1791/A P ENTERPRISES 200000.00
54217 | GST Release Note |  | 4 | 80791 |  | 80791 | 0 | 80791 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80791 |  | 80791 | 23-01-2023 NEFT/AXISP00356693741/RIUP22/1907/A P ENTERPRISES ₹ 80,791.00
54217 | BHaisani Village Pipe laying Work | 2023-08-19 | 8, 9 | 438425 |  | 438425 | 78916.5 | 517341.5 | 4384 | 21921 | 21921 | 43843 | 78916.5 |  | 87685 | 346356 | tds-87685 | 98191 | 06-03-2023 NEFT/AXISP00369190886/RIUP22/2484/A P ENTERPRISES 98191.00
54217 | GST Release Note |  | 8, 9 | 78916.5 | [11 empty] | 78916.5 |  | 346356 | 31-08-2023 NEFT/AXISP00419854902/RIUP23/1807/A P ENTERPRISES/IDIB000M779 ₹ 3,46,356.00
54217 | [17 empty] | 74250 | 05-02-2024 NEFT/AXISP00468456765/RIUP23/4599/A P ENTERPRISES/IDIB000M779 74250.00
52830
52830 | Panchenda Kallan Village Pipe laying Work. | 2022-11-15 | 1 | 2016203.5 | 58442 | 1957762 | 352397.16 | 2310159.16 | 19578 | 97888 | 97888 | 195776 | 352397.16 | 516724 |  | 1029908 |  | 495000 | 20-10-2022 NEFT/AXISP00330252341/RIUP22/1062/A P ENTERPRISES 495000.00
52830 | GST Release Note |  | 1 | 352397.16 |  | 352397.16 | 0 | 352397.16 | 0 | 0 | 0 | 0 | 0 | 0 |  | 352397 |  | 534908 | 22-11-2022 NEFT/AXISP00339521128/RIUP22/1311/A P ENTERPRISES 534908.00
52830 | Hold amount release note | 2022-12-03 |  | 450000 |  | 450000 |  | 450000 | [7 empty] | 450000 |  | 450000 | 03-12-2022 NEFT/AXISP00343125334/RIUP22/1399/A P ENTERPRISES 450000.00
52830 | Pancheda Kallan Village Pipe laying Work. | 2023-01-10 | 6 | 1047594 | 17982 | 1029612 | 185330.16 | 1214942.16 | 10296 | 51481 | 102961 | 102961 | 185330.16 | 0 |  | 761913 |  | 352396 | 21-12-2022 NEFT/AXISP00347813404/RIUP22/1593/A P ENTERPRISES 352396.00
52830 | GST Release Note |  | 6 | 185330 |  | 185330 | 0 | 185330 | 0 | 0 |  |  | 0 |  |  | 185330 |  | 198000 | 18-01-2023 NEFT/AXISP00355710810/RIUP22/1897/A P ENTERPRISES ₹ 1,98,000.00
52830 | Pachenda Kalan Village Pipe Laying Work | 2023-08-08 | 7,8 | 600724.53 | 77323 | 523401.53 | 94212.2754 | 617613.8054 | 5234.0153 | 26170.0765 | 0 | 0 | 94212.2754 | 43786 | 64680 | 448211.4382 | tds-64680 | 495000 | 23-02-2023 NEFT/AXISP00365243860/RIUP22/2284/A P ENTERPRISES 495000.00
52830 | Pachenda Kalan Village Pipe Laying Work | 2023-08-26 | 12,13 | 1119282.75 | 885 | 1118397.75 | 201311.595 | 1319709.345 | 11183.9775 | 55919.8875 | 0 | 0 | 201311.595 | 109074 | 223680 | 942219.885 | tds-223680 | 49500 | 13-04-2023 NEFT/AXISP00381797401/SPUP23/0119/A P ENTERPRISES 49500.00
52830 | GST Release Note |  | 7&8 12&13 | 295523.8704 | [11 empty] | 295523.8704 |  | 19413 | 10-05-2023 10-05-2023 NEFT/AXISP00389200590/SPUP23/0300/A P ENTERPRISES 19413.00
52830 | [17 empty] | 185330 | 12-05-2023 NEFT/AXISP00389894115/RIUP23/202/A P ENTERPRISES 185330.00
52830 | [17 empty] | 198000 | 15-06-2023 NEFT/AXISP00398797334/RIUP23/681/A P ENTERPRISES 198000.00
52830 | [17 empty] | 250212 | 28-08-2023 NEFT/AXISP00418849234/RIUP23/1635/A P ENTERPRISES/IDIB000M779 250212.00
52830 | [17 empty] | 942220 | 31-08-2023 NEFT/AXISP00419716234/RIUP23/1806/A P ENTERPRISES/IDIB000M779 942220.00
52830 | [17 empty] | 24750 | 05-02-2024 NEFT/AXISP00468456763/RIUP23/4601/A P ENTERPRISES/IDIB000M779 24750.00
52830 | [17 empty] | 295524 | 19-07-2024 NEFT O/W-YESIG42010143588-IDIB000M779-A P ENTERPRISES -RIUP24/1203 RS 2,95,524.00
52830 | [17 empty] | 99000 | 29-08-2024 NEFT/AXISP00533190154/RIUP24/1563/A P ENTERPRISES/IDIB000M779 99000.00
53075
53075 | Pachenda Khurd Village Pipe laying Work | 2022-12-24 | 3 | 817552 | 80919 | 736633 | 132594 | 869227 | 7366.33 | 36831.65 | 73663.3 | 73663.3 | 132594 | 216163 |  | 328945 |  | 148500 | 08-11-2022 NEFT/AXISP00335609453/RIUP22/1208/A P ENTERPRISES 148500.00
53075 | GST Release Note | 2023-01-16 | 3 | 132594 | 0 | 132594 | 0 | 132594 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132594 |  | 180446 | 07-01-2023 NEFT/AXISP00353064335/RIUP22/1742/A P ENTERPRISES 180446.00
53075 | Pachenda Khurd Village Pipe laying Work | 2023-04-10 | 2 | 461312.48 | 0 | 461312.48 | 83036 | 544348.48 | 4613.1248 | 23065.624 | 23065.624 | 46131.248 | 83036 | 33987 |  | 330450 |  | 132594 | 18-01-2023 NEFT/AXISP00355697030/RIUP22/1883/A P ENTERPRISES ₹ 1,32,594.00
53075 | GST Release Note | 2023-05-23 | 2 | 83036 |  | 83036 | 0 | 83036 | 0 | 0 |  |  | 0 |  |  | 83036 |  | 198000 | 23-01-2023 NEFT/AXISP00356620188/RIUP22/1937/A P ENTERPRISES ₹ 1,98,000.00
53075 | Pachenda Khurd Village Pipe laying Work | 2023-08-19 | 10, 11 | 694130 |  | 694130 | 124943.4 | 819073.4 | 6941.3 | 34706.5 | 34706.5 | 69413 | 124943.4 | 70108 | 89326 | 478254.7 | tds-89326 | 99000 | 14-03-2023 NEFT/AXISP00371304701/RIUP22/2570/A P ENTERPRISES 99000.00
53075 | GST Release Note |  | 10, 11 | 124943.4 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | 124943.4 |  | 148500 | 13-04-2023 13-04-2023 NEFT/AXISP00381797402/SPUP23/0120/A P ENTERPRISES 148500.00
53075 | [17 empty] | 83036 | 21-06-2023 NEFT/AXISP00399842954/RIUP23/748/A P ENTERPRISES 83036.00
53075 | [14 empty] | 49500 |  | TDS-49500 | 198000 | 28-07-2023 NEFT/AXISP00410084836/RIUP23/1264/A P ENTERPRISES 198000.00
53075 | [17 empty] | 297000 | 28-08-2023 NEFT/AXISP00418870939/RIUP23/1757/A P ENTERPRISES/IDIB000M779 297000.00
53075 | [17 empty] | 99000 | 05-02-2024 NEFT/AXISP00468456764/RIUP23/4600/A P ENTERPRISES/IDIB000M779 99000.00
53075 | [17 empty] | 297000 | 23-08-2024 NEFT/AXISP00531577842/SKUP24/160/A P ENTERPRISES/IDIB000M779 297000.00
55800
55800 | Bhoop Khedi Village pipe laying Work | 2023-06-01 | 7 | 989955.27 | 0 | 989955 | 178191.9 | 1168146.9 | 9900 | 49498 | 49498 | 98996 | 178191.9 | 136068.82 |  | 645994 |  | 198000 | 02-05-2023 NEFT/AXISP00386712950/SPUP23/0355/A P ENTERPRISES ₹ 1,98,000.00
55800 | Bhoop Khedi Village pipe laying Work | 2023-08-19 | 11, 12 | 223424 | 162280 | 61144 | 11005.92 | 72149.92 | 611 | 3057 | 3057 | 6114 | 11005.92 | 0 | 12229 | 48305 | tds-12229 | 447994 | 15-06-2023 NEFT/AXISP00398738898/RIUP23/643/A P ENTERPRISES 447994.00
55800 | GST Release Note |  | 7 | 178191.9 | [11 empty] | 178191.9 |  | 48305 | 31-08-2023 NEFT/AXISP00419854901/RIUP23/1808/A P ENTERPRISES/IDIB000M779 ₹ 48,305.00
55800 | GST Release Note |  | 11, 12 | 11005.92 | [11 empty] | 11005.92 |  | 178192 | 01-02-2024 NEFT/AXISP00467277204/RIUP23/4400/A P ENTERPRISES/IDIB000M779 178192.00
55800 | Bhoop Khedi Village pipe laying Work | 2024-10-15 | 8 | 176276 | 0 | 176276 | 31729.68 | 208005.68 | 1763 | 8814 | 17627.6 | 17628 | 31729.68 | 0 | 0 | 130443 |  | 49500 | 29-08-2024 NEFT/AXISP00533190151/RIUP24/1559/A P ENTERPRISES/IDIB000M779 49500.00
59119
59119 | Morkooka Village pipe laying Work | 2023-08-29 | 13, 14 | 670996 | 0 | 670996 | 120779.28 | 791775.28 | 6710 | 33550 | 33550 | 67100 | 120779.28 | 0 | 134199 | 530086 | tds-134199 | 530086 | 06-09-2023 NEFT/AXISP00422274697/RIUP23/1858/A P ENTERPRISES/IDIB000M779 530086.00
59119 | Morkooka Village pipe laying Work | 2024-01-19 | 24 | 460940 |  | 460940 | 82969.2 | 543909.2 | 4609 | 23047 | 23047 | 46094 | 82969.2 | 100150 |  | 263993 |  | 148500 | 05-02-2024 NEFT/AXISP00468190239/RIUP23/4584/A P ENTERPRISES/IDIB000M779 148500.00
59119 | GST Release Note |  | 13, 14 | 120779.28 | [11 empty] | 120779.28 |  | 247500 | 05-02-2024 NEFT/AXISP00468456761/RIUP23/4598/A P ENTERPRISES/IDIB000M779 247500.00
59119 | GST Release Note |  | 24 | 82969.2 | [11 empty] | 82969.2 |  | 99000 | 16-02-2024 NEFT/AXISP00472106411/RIUP23/4733/A P ENTERPRISES/IDIB000M779 99000.00
59119 | [17 empty] | 82969 | 24-06-2024 NEFT/AXISP00511368166/RIUP24/0947/A P ENTERPRISES/IDIB000M779 82969.00
59578 | [16 empty] | 59578
59578 | Sikandarpur Village OHT 200KL 14M staging Work | 2023-09-23 | 13,15 | 442500 | 0 | 442500 | 79650 | 522150 | 4425 | 22125 | 0 | 0 | 79650 |  | 86500 | 415950 | tds-86500 | 217950 | 11-10-2023 NEFT/AXISP00433203146/RIUP23/2583/A P ENTERPRISES/IDIB000M779 217950.00
59578 | GST Release Note |  | 15 | 79650 | [11 empty] | 79650 |  | 49500 | 20-07-2024 NEFT/AXISP00520155444/RIUP24/1210/A P ENTERPRISES/IDIB000M779 49500.00
59578 | [17 empty] | 247500 | 29-08-2024 NEFT/AXISP00533190152/RIUP24/1558/A P ENTERPRISES/IDIB000M779 247500.00
59709
59709 | Seemli Village Pipe laying Work | 2023-10-09 | 15, 16, 18 | 986968.4 | 24871.2 | 962097.2 | 173177.496 | 1135274.696 | 9620.972 | 48104.86 | 48104.86 | 96209.72 | 173177.496 | 178264 | 192419 | 581793 | tds-192419 | 581792 | 17-10-2023 NEFT/AXISP00435127245/RIUP23/2656/A P ENTERPRISES/IDIB000M779 581792.00
59709 | GST Release Note |  | 15, 16, 18 | 173177.496 | [11 empty] | 173177.496 |  | 99000 | 02-05-2024 NEFT/AXISP00496215186/RIUP24/0359/A P ENTERPRISES/IDIB000M779 99000.00
59709 | [17 empty] | 297000 | 30-04-2024 NEFT/AXISP00495097365/RIUP24/0357/A P ENTERPRISES/IDIB000M779 297000.00
59709 | [17 empty] | 173177 | 26-06-2024 NEFT/AXISP00511923118/RIUP24/0946/A P ENTERPRISES/IDIB000M779 173177.00
59709 | [17 empty] | 99000 | 18-09-2024 NEFT/AXISP00541733393/RIUP24/1838/A P ENTERPRISES/IDIB000M779 99000.00
59864
59864 | Rohana Khurd Village Pipe laying Work | 2023-10-11 | 15, 17,19 | 1100033 | 265241 | 834792 | 150262.56 | 985054.56 | 8347.92 | 41739.6 | 41739.6 | 83479.2 | 150262.56 | 58144 | 166958 | 601342 | tds-166958 | 601341 | 02-11-2023 NEFT/AXISP00439799501/RIUP23/2902/A P ENTERPRISES/IDIB000M779 601341.00
59864 | Rohana Khurd Village Pipe laying Work | 2024-01-06 | 19, 21 | 388928 |  | 388928 | 70007.04 | 458935.04 | 3889.28 | 19446.4 | 38892.8 | 38892.8 | 70007.04 | 35597 |  | 252210 |  | 148500 | 04-01-2024 NEFT/AXISP00459277739/RIUP23/4105/A P ENTERPRISES/IDIB000M779 148500.00
59864 | GST Release Note |  | 19, 21 | 220269.6 | [11 empty] | 220269.6 |  | 165371 | 22-03-2024 NEFT/AXISP00483444832/RIUP23/5207/A P ENTERPRISES/IDIB000M779 165371.00
59864 | Rohana Khurd Village Pipe laying Work | 2024-05-13 | 6, 3 | 158400 |  | 158400 | 28512 | 186912 | 1584 | 7920 | 15840 | 15840 | 28512 |  |  | 117216 |  | 148500 | 02-05-2024 NEFT/AXISP00496215185/RIUP24/0360/A P ENTERPRISES/IDIB000M779 148500.00
59864 | [17 empty] | 99000 | 20-07-2024 NEFT/AXISP00520155441/RIUP24/1211/A P ENTERPRISES/IDIB000M779 99000.00
59864 | [17 empty] | 99000 | 29-08-2024 NEFT/AXISP00533190150/RIUP24/1560/A P ENTERPRISES/IDIB000M779 99000.00
60067
60067 | MUSTAFABAD Village BALANCE PIPE LAYING Work | 2023-11-06 | 20,22 | 1043683 | 78762 | 964921 | 173685.78 | 1138606.78 | 9649.21 | 48246.05 | 96492.1 | 96492.1 | 173685.78 |  |  | 714042 |  | 346500 | 04-01-2024 NEFT/AXISP00459277738/RIUP23/4106/A P ENTERPRISES/IDIB000M779 346500.00
60067 | GST Release Note |  | 20, 22 | 173685.78 | [11 empty] | 173685.78 |  | 367541 | 12-01-2024 NEFT/AXISP00462196165/RIUP23/4237/A P ENTERPRISES/IDIB000M779 367541.00
60067 | [17 empty] | 173686 | 22-03-2024 NEFT/AXISP00483612633/RIUP23/5227/A P ENTERPRISES/IDIB000M779 173686.00
60069
60069 | Kutubpur Village CONSTRUCTION OF PIPELINE Work | 2023-11-06 | 18, 20 | 747459 | 4060 | 743399 | 133811.82 | 877210.82 | 7433.99 | 37169.95 | 74339.9 | 74339.9 | 133811.82 | 15444 |  | 534671 |  | 247500 | 04-01-2024 NEFT/AXISP00459277737/RIUP23/4107/A P ENTERPRISES/IDIB000M779 247500.00
60069 | GST Release Note |  | 18, 20 | 133811.82 | [11 empty] | 133811.82 |  | 287171 | 12-01-2024 NEFT/AXISP00462196164/RIUP23/4235/A P ENTERPRISES/IDIB000M779 287171.00
60069 | Kutubpur Village CONSTRUCTION OF PIPELINE WORK | 2024-02-12 | 25 | 809672 | 292245 | 517427 | 93136.86 | 610563.86 | 5174.27 | 25871.35 | 51742.7 | 51742.7 | 93136.86 | 148246 |  | 234650 |  | 234650 | 31-03-2024 NEFT/AXISP00486642367/RIUP23/5110/A P ENTERPRISES/IDIB000M779 234650.00
60069 | GST Release Note |  | 25 | 93136.86 | [11 empty] | 93136.86 |  | 133812 | 31-03-2024 NEFT/AXISP00486642366/RIUP23/5226/A P ENTERPRISES/IDIB000M779 133812.00
60069 | [17 empty] | 100000 | cash given as per Tally ledger
60069 | [17 empty] | 99000 | 29-08-2024 NEFT/AXISP00533190149/RIUP24/1561/A P ENTERPRISES/IDIB000M779 99000.00
60090
60090 | NIYAMU Village BALANCE PIPE LAYING Work | 2002-11-06 | 21,23 | 802210 |  | 802210 | 144397.8 | 946607.8 | 8022.1 | 40110.5 | 80221 | 80221 | 144397.8 | 19725 |  | 573910 |  | 297000 | 04-01-2024 NEFT/AXISP00459277736/RIUP23/4108/A PENTERPRISES/IDIB000M779 297000.00
60090 | GST Release Note |  | 21,23 | 144397.8 | [11 empty] | 144397.8 |  | 200000 | 15-03-2024 NEFT/AXISP00481321981/RIUP23/4939/A P ENTERPRISES/IDIB000M779 200000.00
60090 | [17 empty] | 144398 | 06-04-2024 NEFT/AXISP00489186679/RIUP23/5244/A P ENTERPRISES/IDIB000M779 144398.00
60090 | [17 empty] | 49500 | 29-08-2024 NEFT/AXISP00533190153/RIUP24/1557/A P ENTERPRISES/IDIB000M779 49500.00
[6 empty] | 20153787.72 | 3379208.7664 |  | 187733.6156 | 938670.078 | 1180397.694 | 1586222.228 | 3379208.7664 | 1821344.82 | 1321736 | 16705844.6296 |  | 18498649 | Total Paid
[18 empty] | -1792804.3704 | Balance payable