## Sheet1
Subcontractor: | AARHAM INTERNATIONAL
State: | Uttar Pradesh |  | AARHAM INTERNATIONAL |  |  |  |  | Pipe Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | Total_Amount | UTR | Advance
[7 empty] | 18% |  | 2% | 5% | 10% | 10% | 18%
51760 | [15 empty] | 51760
51760 | Yarpur Village Pipeline laying work | 2022-10-17 | 2 | 1198373 | 0 | 1198373 | 215707 | 1414080 | 23967 | 119837 |  | 119837 | 215707 | 215632 | 719100 |  | 220500 | 08-08-2022 NEFT/AXISP00310461061/RIUP22/470/AARHAM INTERNATI 220500.00 | -148377
51760 | GST Release Note | 2022-11-02 | 2 | 215707 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215707 |  | 490000 | 18-10-2022 NEFT/AXISP00329290828/RIUP22/1030/AARHAM INTERNAT 490000.00
51760 | Yarpur Village Pipeline laying work | 2023-09-19 | 7 | 105083 | 0 | 105083 | 18915 | 123998 | 2479.96 | 5254 | 10508 | 10508 | 18915 | 11709 | 64624 |  | 8600 | 20-10-2022 NEFT/AXISP00330319204/RIUP22/1075/AARHAM INTERNAT 8600.00
51760 | Yarpur Village Pipeline laying work | 2023-09-19 | 8 | 755469 | 89652 | 665817 | 119847 | 785664 | 13316 | 33291 | 66582 | 66582 | 119847 | 8354 | 477692 |  | 215707 | 22-11-2022 NEFT/AXISP00339527010/RIUP22/1315/AARHAM INTERNAT 215707.00
51760 | GST | 2023-10-26 | 7 | 18915 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18915 |  | 50000 | 15-12-2022 NEFT/AXISP00346453829/RIUP22/1521/AARHAM INTERNAT 50000.00
51760 | GST | 2023-10-26 | 8 | 119847 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119847 |  | 147000 | 07-02-2023 NEFT/AXISP00361424978/RIUP22/2129/AARHAM INTERNAT ₹ 1,47,000.00
51760 | [16 empty] | 98000 | 19-06-2023 NEFT/AXISP00399550939/RIUP23/731/AARHAM INTERNATI 98000.00
51760 | [16 empty] | 232691 | 04-10-2023 NEFT/AXISP00430543821/RIUP23/2412A/AARHAM INTERNATION 232691.00
51760 | [16 empty] | 65002 | 04-10-2023 NEFT/AXISP00430543820/RIUP23/2411A/AARHAM INTERNATION 65002.00
51760 | [16 empty] | 138762 | 08-11-2023 NEFT/AXISP00441999414/RIUP23/2937/AARHAM INTERNATION 138762.00
51760 | [16 empty] | 98000 | 08-12-2023 NEFT/AXISP00451236003/RIUP23/3659/AARHAM INTERNATION 98000.00
51760
51760
52429 | [15 empty] | 52429
52429 | Bhogimazra Village Pipeline laying work | 2022-10-07 | 1 | 209791 | 0 | 209791 | 37762 | 247553 | 4195.82 | 10490 | 10490 | 20979 | 37762 | 17255 | 146381.18 |  | 147000 | 20-10-2022 NEFT/AXISP00330252336/RIUP22/1059/AARHAM INTERNAT 147000.00 | -113022.68
52429 | GST | 2022-11-02 | 1 | 37762 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 37762 |  | 37145 | 22-11-2022 NEFT/AXISP00339527011/RIUP22/1316/AARHAM INTERNAT 37145.00
52429 | Bhogimazra Village Pipeline laying work | 2023-01-06 | 5 | 249850 | 0 | 249850 | 44973 | 294823 | 4997 | 12493 | 24985 | 24985 | 44973 | 63367 | 119023 |  | 119023 | 18-01-2023 NEFT/AXISP00355694664/RIUP22/1829/AARHAM INTERNAT 119023.00
52429 | GST | 2023-02-20 | 5 | 44973 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 44973 |  | 49000 | 20-02-2023 NEFT/AXISP00364387945/RIUP22/2229/AARHAM INTERNAT 49000.00
52429 | Bhogimazra Village Pipeline laying work | 2023-01-06 | 5 | 62098 | 0 | 62098 | 11178 | 73276 | 1241.96 | 3105 | 6210 | 6210 | 11178 | 14615 | 30716.04 |  | 44973 | 24-02-2023 NEFT/AXISP00365286192/RIUP22/2278/AARHAM INTERNAT 44973.00
52429 | GST Release Note |  | 5 | 11178 | 0 |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 11178 |  | 29400 | 11-04-2023 NEFT/AXISP00380905284/SPUP23/0071/AARHAM INTERNAT 29400.00
52429 | Bhogimazra Village Pipeline laying work | 2023-09-05 | 6 | 301032 | 47687 | 253345 | 45602 | 298947 | 5066.9 | 12667 | 25335 | 25335 | 45602 | 5278 | 179663.1 |  | 98000 | 16-06-2023 NEFT/AXISP00399073691/RIUP23/693/AARHAM INTERNATI 98000.00
52429 | GST Release Note | 2023-10-26 | 6 | 45602 |  | 45602 | 0 | 45602 |  | 0 | 0 | 0 | 0 | 0 | 45602 |  | 98000 | 11-09-2023 NEFT/AXISP00423685740/RIUP23/1959/AARHAM INTERNATION 98000.00
52429 | [16 empty] | 11178 | 19-10-2023 NEFT/AXISP00435643032/RIUP23/2754/AARHAM INTERNATION 11178.00
52429 | [16 empty] | 45602 | 01-11-2023 NEFT/AXISP00439457388/RIUP23/2936/AARHAM INTERNATION 45602.00
52429 | [16 empty] | 49000 | 29-11-2023 NEFT/AXISP00439456856/RIUP23/3485/AARHAM INTERNATION 49000.00
52429
53817 | [15 empty] | 53817
53817 | Bibipur Hatiya Village Pipeline laying work | 2022-12-15 | 4 | 819165 | 63049 | 756116 | 136101 | 892217 | 15122.32 | 37806 | 75612 | 75612 | 136101 | 99041 | 452923 |  | 452923 | 03-01-2023 NEFT/AXISP00351384277/RIUP22/1744/AARHAM INTERNAT 452923.00 | -186173
53817 | GST Release Note |  | 4 | 136101 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 136101 |  | 136101 | 24-01-2023 NEFT/AXISP00356990172/RIUP22/1976/AARHAM INTERNAT ₹ 1,36,101.00
53817 | Bibipur Hatiya Village Pipeline laying work | 2023-01-27 | 6 | 351667 | 0 | 351667 | 63300 | 414967 | 7033 | 17583 | 35167 | 35167 | 63300 | 71654 | 185063 |  | 185036 | 31-01-2023 NEFT/AXISP00358425205/RIUP22/2043/AARHAM INTERNAT 185063.00
53817 | GST Release Note |  | 6 | 63300 | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 63300 |  | 63300 | 24-02-2023 NEFT/AXISP00365286191/RIUP22/2279/AARHAM INTERNAT 63300.00
53817 | Bibipur Hatiya Village Pipeline laying work | 2023-07-24 | 3 | 61692 | 4055.32 | 65747.32 | 11835 | 77582 | 1315 | 3287 | 6575 | 6575 | 11835 | 1224 | 46771 |  | 98000 | 13-04-2023 13-04-2023 NEFT/AXISP00381797400/SPUP23/0122/AARHAM INTERNAT 98000.00
53817 | Bibipur Hatiya Village Pipeline laying work | 2023-07-24 | 4 | 453007.5 | 66762 | 386245.5 | 69524 | 455770 | 7725 | 19312 | 0 | 0 | 69524 | 0 | 359209 |  | 78400 | 16-06-2023 NEFT/AXISP00399073687/RIUP23/694/AARHAM INTERNATI 78400.00
53817 | GST Release Note |  | 3 | 11835 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11835 |  | 46771 | 02-08-2023 NEFT/AXISP00411959004/RIUP23/1322/AARHAM INTERNAT ₹ 46,771.00
53817 | GST Release Note |  | 4 | 69524 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 69524 |  | 182810 | 02-08-2023 NEFT/AXISP00411959005/RIUP23/1323/AARHAM INTERNAT ₹ 1,82,810.00
53817 | [16 empty] | 98000 | 21-08-2023 NEFT/AXISP00417026989/RIUP23/1632/AARHAM INTERNAT 98000.00
53817 | [16 empty] | 81358 | 24-08-2023 NEFT/AXISP00418043566/RIUP23/1673/AARHAM INTERNATION 81358.00
53817 | [16 empty] | 49000 | 14-12-2023 NEFT/AXISP00452866512/RIUP23/3720/AARHAM INTERNATION 49000.00
53817 | [16 empty] | 39200 | 02-02-2024 NEFT/AXISP00467749363/RIUP23/4559/AARHAM INTERNATION/SBIN0011556 39200.00
53817
55128 | [15 empty] | 55128
55128 | HASANPUR Village Pipe laying work | 2023-02-28 | 7 | 572623.25 | 40532 | 532091.25 | 95776 | 627867 | 10641.825 | 26604.5625 | 53209.125 | 53209.125 | 95776 | 38678 | 349748 |  | 196000 | 08-03-2023 NEFT/AXISP00369766204/RIUP22/2502/AARHAM INTERNAT 196000.00 | -196001
55128 | HASANPUR Village Pipe laying work | 2023-05-09 | 1 | 407456 | 0 | 407456 | 73342 | 480798 | 8149.12 | 20372.8 | 40745.6 | 40745.6 | 73342 | 97239 | 200204 |  | 98000 | 21-03-2023 NEFT/AXISP00373201702/RIUP22/2685/AARHAM INTERNAT 98000.00
55128 | GST Release Note | 2023-05-18 | 7 | 95776 |  |  | 0 | 0 | 0 | [5 empty] | 95776 |  | 58800 | 27-03-2023 NEFT/AXISP00374603537/RIUP22/2738/AARHAM INTERNAT 58800.00
55128 | GST Release Note | 2023-05-18 | 1 | 73342 | [10 empty] | 73342 |  | 98000 | 11-04-2023 NEFT/AXISP00380905282/SPUP23/0073/AARHAM INTERNAT 98000.00
55128 | [16 empty] | 95776 | 20-05-2023 NEFT/AXISP00391552051/RIUP23/303/AARHAM INTERNATI ₹ 95,776.00
55128 | [16 empty] | 99153 | 20-05-2023 NEFT/AXISP00391552052/RIUP23/302/AARHAM INTERNATI ₹ 99,153.00
55128 | [16 empty] | 98000 | 29-05-2023 NEFT/AXISP00392949341/RIUP23/426/AARHAM INTERNATI 98000.00
55128 | [16 empty] | 73342 | 28-06-2023 NEFT/AXISP00401332287/RIUP23/866/AARHAM INTERNATI 73342.00
55128 | [16 empty] | 98000 | 26-09-2023 NEFT/AXISP00427655665/RIUP23/2284/AARHAM INTERNATION 98000.00
55128
57798
57798 | Ahmadpur Village Pipeline laying work | 2023-06-06 | 2 | 646976 | 18014 | 628962 | 113213 | 742175 | 12579.24 | 31448 | 62896 | 62896 | 113213 | 3450 | 455693 |  | 455693 | 16-06-2023 NEFT/AXISP00399009125/RIUP23/661/AARHAM INTERNATI 455693.00 | -49000
57798 | Ahmadpur Village Pipeline laying work | 2023-10-31 | 9 | 398973 | 0 | 398973 | 71815 | 470788 | 7979.46 | 19949 | 39897 | 39897 | 71815 | 96271 | 194980 |  | 113213 | 31-07-2023 NEFT/AXISP00410478614/RIUP23/1272/AARHAM INTERNAT ₹ 1,13,213.00
57798 | GST |  | 2 | 113213 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113213 |  | 196000 | 09-11-2023 NEFT/AXISP00442541904/RIUP23/3172/AARHAM INTERNATION 196000.00
57798 | GST |  | 9 | 71815 |  | 71815 | 0 | 71815 | 0 | 0 | 0 | 0 | 0 | 0 | 71815 |  | 71815 | 30-11-2023 NEFT/AXISP00447912056/RIUP23/3537/AARHAM INTERNATION 71815.00
57798 | Ahmadpur Village Pipeline laying work | 2024-01-20 | 12 | 62610 | 0 | 62610 | 11270 | 73880 | 1252.2 | 3131 | 6261 | 6261 | 11270 | 1765 | 43940 |  | 42920 | 06-03-2024 NEFT/AXISP00477669910/RIUP23/4644/AARHAM INTERNATION/SBIN0011556 42920.00
57798 | GST |  | 12 | 11270 | [10 empty] | 11270 |  | 11270 | 20-03-2024 NEFT/AXISP00482717103/RIUP23/5148/AARHAM INTERNATION/SBIN0011556 11270.00
57798 | [16 empty] | 49000 | 18-09-2024 NEFT/AXISP00541733387/RIUP24/1831/AARHAM INTERNATION/SBIN0011556 49000.00
57798
57798
59739 | [15 empty] | 59739
59739 | Nai Nagla Sakauti Village Pipeline laying work | 2022-11-30 | 10 | 466158 | 36028 | 430130 | 77423 | 507553 | 8602.6 | 21507 | 43013 | 43013 | 77423 | 175368 | 138626 |  | 98000 | 13-10-2023 NEFT/AXISP00434019644/RIUP23/2633/AARHAM INTERNATION 98000.00 | -147002
59739 | GST |  | 10 | 77423 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77423 |  | 40627 | 15-12-2023 NEFT/AXISP00453272887/RIUP23/3728/AARHAM INTERNATION 40627.00
59739 | [16 empty] | 77424 | 30-12-2023 NEFT/AXISP00457527704/RIUP23/4001/AARHAM INTERNATION 77424.00
59739 | [16 empty] | 98000 | 08-01-2024 NEFT/AXISP00460674629/RIUP23/4168/AARHAM INTERNATION ₹ 98,000.00
59739 | [16 empty] | 49000 | 13-12-2024 NEFT/AXISP00583928106/RIUP24/2691/AARHAM INTERNATION/SBIN0011556 49000.00
59740 | [15 empty] | 59740
59740 | KADARPUR VILLAGE Pipe Line & FHTC Work | 2023-12-31 | 11 | 356029 | 0 | 356029 | 64085 | 420114 | 7120.58 | 17801 | 35603 | 35603 | 64085 | 40934 | 218967 |  | 196000 | 23-10-2023 NEFT/AXISP00436449476/RIUP23/2823/AARHAM INTERNATION 196000.00 | 0
59740 | GST |  | 11 | 64085 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64085 |  | 22967 | 17-01-2024 NEFT/AXISP00463099941/RIUP23/4201/AARHAM INTERNATION/SBIN0011556 22967.00
59740 | [16 empty] | 64085 | 05-02-2024 NEFT/AXISP00468222688/RIUP23/4407/AARHAM INTERNATION/SBIN0011556 64085.00
62902 | [15 empty] | 62902
62902 | Janipur village - Pipeline work | 2024-03-18 | 18 | 641752 |  | 641752 | 115515 | 757267 | 12835.04 | 32088 | 64175 | 64175 | 115515 | 84523 | 383956 |  | 196000 | 14-05-2024 NEFT/AXISP00499817094/RIUP24/0503/AARHAM INTERNATION/SBIN0011556 196000.00 | -120860
62902 |  |  | 18 | 115515 | [10 empty] | 115515 |  | 274400 | 03-08-2024 NEFT/AXISP00524511281/RIUP24/1351/AARHAM INTERNATION/SBIN0011556 274400.00
62902 | Janipur village - FHTC work | 2024-12-04 | A1/2024-25/01 | 50624 | 0 | 50624 | 9112 | 59736 | 1012.48 | 2531 | 5062 | 5062 | 9112 | 0 | 36957 |  | 98000 | 18-09-2024 NEFT/AXISP00541733386/RIUP24/1830/AARHAM INTERNATION/SBIN0011556 98000.00
62902 | GST |  | 1 | 9112 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9112 |  | 98000 | 15-10-2024 NEFT/AXISP00553688662/RIUP24/2204/AARHAM INTERNATION/SBIN0011556 98000.00
62902
[5 empty] | 94574 |  |  |  |  | 450557.3625 | 612325.725 | 742651.725 | 1406295 | 1046357 | 6210531.32 |  | 7170967 | Total Paid
[17 empty] | -960435.68 | Balance Payable | -960435.68
AARHAM INTERNATIONAL
2025-01-20
[12 empty] | Total Hold |  | 1805534.8125
[12 empty] | DPR Excess Debit |  | 1046357
[12 empty] | Advance/ Surplus |  | -960435.68
[12 empty] | GST Remaining |  | 0
[5 empty] | Item no | dpr | Cum | Extra | Rate | Amt
[5 empty] | B.O.E | 39.12 | 353.28 | 314.16 | 50 | 15708
[5 empty] | Restoration BOE | 39.12 | 353.28 | 314.16 | 200 | 62832
[5 empty] | 63MM DIA | 2429 | 2726.1 | 297.1 | 85 | 25253.5
[5 empty] | 90MM DIA | 440 | 503.8 | 63.8 | 95 | 6061
[5 empty] | 200MM DIA | 318 | 526.5 | 208.5 | 125 | 26062.5
0
[10 empty] | 0 |  | 97239 | pending hold
0
0
[10 empty] | 135917 | upto date hold
[7 empty] | 353.25 |  |  | 38678 | already hold