## Sheet1
Subcontractor: | Abhinandini Enterprises
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Hydro_Testing | On_Commission | Painting & Finishing hold | GST_SD_Amount | DPR EXCESS | Final_Amount |  | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 10% |  |  | 10% | 18%
52758
52758 | Panchenda Kalan Village Pump House Work | 2022-11-10 | 2 | 381000 | 54603 | 326397 | 58751 | 385148 | 3263.97 | 32639.7 |  |  |  | 58751 |  | 290493 |  | 250000 | 30-11-2022 NEFT/AXISP00341668618/RIUP22/1370/ABINANDNI ENTER 250000.00
52758 | GST Release Note |  | 2 | 58751 | [11 empty] | 58751 |  | 40493 | 03-01-2023 NEFT/AXISP00351384281/RIUP22/1752/ABINANDNI ENTER 40493.00
[16 empty] | 0 |  | 58751 | 24-01-2023 NEFT/AXISP00356837275/RIUP22/1916/ABINANDNI ENTER 58751.00
53258
53258 | Medpur Village Pump House Work |  | 3 | 370000 | 69075 | 311925 | 56146.5 | 368071.5 | 3119.25 | 31192.5 |  |  |  | 56146.5 |  | 277613.25 |  | 277613 | 07-02-2023 NEFT/AXISP00361376408/RIUP22/2107/ABINANDNI ENTER ₹ 2,77,613.00
53258 | GST Relase Note |  | 3 | 56146 | [11 empty] | 56146 |  | 56147 | 12-05-2023 NEFT/AXISP00389894139/RIUP23/204/ABINANDNI ENTERP 56147.00
54877
54877 | Saidpur Village Pump House Work |  | 4 | 381000 | 64514 | 316486 | 56967.48 | 373453.48 | 3164.86 | 31648.6 |  |  |  | 56967.48 |  | 281672.54 |  | 281672 | 04-02-2023 NEFT/AXISP00360502879/RIUP22/2099/ABINANDNI ENTER ₹ 2,81,672.00
54877 | GST Release Note |  | 4 | 56967 | [11 empty] | 56967 |  | 56967 | 12-05-2023 NEFT/AXISP00389894138/RIUP23/205/ABINANDNI ENTERP 56967.00
55163
55163 | Khalwara Village Pump House Work | 2023-02-27 | 5 | 380993.68 | 58124 | 322869.68 | 58117.68 | 264752 | 3228.6968 | 32286.968 |  |  |  | 58124 |  | 287354.0152 |  | 287359 | 06-03-2023 NEFT/AXISP00369001727/RIUP22/2462/ABINANDNI ENTER 287359.00
55163 | GST Release Note | 2023-05-25 | 5 | 58117 | [11 empty] | 58117 |  | 58118 | 12-05-2023 NEFT/AXISP00389894112/RIUP23/206/ABINANDNI ENTERP 58118.00
[6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  |  | 55166
55166 | Saidipur Raju Village Pump House Work | 2023-06-01 | 2 | 361000 | 40210 | 320790 | 57742 | 378532 | 3207.9 | 32079 |  |  |  | 57742 |  | 285503 |  | 285503 | 27-06-2023 NEFT/AXISP00401014815/RIUP23/874/ABINANDNI ENTERP 285503.00
55166 | GST Release Note |  | 2 | 57742 | [11 empty] | 57742 |  | 57742 | 24-08-2023 NEFT/AXISP00418043564/RIUP23/1542/ABINANDNI ENTERPRI/ 57742.00
55167
55167 | GHYANMAZARA Village Pump House Work | 2023-06-01 | 3 | 381000 | 59049 | 321951 | 57951 | 379902 | 3219.51 | 32195.1 |  |  |  | 57951 |  | 286537 |  | 286536 | 15-07-2023 NEFT/AXISP00407207176/RIUP23/1056/ABINANDNI ENTER 286536.00
55167 | GST Release Note | 2023-10-25 | 3 | 57951 | [11 empty] | 57951 |  | 57951 | 13-02-2024 NEFT/AXISP00470943294/RIUP23/4300/ABINANDNI ENTERPRI/IDIB000M020 57951.00
55311
55311 | Wazidpur kawali Village Pump House Work | 2023-06-01 | 1 | 381000 | 57372 | 323628 | 58253 | 381881 | 3236.28 | 32362.8 |  |  |  | 58253 |  | 288029 |  | 288029 | 27-06-2023 NEFT/AXISP00401014814/RIUP23/873/ABINANDNI ENTERP 288029.00
55311 | GST Release Note |  | 1 | 58253 | [11 empty] | 58253 |  | 58253 | 28-08-2023 NEFT/AXISP00418870936/RIUP23/1541/ABINANDNI ENTERPRI/58253.00
58960
58960 | Ahamadwala Village Pump House Work | 2023-08-18 | 4 | 210000 | 48752 | 161248 | 29025 | 190273 | 1612.48 | 16124.8 |  |  |  | 29025 |  | 143511 |  | 143510 | 28-08-2023 NEFT/AXISP00418849242/RIUP23/1699/ABINANDNI ENTERPRI/143510.00
58960 | GST Release Note |  | 4 | 29025 | [11 empty] | 29025 |  | 20880 | 02-02-2024 NEFT/AXISP00467749360/RIUP23/4482/ABINANDNI ENTERPRI/IDIB000M020 20880.00
58960 | Ahamadwala Village Pump House Work | 2023-11-08 | 12 | 116000 | 0 | 116000 | 20880 | 136880 | 1160 | 11600 |  |  |  | 20880 |  | 103240 |  | 103240 | 07-02-2024 NEFT/AXISP00469113943/RIUP23/4223/ABINANDNI ENTERPRI/IDIB000M020 103240.00
58960 | GST Release Note |  | 12 | 20880 | [11 empty] | 20880 |  | 29024 | 07-02-2024 NEFT/AXISP00469113944/RIUP23/4301/ABINANDNI ENTERPRI/IDIB000M020 29024.00
[17 empty] | 58961 |  |  | Please book the bills from Row No-2 & 25 ( T.I- 07 & 10 ) as Shirish Sir has instructed to hold the payment only not booking bills
58961 | JABARDASTPUR MANDAUDI Village Pump House Work | 2023-08-18 | 7 | 210000 | 39252.3 | 170748 | 30735 | 201483 | 1707.48 | 17074.8 |  |  |  | 30735 |  | 151966 |  | 151965 | 16-07-2024 NEFT/AXISP00519021659/RIUP24/1110/ABINANDNI ENTERPRI/IDIB000M020 151965.00
58961 | GST Release Note |  | 7 | 30735 | [11 empty] | 30735 |  | 30734 | 16-07-2024 NEFT/AXISP00519021661/RIUP24/1112/ABINANDNI ENTERPRI/IDIB000M020 30734.00
58961 | JABARDASTPUR MANDAUDI Village Pump House Work | 2023-09-25 | 10 | 151000 | 0 | 151000 | 27180 | 178180 | 1510 | 15100 |  |  |  | 27180 |  | 134390 |  | 134390 | 16-07-2024 NEFT/AXISP00519021660/RIUP24/1111/ABINANDNI ENTERPRI/IDIB000M020 134390.00
58961 | GST Release Note |  | 10 | 27180 | [11 empty] | 27180 |  | 27180 | 30-01-2025 NEFT/AXISP00606020243/RIUP24/1595/ABINANDNI ENTERPRI/IDIB000M020 27180.00
59643
59643 | Ahrora Village Pump House Work | 2023-08-29 | 8 | 361000 | 41152 | 319848 | 57573 | 377421 | 3198.48 | 31984.8 |  |  |  | 57573 |  | 284665 |  | 284664 | 17-10-2023 NEFT/AXISP00435111135/RIUP23/2606/ABINANDNI ENTERPRI/IDIB000M020 284664.00
59643 | GST Release Note | 2023-10-21 | 8 | 57573 | [11 empty] | 57573 |  | 57573 | 09-02-2024 NEFT/AXISP00469899334/RIUP23/4302/ABINANDNI ENTERPRI/IDIB000M020 57573.00
59780
59780 | Nanhera Village Pump House Work | 2023-09-21 | 9 | 381000 | 28500 | 352500 | 63450 | 415950 | 3525 | 35250 |  |  | 35250 | 63450 |  | 278475 |  | 278475 | 19-10-2023 NEFT/AXISP00435739496/RIUP23/2782A/ABINANDNI ENTERPRI/IDIB000M020 278475.00
59780 | GST Release Note | 2023-10-22 | 9 | 63450 | [11 empty] | 63450 |  | 63450 | 01-02-2024 NEFT/AXISP00467277207/RIUP23/4303/ABINANDNI ENTERPRI/IDIB000M020 63450.00
60092
60092 | Guniyajuddi Boundary wall work | 2023-11-06 | 11 | 291116 | 36500 | 254616 | 45830.88 | 300446.88 | 2546.16 | 12730.8 |  |  |  | 45830.88 |  | 239339.04 |  | 148500 | 09-11-2023 NEFT/AXISP00442779073/RIUP23/3207/ABINANDNI ENTERPRI/IDIB000M020 148500.00
60092 | GST Release note |  | 11 | 45830.88 | [11 empty] | 45830.88 |  | 90839 | 12-01-2024 NEFT/AXISP00462195174/RIUP23/3274/ABINANDNI ENTERPRI/IDIB000M020 90839.00
60092 | [17 empty] | 45831 | 01-02-2024 NEFT/AXISP00467277203/RIUP23/4481/ABINANDNI ENTERPRI/IDIB000M020 45831.00
60127
60127 | Mandala Village-Pipe Laying Work | 2023-11-11 | 13 | 654877 | 74750 | 580127 | 104422.86 | 684549.86 | 5801.27 | 29006.35 | 58012.7 | 58012.7 |  | 104422.86 |  | 429293.98 |  | 429294 | 14-12-2023 NEFT/AXISP00452966711/RIUP23/3601/ABINANDNI ENTERPRI/IDIB000M020 429294.00
60127 | GST Release Note |  | 13 | 104422.86 | [11 empty] | 104422.86 |  | 55001 | 14-05-2024 NEFT/AXISP00499706378/RIUP23/5172/ABINANDNI ENTERPRI/IDIB000M020 55001.00
60127 | Mandala Village-Pipe Laying Work | 2024-01-12 | 14 | 74324 |  | 74324 | 13378.32 | 87702.32 | 743.24 | 3716.2 | 7432.4 | 7432.4 |  | 13378.32 |  | 54999.76 |  | 104423 | 14-06-2024 NEFT/AXISP00509460935/RIUP23/4483/ABINANDNI ENTERPRI/IDIB000M020 104423.00
60127 | GST Release Note |  | 14 | 13378.32 | [11 empty] | 13378.32 |  | 13378 | 30-01-2025 NEFT/AXISP00606020244/RIUP24/1596/ABINANDNI ENTERPRI/IDIB000M020 13378.00
65956
65956 | Pachenda kalan Village BW Work | 2024-09-02 | 1 | 445200 | 48624 | 396576 | 71383.68 | 467959.68 | 3965.76 | 19828.8 |  |  |  | 71383.68 | 25200 | 347581.44 |  | 247500 | 23-10-2024 NEFT/AXISP00557269325/RIUP24/2290/ABINANDNI ENTERPRI/IDIB000M020 247500.00
65956 | GST Release Note |  |  | 71383.68 | [11 empty] | 71383.68 |  | 71384 | 28-03-2025 NEFT/AXISP00641455071/RIUP24/3344/ABINANDNI ENTERPRI/IDIB000M020 71384.00
66317
66317 | SADPUR Village CONSTRUCTION WORK OF PUMP HOUSE Work | 2024-10-01 | 2 | 222000 | 0 | 222000 | 39960 | 261960 | 2220 | 11100 |  |  | 0 | 39960 |  | 208680 |  | 50000 | 23-12-2024 NEFT/AXISP00587800980/RIUP24/2542/ABINANDNI ENTERPRI/IDIB000M020 50000.00
66317 | SADPUR Village CONSTRUCTION WORK OF PUMP HOUSE Work | 2024-11-19 | 3 | 101850 | 0 | 101850 | 18333 | 120183 | 1018.5 | 5092.5 |  |  | 0 | 18333 |  | 95739 |  | 208680 | 31-12-2024 NEFT/AXISP00591007089/RIUP24/2321/ABINANDNI ENTERPRI/IDIB000M020 208680.00
66317 | GST Release Note |  | 2 & 3 | 58293 | [11 empty] | 58293 |  | 58293 | 28-03-2025 NEFT/AXISP00641455068/RIUP24/3205/ABINANDNI ENTERPRI/IDIB000M020 58293.00
66734
66734 | BHIRAHERI Village PUMP HOUSE Work | 2024-11-19 | 5 | 323850 | 0 | 323850 | 58293 | 382143 | 3238.5 | 16192.5 |  |  | 0 | 58293 |  | 304419 |  | 275000 | 12-03-2025 NEFT/AXISP00632194497/RIUP24/2540/ABINANDNI ENTERPRI/IDIB000M020 275000.00 | deleted from PMC and uploaded on 66735
66734 | GST Release Note |  | 5 | 58293 | [11 empty] | 58293 |  | 58293 | 28-03-2025 NEFT/AXISP00641455070/RIUP24/3207/ABINANDNI ENTERPRI/IDIB000M020 58293.00
66735
66735 | BHIRAHERI Village PUMP HOUSE Work | 2024-11-19 | 4 | 323850 | 14000 | 309850 | 55773 | 365623 | 3098.5 | 15492.5 |  |  | 0 | 55773 |  | 291259 |  | 200000 | 26-DEC-24 11:01:58 Debit N/RIUP24/2541/ABINANDNI ENTE/INDBN26123786884/ 200000
66735 | GST Release Note |  |  | 55773 | [11 empty] | 55773 |  | 55773 | 28-03-2025 NEFT/AXISP00641455069/RIUP24/3206/ABINANDNI ENTERPRI/IDIB000M020 55773.00