## Sheet1
Subcontractor: | Choudhary Construction
State: | Uttar Pradesh | [5 empty] | All work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Painting & Finishing (5%) | GST_SD_Amount | Hold amount | Final_Amount | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10% | 5%
52841 | Khorsama village Pump house chamber work | 2023-01-05 | 2 | 381000 | 30520 | 350480 | 63086 | 413566 | 3505 | 17524 |  |  |  | 63086 | 17524 | 311927 | 148500 | 09-11-2022 NEFT/AXISP00335986784/RIUP22/1223/CHOUDHARY CONST 148500.00 | 0
52841 | GST Release Note | 2023-02-25 | 2 | 63086 | [11 empty] | 63086 | 163427 | 10-01-2023 NEFT/AXISP00353656953/RIUP22/1821/CHOUDHARY CONST 163427.00
52841 | [16 empty] | 63086 | 01-03-2023 NEFT/AXISP00367214839/RIUP22/2381/CHOUDHARY CONST 63086.00
52844 | Sakauti village Pump house chamber work | 2023-01-05 | 1 | 381000 | 41965 | 339035 | 61026 | 400061 | 3390 | 16952 |  |  |  | 61026 | 16952 | 301741 | 148500 | 20-10-2022 NEFT/AXISP00330252335/RIUP22/1060/CHOUDHARY CONST 148500.00 | 0
52844 | GST Release Note | 2023-02-25 | 1 | 61026 | [11 empty] | 61026 | 153241 | 09-01-2023 NEFT/AXISP00353549289/RIUP22/1818/CHOUDHARY CONSTRUCTION CO 153241.00
52844 | [16 empty] | 61026 | 01-03-2023 NEFT/AXISP00367210626/RIUP22/2339/CHOUDHARY CONST 61026.00
54747 | Patni partapur Village Pump House work | 2023-02-03 | 3 | 228600 | 15260 | 213340 | 38401.2 | 251741.2 | 2133.4 | 10667 |  |  | 10667 | 38401.2 |  | 189873 | 148500 | 24-02-2023 NEFT/AXISP00365393657/RIUP22/2301/CHOUDHARY CONST 148500.00 | 0
54747 | Patni partapur Village Pump House work | 2023-03-10 | 4 | 152400 | 0 | 152400 | 27432 | 179832 | 1524 | 7620 |  |  | 7620 | 27432 |  | 135636 | 41373 | 01-03-2023 NEFT/AXISP00367214838/RIUP22/2376/CHOUDHARY CONST 41373.00
54747 | GST Release Note | 2023-03-17 | 3 | 38401 | [11 empty] | 38401 | 135636 | 15-03-2023 NEFT/AXISP00371550762/RIUP22/2573/CHOUDHARY CONST 135636.00
54747 | GST Release Note | 2023-04-24 | 4 | 27432 | [11 empty] | 27432 | 38401 | 20-03-2023 NEFT/AXISP00372793134/RIUP22/2668/CHOUDHARY CONST 38401.00
54747 | [16 empty] | 27432 | 02-05-2023 NEFT/AXISP00386545791/SPUP23/0342/CHOUDHARY CONST 27432.00
55156 | Mubarikpur Village Boundary wall work | 2023-04-15 | 1 | 275625 | 15260 | 260365 | 46865.7 | 307230.7 | 2603.65 | 13018.25 |  |  | 13018.25 | 46865.7 |  | 231725 | 231725 | 21-04-2023 NEFT/AXISP00383548030/SPUP23/0220/CHOUDHARY CONST 231725.00 | -1
55156 | GST Release Note | 2023-05-26 | 1 | 46866 | [11 empty] | 46866 | 46866 | 02-06-2023 NEFT/AXISP00395047112/RIUP23/475/CHOUDHARY CONSTR 46866.00
55156 |  | 2023-07-07 | 4 | 118125 |  | 118125 | 21262.5 | 139387.5 | 1181.25 | 5906.25 |  |  | 5906.25 | 21262.5 |  | 105131 | 105132 | 17-07-2023 NEFT/AXISP00407488696/RIUP23/1109/CHOUDHARY CONST 105132.00
55156 | GST release | 2023-07-25 | 4 | 21263 | [11 empty] | 21263 | 21263 | 31-08-2023 NEFT/AXISP00419716231/RIUP23/1802/CHOUDHARY CONSTRUC/PUNB0745400 21263.00
[6 empty] | 0 | 0 | 0 | 0 | [6 empty] | 0
57702 | Hathchhoya village Pump house work | 2023-06-02 | 3 | 228600 | 26705 | 201895 | 36341.1 | 238236.1 | 2018.95 | 10094.75 |  |  | 10094.75 | 36341.1 |  | 179687 | 179686 | 20-06-2023 NEFT/AXISP00399675463/RIUP23/689/CHOUDHARY CONSTR 179686.00 | 1
57702 | Hathchhoya village Pump house work | 2023-07-07 | 5 | 152400 | 0 | 152400 | 27432 | 179832 | 1524 | 7620 |  |  | 15240 | 27432 |  | 128016 | 128016 | 19-07-2023 NEFT/AXISP00408124081/RIUP23/1123/CHOUDHARY CONST ₹ 1,28,016.00
57702 | GST release | 2023-07-18 | 3 | 36341 | [11 empty] | 36341 | 36341 | 21-07-2023 NEFT/AXISP00408446754/RIUP23/1153/CHOUDHARY CONST 36341.00
57702 | GST release | 2023-07-25 | 5 | 27432 | [11 empty] | 27432 | 27432 | 31-08-2023 NEFT/AXISP00419716232/RIUP23/1803/CHOUDHARY CONSTRUC/PUNB0745400 27432.00
57704 | Patni pratappur village Boundary wall work | 2023-05-31 | 2 | 434000 | 30520 | 403480 | 72626 | 476106 | 4035 | 20174 |  |  | 20174 | 72626 | 36050 | 323047 | 323047 | 15-06-2023 NEFT/AXISP00398841900/RIUP23/664/CHOUDHARY CONSTR 323047.00 | 0
57704 | GST Release Note | 2023-06-16 | 2 | 72626 | [11 empty] | 72626 | 72626 | 19-06-2023 NEFT/AXISP00399545677/RIUP23/721/CHOUDHARY CONSTR 72626.00
58339 | Akapur Fusgarah village Pump house chamber work | 2023-07-07 | 6 | 228600 | 0 | 228600 | 41148 | 269748 | 2286 | 11430 |  |  | 11430 | 41148 |  | 203454 | 203454 | 21-07-2023 NEFT/AXISP00408446748/RIUP23/1105/CHOUDHARY CONST 203454.00 | 1
58339 | GST Release note | 2023-07-25 | 6 | 41148 | [11 empty] | 41148 | 41148 | 31-08-2023 NEFT/AXISP00419716233/RIUP23/1804/CHOUDHARY CONSTRUC/PUNB0745400 41148.00
58339 | Akapur Fusgarah village Pump house chamber work | 2023-09-07 | 8 | 57150 | 0 | 57150 | 10287 | 67437 | 571.5 | 2858 |  |  | 2857.5 | 10287 |  | 50863 | 50862 | 13-09-2023 NEFT/AXISP00424687452/RIUP23/1990/CHOUDHARY CONSTRUC/PUNB0745400 50862.00
58339 | GST Release Note | 2023-10-11 | 8 | 10287 | [11 empty] | 10287 | 10287 | 17-10-2023 NEFT/AXISP00435127456/RIUP23/2694/CHOUDHARY CONSTRUC/PUNB0745400 10287.00
58339 | Akapur Fusgarah village Pump house chamber work | 2024-11-11 | 4 | 38100 | 0 | 38100 | 6858 | 44958 | 381 | 1905 |  |  | 0 | 6858 |  | 35814 | 35814 | 10-01-2025 NEFT/AXISP00597065256/RIUP24/2666/CHOUDHARY CONSTRUC/PUNB0745400 35814.00
58339 | GST Release Note |  | 4 | 6858 | [11 empty] | 6858 | 6858 | 10-01-2025 NEFT/AXISP00597065258/RIUP24/2885/CHOUDHARY CONSTRUC/PUNB0745400 6858.00
58545
58545 | BW village GH work | 27-10--23 | 14 | 23500 |  | 23500 | 4230 | 27730 | 235 | 1175 |  |  |  | 4230 |  | 22090 | 4230 | 11-12-2023 NEFT/AXISP00451701536/RIUP23/3607/CHOUDHARY CONSTRUC/PUNB0745400 4230.00 | 0
58545 | GST Release note |  | 14 | 4230 | [11 empty] | 4230 | 22090 | 11-12-2023 NEFT/AXISP00451701535/RIUP23/3606/CHOUDHARY CONSTRUC/PUNB0745400 22090.00
58696 | Paotikalan Village Pump House work | 2023-08-01 | 7 | 185000 | 26705 | 158295 | 28493.1 | 186788.1 | 1582.95 | 7914.75 |  |  | 7914.75 | 28493.1 |  | 140883 | 140882 | 05-08-2023 NEFT/AXISP00412924936/RIUP23/1377/CHOUDHARY CONST 140882.00 | 56
58696 | Paotikalan Village Pump House work | 2023-09-07 | 10 | 119800 | 0 | 119800 | 21564 | 141364 | 1198 | 5990 |  |  | 5990 | 21564 |  | 106622 | 106622 | 18-09-2023 NEFT/AXISP00425751843/RIUP23/2097/CHOUDHARY CONSTRUC/PUNB0745400 106622.00
58696 | GST | 2023-10-11 | 7 | 28493.1 |  | 28493 | 0 | 28493 | 0 | 0 |  |  | 0 | 0 |  | 28493 | 28439 | 03-10-2023 NEFT/AXISP00429778561/RIUP23/2244/CHOUDHARY CONSTRUC/PUNB0745400 28493.00
58696 | GST |  | 10 | 21564 |  | 21564 | 0 | 21564 | 0 | 0 |  |  | 0 | 0 |  | 21564 | 21564 | 17-10-2023 NEFT/AXISP00435127458/RIUP23/2696/CHOUDHARY CONSTRUC/PUNB0745400 21564.00
58696 | Paotikalan Village Pump House work | 2024-07-13 | 3 | 19050 | 0 | 19050 | 3429 | 22479 | 190.5 | 952.5 |  |  |  | 3429 |  | 17907 | 17906 | 21-09-2024 NEFT/AXISP00542907683/RIUP24/1474/CHOUDHARY CONSTRUC/PUNB0745400 17906.00
58696 | GST |  | 3 | 3429 | [11 empty] | 3429 | 3429 | 14-11-2024 NEFT/AXISP00569462149/RIUP24/2081/CHOUDHARY CONSTRUC/PUNB0745400 3429.00
58696
59192 | KASERWAKALAN VILLAGE Pump House work | 2023-09-07 | 9 | 314500 | 19075 | 295425 | 53176.5 | 348601.5 | 2954.25 | 14771.25 |  |  | 14771.25 | 53176.5 |  | 262928 | 262929 | 18-09-2023 NEFT/AXISP00425751833/RIUP23/2049/CHOUDHARY CONSTRUC/PUNB0745400 262929.00 | -1
59192 | GST | 2023-10-11 | 9 | 53177 |  | 53177 | 0 | 53177 | 0 | 0 |  |  | 0 | 0 |  | 53177 | 53177 | 17-10-2023 NEFT/AXISP00435127457/RIUP23/2695/CHOUDHARYCONSTRUC/PUNB0745400 53177.00
59695 | Sheikpur Bamnoli Village Kairana Block - PH work | 2023-10-09 | 11 | 185000 |  | 185000 | 33300 | 218300 | 1850 | 9250 |  |  |  | 33300 |  | 173900 | 173900 | 17-10-2023 NEFT/AXISP00435111138/RIUP23/2644/CHOUDHARY CONSTRUC/PUNB0745400 173900.00 | 0.8
59695 | GST release | 2023-11-14 | 11 | 33300 | [11 empty] | 33300 | 99000 | 09-11-2023 NEFT/AXISP00442541864/RIUP23/3164/CHOUDHARY CONSTRUC/PUNB0745400 99000.00
59695 | Sheikpur Bamnoli Village Kairana Block - PH work | 2023-12-27 | 17 | 138850 | 15260 | 123590 | 22246.2 | 145836.2 | 1235.9 | 6179.5 |  |  |  | 22246.2 |  | 116174.6 | 33300 | 18-11-2023 NEFT/AXISP00445057527/RIUP23/3301/CHOUDHARY CONSTRUC/PUNB0745400 33300.00
59695 | GST release |  | 17 | 22246.2 | [11 empty] | 22246.2 | 17174 | 12-01-2024 NEFT/AXISP00462196166/RIUP23/4140/CHOUDHARY CONSTRUC/PUNB0745400 17174.00
59695 | [16 empty] | 22246 | 16-02-2024 NEFT/AXISP00472105173/RIUP23/4323/CHOUDHARY CONSTRUC/PUNB0745400 22246.00
59696 | Nau Nagla Chondhaheri village Unn block PH work | 2023-10-09 | 12 | 185000 |  | 185000 | 33300 | 218300 | 1850 | 9250 |  |  |  | 33300 |  | 173900 | 173900 | 17-10-2023 NEFT/AXISP00435111136/RIUP23/2642/CHOUDHARY CONSTRUC/PUNB0745400 173900.00 | 1
59696 | Nau Nagla Chondhaheri village Unn block PH work | 2023-11-06 | 15 | 138850 |  | 138850 | 24993 | 163843 | 1388.5 | 6942.5 |  |  |  | 24993 |  | 130519 | 99000 | 09-11-2023 NEFT/AXISP00442779055/RIUP23/3195/CHOUDHARY CONSTRUC/PUNB0745400 99000.00
59696 | GST release | 2023-11-14 | 12 | 33300 | [11 empty] | 33300 | 33300 | 18-11-2023 NEFT/AXISP00445057528/RIUP23/3302/CHOUDHARY CONSTRUC/PUNB0745400 33300.00
59696 | GST release |  | 15 | 24993 | [11 empty] | 24993 | 31518 | 30-11-2023 NEFT/AXISP00447586131/RIUP23/3333/CHOUDHARY CONSTRUC/PUNB0745400 31518.00
59696 | [16 empty] | 24993 | 22-12-2023 NEFT/AXISP00455046736/RIUP23/3832/CHOUDHARY CONSTRUC/PUNB0745400 24993.00
59697 | Khera Bhau Simbalika Village - Unn Block - PH work | 2023-10-09 | 13 | 304800 | 22890 | 281910 | 50743.8 | 332653.8 | 2819.1 | 14095.5 |  |  |  | 50743.8 |  | 264995.4 | 264995 | 17-10-2023 NEFT/AXISP00435111137/RIUP23/2643/CHOUDHARY CONSTRUC/PUNB0745400 264995.00 | -0.6
59697 | GST release | 2023-11-14 | 13 | 50743 | [11 empty] | 50743 | 50744 | 18-11-2023 NEFT/AXISP00445057529/RIUP23/3303/CHOUDHARY CONSTRUC/PUNB0745400 50744.00
59697
60657 | RATAUNDH VILLAGE PUMP.HOUSE WORK ATBIBIPUR | 2023-11-30 | 16 | 185000 | 26705 | 158295 | 28493.1 | 186788.1 | 1582.95 | 7914.75 |  |  |  | 28493.1 |  | 148797.3 | 148797 | 15-12-2023 NEFT/AXISP00453272889/RIUP23/3730/CHOUDHARY CONSTRUC/PUNB0745400 148797.00 | 0.4
60657 | RATAUNDH VILLAGE PUMP.HOUSE WORK ATBIBIPUR | 2023-12-31 | 18 | 129500 | 0 | 129500 | 23310 | 152810 | 1295 | 6475 |  |  |  | 23310 |  | 121730 | 28493 | 22-12-2023 NEFT/AXISP00455046735/RIUP23/3833/CHOUDHARY CONSTRUC/PUNB0745400 28493.00
60657 | RATAUNDH VILLAGE PUMP.HOUSE WORK ATBIBIPUR | 2023-12-31 | 19 | 11000 | 0 | 11000 | 1980 | 12980 | 110 | 550 |  |  |  | 1980 |  | 10340 | 132070 | 09-01-2024 NEFT/AXISP00461001711/RIUP23/4141/CHOUDHARY CONSTRUC/PUNB0745400 132070.00
60657 | GST release |  | 16 | 28493.1 | [11 empty] | 28493.1 | 25290 | 12-02-2024 NEFT/AXISP00470368418/RIUP23/4324/CHOUDHARY CONSTRUC/PUNB0745400 25290.00
60657 | GST release |  | 18 & 19 | 25290 | [11 empty] | 25290
61690 | JAMALPUR VILLAGE PUMP.HOUSE WORK | 2024-01-08 | 20 | 185000 | 30520 | 154480 | 27806.4 | 182286.4 | 1544.8 | 7724 |  |  |  | 27806.4 |  | 145211.2 | 145211 | 18-01-2024 NEFT/AXISP00463439410/RIUP23/4261/CHOUDHARY CONSTRUC/PUNB0745400 145211.00 | 0.36
61690 | JAMALPUR VILLAGE PUMP.HOUSE WORK | 2024-01-31 | 21 | 138850 | 3052 | 135798 | 24443.64 | 160241.64 | 1357.98 | 6789.9 |  |  |  | 24443.64 |  | 127650.12 |  | Hold By Sanjay Sir
61690 | GST |  | 20,21 | 52250.04 | [11 empty] | 52250.04 | 52250 | 26-04-2024 NEFT/AXISP00494041789/RIUP24/004/CHOUDHARY CONSTRUC/PUNB0745400 52250.00
61690 | [16 empty] | 127650 | 05-07-2024 NEFT/AXISP00515770430/RIUP23/4623/CHOUDHARY CONSTRUC/PUNB0745400 127650.00
62761
62761 | Banjheri village PH work | 2024-03-05 | 22 | 323850 |  | 323850 | 58293 | 382143 | 3238.5 | 16192.5 |  |  |  | 58293 |  | 304419 | 304418 | 31-03-2024 NEFT/AXISP00486642310/RIUP23/5314/CHOUDHARY CONSTRUC/PUNB0745400 304418.00 | 1
62761 | GST |  | 22 | 58293 | [11 empty] | 58293 | 58293 | 26-04-2024 NEFT/AXISP00494041796/RIUP24/0218/CHOUDHARY CONSTRUC/PUNB0745400 58293.00
62761
63309
63309 | Badhupura village BW work | 2023-04-09 | 1 | 313460 |  | 313460 | 56422.8 | 369882.8 | 3134.6 | 15673 |  |  |  | 56422.8 |  | 294652.4 | 294652 | 26-04-2024 NEFT/AXISP00494041794/RIUP24/0146/CHOUDHARY CONSTRUC/PUNB0745400 294652.00 | 0.2
63309 | GST |  | 1 | 56422.8 | [11 empty] | 56422.8 | 56423 | 05-07-2024 NEFT/AXISP00515770429/RIUP24/0572/CHOUDHARY CONSTRUC/PUNB0745400 56423.00
65787
65787 | , KABEERPUR AHATMAL village RR work BLOCK- UNN | 2024-11-11 | 5 | 131158 | 15260 | 115898 | 20861.64 | 136759.64 | 1158.98 | 5794.9 | 11589.8 | 11589.8 |  | 20861.64 |  | 85764.52 | 99000 | 01-10-2024 NEFT/AXISP00547368148/RIUP24/2045/CHOUDHARY CONSTRUC/PUNB0745400 99000.00 | -17123.84
65787 | GST |  | 5 | 20861.64 | [11 empty] | 20861.64 | 24750 | 10-01-2025 NEFT/AXISP00597065259/RIUP24/2886/CHOUDHARY CONSTRUC/PUNB0745400 24750.00
65787
[10 empty] | 269404.3 | 11589.8 | 11589.8 | 125683.75 | 969851.68 | 70526 | 5815249.32 | 5832314 | Total Paid | -17064.68
[17 empty] | -17064.68 | Balance Payable
Choudhary Construction
2025-01-13
[9 empty] | Total Hold |  |  | 418267.65
[9 empty] | Advance / Surplus |  |  | -17064.68 | -17064.68
[9 empty] | Extra Hold |  |  | 70526 | 70526
[9 empty] | GST Remaining |  |  | -0.1 | 27719.64