## Sheet1
Subcontractor: | Harinam Gold
State: | Uttar Pradesh | [6 empty] | Boundary wall
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | Painting and finishing | On_Commission | Hydro_Testing | Hold | GST_SD_Amount | Final_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% | 10% |  | 18%
56723 | Kelashikarpur village BW work | 2023-04-13 | 3 | 318080 | 47687 | 270393 | 48671 | 319064 | 2704 | 27039.3 |  | 0 | 0 |  | 48671 | 240650 | 198000 | 21-04-2023 NEFT/AXISP00383483041/SPUP23/0222/HARI NAM GOLD 198000.00
56723 |  |  | 3 | 48671 | [11 empty] | 48671 | 42650 | 06-05-2023 NEFT/AXISP00388049690/SPUP23/0348/HARINAM GOLD 42650.00
56723 | [16 empty] | 48671 | 14-01-2025 NEFT/AXISP00598257722/RIUP24/2933/HARINAM GOLD/UBIN0534391 48671.00
[6 empty] | 0 | 0% | 0 | 0% | 0% |  | 0% | 0% |  | 0% | 0 |  |  | 0
56722 | Manakpur Yunishpur village PH work | 2023-04-13 | 2 | 185000 | 49429.07 | 135571 | 24403 | 159974 | 1356 | 6778.55 | 6778.55 | 0 | 0 |  | 24403 | 120658 | 120658 | 24-04-2023 24-04-2023 NEFT/AXISP00383652904/SPUP23/0234/HARINAM GOLD 120658.00
56722 |  | 2023-07-21 | 49 | 149194 |  | 149194 | 26855 | 176049 | 1492 | 7460 |  |  |  | 21698 | 26855 | 118544 | 118544 | 20-09-2023 NEFT/AXISP00426115420/RIUP23/1473/HARINAM GOLD/UBIN0534391 118544.00
56722 |  |  | 2, 49 | 51258 | [11 empty] | 51258 | 22911 | 30-08-2024 NEFT/AXISP00533718983/RIUP24/1542/HARINAM GOLD/UBIN0534391 22911.00
56722 | [16 empty] | 39600 | 10-01-2025 NEFT/AXISP00597065261/RIUP24/2888/HARINAM GOLD/UBIN0534391 39600.00
-11253
55201 | Bhandaura village PH work | 2022-12-05 | 98 | 228600 | 70787 | 157813 | 28406 | 186219 | 1578.13 | 7890.65 | 7890.65 |  |  |  | 28406 | 140453.57 | 140453 | 27-02-2023 NEFT/AXISP00365798949/RIUP22/2318/HARINAM GOLD 140453.00
55201 | GST |  | 98 | 28406 | [11 empty] | 28406 | 28406 | 3 18-09-2023 NEFT/AXISP00425751842/RIUP23/2056/HARINAM GOLD/UBIN0534391 28406.00
55201 |  |  | 50 | 152400 | 19075 | 133325 | 23998.5 | 157323.5 | 1333.25 | 6666.25 | 13332.5 |  |  | 7981 | 23998.5 | 104012 | 104012 | 22-09-2023 NEFT/AXISP00426750478/RIUP23/1490/HARINAM GOLD/UBIN0534391 104012.00
55201 | GST |  | 50 | 23998.5 | [11 empty] | 23998.5
55201 | [18 empty] | 23999.07
54131 | Kelasikarpur village PH work | 2022-12-20 | 94 | 222000 | 59921 | 162079 | 29174 | 191253 | 1621 | 8104 |  |  |  |  | 29174 | 152354 | 152353 | 29-12-2022 NEFT/AXISP00349704424/RIUP22/1679/HARINAM GOLD 1,52,353.00
54131 | 0.4 | 2023-02-13 | 96 | 159000 | 3815 | 155185 | 27933 | 183118 | 1552 | 7759 | 7759.25 |  |  |  | 27933 | 138115 | 138115 | 28-02-2023 NEFT/AXISP00349568596/RIUP22/2374/HARINAM GOLD 1,38,115/-
54131 | GST |  | 94 | 29174 | [11 empty] | 29174 | 29174 | 22-09-2023 NEFT/AXISP00426938285/RIUP23/2052/HARINAM GOLD/UBIN0534391 29174.00
54131 | GST |  | 96 | 27933 | [11 empty] | 27933 | 27933 | 22-09-2023 NEFT/AXISP00426938282/RIUP23/2055/HARINAM GOLD/UBIN0534391 27933.00
1
54130 | Thirwa village PH work | 20.12.22 | 95 | 222000 | 88878 | 133122 | 23962 | 157084 | 1331.22 | 6656.1 |  |  |  |  | 23962 | 125135 | 99000 | 26-12-2022 NEFT/AXISP00348781174/RIUP22/1629/HARINAM GOLD 99000.00
54130 |  | 13.02.23 | 97 | 159000 | 3815 | 155185 | 27933 | 183118 | 1551.85 | 15518.5 |  |  |  |  | 27933 | 138115 | 26135 | 31-12-2022 NEFT/AXISP00350264761/RIUP22/1695/HARINAM GOLD 26135.00
54130 | GST |  | 95 | 23962 | [11 empty] | 23962 | 138115 | 27-02-2023 NEFT/AXISP00365798948/RIUP22/2317/HARINAM GOLD 138115.00
54130 | GST |  | 97 | 27933 | [11 empty] | 27933 | 23962 | 22-09-2023 NEFT/AXISP00426938285/RIUP23/2053/HARINAM GOLD/UBIN0534391 23962.00
54130 | [16 empty] | 27933 | 22-09-2023 NEFT/AXISP00426938283/RIUP23/2054/HARINAM GOLD/UBIN0534391 27933.00
54130 | [18 empty] | 0
58620 | Nojal Nojali village PH work | 2023-07-21 | 47 | 296000 | 59132 | 236868 | 42636.24 | 279504.24 | 2368.68 | 11843.4 | 11843.4 |  |  |  | 42636.24 | 210812.52 | 210812 | 20-09-2023 NEFT/AXISP00426115421/RIUP23/1369/HARINAM GOLD/UBIN0534391 210812.00
58620 |  |  | 47 | 42636.24 | [11 empty] | 42636.24
42636.76
59990 | Rampur Kheri village RR work | 2023-10-19 | 83 | 824806 | 196472 | 628334 | 113100.12 | 741434.12 | 125666.8 | 31416.7 |  | 62833.4 | 62833.4 |  | 113100.12 | 345583.7 | 345585 | 07-11-2023 NEFT/AXISP00441165816/RIUP23/3017/HARINAM GOLD/UBIN0534391 345585.00 | 10% TDS deducted
59990 |  |  | 83 | 113100.12 |  |  |  |  | 6283.34 | [6 empty] | 113100.12 | 99000 | 10-09-2024 NEFT/AXISP00538525502/RIUP24/1731/HARINAM GOLD/UBIN0534391 99000.00
59990 | [8 empty] | 119383.46 | 34482.28 | [6 empty] | 99000 | 22-10-2024 NEFT/AXISP00556849616/RIUP24/2286/HARINAM GOLD/UBIN0534391 99000.00
-84901.18
60864 | Bhandaura village BW work | 2023-12-01 | 103 | 409850 | 131617.5 | 278232.5 | 50081.85 | 328314.35 | 2782.325 | 13911.625 | 27823.25 |  |  |  | 50081.85 | 233715.3 | 233715 | 02-01-2024 NEFT/AXISP00458541613/RIUP23/3968/HARINAM GOLD/UBIN0534391 233715.00
60864 | GST |  | 103 | 50081.85 | [11 empty] | 50081.85 | 50082 | 30-08-2024 NEFT/AXISP00533718984/RIUP24/1544/HARINAM GOLD/UBIN0534391 50082.00
0.15
63272 | KASAMPUR village BW work | 2024-03-30 | 154 | 217000 | 0 | 217000 | 39060 | 256060 | 2170 | 10850 | 0 |  |  |  | 39060 | 203980 | 203980 | 04-06-2024 NEFT/AXISP00506012640/RIUP24/0207/HARINAM GOLD/UBIN0534391 203980.00
63272 | GSt |  | 154 | 39060 | [11 empty] | 39060 | 39060 | 30-08-2024 NEFT/AXISP00533718977/RIUP24/1172/HARINAM GOLD/UBIN0534391 39060.00
0
63273 | KASAMPUR village PH work | 2024-03-30 | 152 | 304800 | 0 | 304800 | 54864 | 359664 | 3048 | 15240 |  | 0 | 0 |  | 54864 | 286512 | 286512 | 26-04-2024 NEFT/AXISP00494052850/RIUP24/0208/HARINAM GOLD/UBIN0534391 286512.00
63273 | GST |  | 152 | 54864 | [11 empty] | 54864 | 54864 | 30-08-2024 NEFT/AXISP00533718975/RIUP24/1170/HARINAM GOLD/UBIN0534391 54864.00
63273
63273
0
63274 | BHANERAJAT village PH work | 2024-03-30 | 153 | 296000 | 228521 | 67479 | 12146.22 | 79625.22 | 674.79 | 3373.95 | 0 |  |  |  | 12146.22 | 63430.26 | 63430 | 26-04-2024 NEFT/AXISP00494052851/RIUP24/0209/HARINAM GOLD/UBIN0534391 63430.00
63274 | GSt |  | 153 | 12146.22 | [11 empty] | 12146.22 | 12146 | 30-08-2024 NEFT/AXISP00533718976/RIUP24/1171/HARINAM GOLD/UBIN0534391 12146.00
63274
0.48
64752 | BHANERAJAT village BW work | 2024-07-09 | 26 | 382585 | 59451 | 323134 | 58164.12 | 381298.12 | 3231.34 | 16156.7 |  |  |  | 52150 | 58164.12 | 251595.96 | 200000 | 03-08-2024 NEFT/AXISP00524511269/RIUP24/1120/HARINAM GOLD/UBIN0534391 200000.00
64752 | GST Release note | 2024-07-09 | 26 | 58164.12 | [11 empty] | 58164.12 | 99000 | 10-09-2024 NEFT/AXISP00538525503/RIUP24/1733/HARINAM GOLD/UBIN0534391 99000.00
64752 | [18 empty] | 10760.08
65167 | KHERI BAIRAGI village- PH work | 2024-07-26 | 30 | 296000 | 15260 | 280740 | 50533.2 | 331273.2 | 2807.4 | 14037 |  |  |  |  | 50533.2 | 263895.6 | 247500 | 03-08-2024 NEFT/AXISP00524511283/RIUP24/1353/HARINAM GOLD/UBIN0534391 247500.00
65167 | GST Release note | 2024-07-26 | 30 | 50533.2 | [11 empty] | 50533.2 | 49500 | 10-09-2024 NEFT/AXISP00538525517/RIUP24/1732/HARINAM GOLD/UBIN0534391 49500.00
65167 | [16 empty] | 50533 | 14-01-2025 NEFT/AXISP00598257723/RIUP24/2934/HARINAM GOLD/UBIN0534391 50533.00 | -33104.2
66382 | Manakpur Yunispur village BW work | 2024-10-21 | 35 | 290640 | 49595 | 241045 | 43388.1 | 284433.1 | 2410.45 | 12052.25 |  |  |  |  | 43388.1 | 226582.3 | 200000 | 14-11-2024 NEFT/AXISP00569462150/RIUP24/2293/HARINAM GOLD/UBIN0534391 200000.00
66382 | GST Release note |  | 35 | 43388.1 | [11 empty] | 43388.1 | 43388 | 10-01-2025 NEFT/AXISP00597065255/RIUP24/2733/HARINAM GOLD/UBIN0534391 43388.00
66382 | [16 empty] | 26583 | 10-01-2025 NEFT/AXISP00597065262/RIUP24/2889/HARINAM GOLD/UBIN0534391 26583.00
-0.6
68536 | SAIHATA Village Pump House Work Block | 2025-04-17 | 5 | 210000 | 123022 | 86978 | 15656.04 | 102634.04 | 869.78 | 4348.9 |  |  |  |  | 15656.04 | 81759.32 | 99000 | 25-03-2025 NEFT/AXISP00638559400/RIUP24/3482/HARINAM GOLD/UBIN0534391 99000.00
68536
-17240.68
68537 | SAIHATA Village Pump House Work Block | [15 empty] | 99000 | 15-05-2025 NEFT/AXISP00666018232/RIUP25/0251/HARINAM GOLD/UBIN0534391 99000.00
68537
-99000
69013 | THANABHAWAN Village Boundary Wall Work At- JANIPUR Block- | [15 empty] | 99000 | 02-05-2025 NEFT/AXISP00660145763/RIUP25/0191/HARINAM GOLD/UBIN0534391 99000.00
69013
-99000
69014 | DAKHORI JAMALPUR Village Boundary Wall Work At- Block-THANABHAWAN | [15 empty] | 99000 | 02-05-2025 NEFT/AXISP00660145764/RIUP25/0192/HARINAM GOLD/UBIN0534391 99000.00
69014 | [15 empty] | 0
69014 | [18 empty] | -99000
[10 empty] | 261585.155 | 75427.6 | 62833.4 | 62833.4 | 81829 | 740965.39 | 4171212.88 | 4537315 | Total Paid | -366102.12
[17 empty] | -366102.12 | Balance Payable
Harinam Gold
2025-05-17
[10 empty] | Hold Amount |  | 462679.555
[10 empty] | Advance / Surplus |  | -366102.12
Debit
[10 empty] | GST Remaining |  | 15656.04