## Sheet1
Subcontractor: | Pawanputra Construction
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Painting and finishing | Hold amount | Final_Amount |  | Total_Amount | UTR | Advance Village Wise
[9 empty] | 1% | 5% | 10% | 10% |  | 0.1
0
62565 | common village DG foundation work | 2024-02-19 | 60 | 200000 | 62618.425 | 137381.575 | 24728.6835 | 162110.2585 | 1373.8158 | 6869.0788 |  |  | 24728.6835 |  |  | 129138.6805 |  | 99000 | 14-03-2024 NEFT/AXISP00480996450/RIUP23/5101/PAWANPUTRA CONSTRU/CNRB0004804 99000.00
62565 | GST release note |  | 60 | 24728.6835 | [11 empty] | 24728.6835 |  | 30138 | 06-04-2024 NEFT/AXISP00489186681/RIUP23/5293/PAWANPUTRA CONSTRU/CNRB0004804 30138.00
62565 | common village DG foundation work | 2024-03-08 | 64 | 40000 |  | 40000 | 7200 | 47200 | 400 | 2000 |  |  | 7200 |  |  | 37600 |  | 24729 | 06-04-2024 NEFT/AXISP00489186682/RIUP23/5294/PAWANPUTRA CONSTRU/CNRB0004804 24729.00
62565 | common village DG foundation work | 2024-04-04 | 2 | 160000 | 64873 | 95127 | 17122.86 | 112249.86 | 951.27 | 4756.35 |  |  | 17122.86 |  |  | 89419.38 | Enter only
[17 empty] | 0 |  |  | 127019.744
62581 | Rasulpur Kailora Fimpur Khurd Village Cross draingae & Valve Chamber work | 2024-02-22 | 61 | 119096.25 |  | 119096.25 | 21437.325 | 140533.575 | 1190.9625 | 5954.8125 |  |  | 21437.325 |  |  | 111950.475 |  | 99000 | 14-03-2024 NEFT/AXISP00480996451/RIUP23/5102/PAWANPUTRA CONSTRU/CNRB0004804 99000.00
62581 | Rasulpur Kailora Village Cross draingae & Valve Chamber work | 2024-02-22 | 62 | 38100 |  | 38100 | 6858 | 44958 | 381 | 1905 |  |  | 6858 |  |  | 35814 |  | 12951 | 06-04-2024 NEFT/AXISP00489186672/RIUP23/5208/PAWANPUTRA CONSTRU/CNRB0004804 12951.00
62581 | GST release note |  | 61, 62 | 28295.325 | [11 empty] | 28295.325 |  | 35814 | 06-04-2024 NEFT/AXISP00489186673/RIUP23/5209/PAWANPUTRA CONSTRU/CNRB0004804 35814.00
62581 | [17 empty] | 28295 | 06-04-2024 NEFT/AXISP00489186674/RIUP23/5210/PAWANPUTRA CONSTRU/CNRB0004804 28295.00
[17 empty] | 0 |  |  | -0.2
61373 | Hind Village PH work | [16 empty] | 99000 | 29-12-2023 NEFT/AXISP00456827641/RIUP23/4026/PAWANPUTRA CONSTRU/CNRB0004804 99000.00
61373
61373
0
61372 | Hind Village BW work
61372
61372
[8 empty] | Total Payable Amount Rs. - |  | 21485.2412 | 0 | 0 | 77346.8685 | 0 | Total Payable | 456946.544 |  | 428927 | Total Paid | 127019.544
[10 empty] | 28020 | [7 empty] | 28019.544 | Balance Payable
Updated On 07-02-2024 ( By Vikash )
Pawanputra Construction
[6 empty] | Total Hold |  | 21485.2412
Total Debit
[6 empty] | Advance/ Surplus |  | 28019.544