## Sheet1
Subcontractor: | M/s Praveen kumar Contractor
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit_Amount | After Debit Amt | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount for quantity more than DPR | Final_Amount |  | PAYMENT NOTE No. | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% |  |  | 18%
68219
68219 | KHATAULI Village CONSTRUCTION OF BOUNDARY WALL WORK | 2025-03-05 | 1 | 376320 | 127570 | 248750 | 44775 | 293525 | 2487.5 | 12437.5 |  |  | 44775 | 0 | 233825 |  |  | 150000 | 11-03-2025 NEFT/AXISP00631402780/RIUP24/3349/PRAVEEN KUMAR/PUNB0123500 150000.00
68219 | KHATAULI Village CONSTRUCTION OF BOUNDARY WALL WORK | 2025-03-12 | 2 | 185318 | 0 | 185318 | 33357 | 218675 | 1853.18 | 9265.9 |  |  | 33357 | 0 | 174199 |  |  | 50000 | 21-03-2025 NEFT/AXISP00636917551/RIUP24/3471/PRAVEEN KUMAR/PUNB0123500 50,000.00
68219 | GST Release Note |  | 1 , 2 | 78132 | [10 empty] | 78132 |  |  | 174199 | 17-04-2025 NEFT/AXISP00652635642/RIUP24/3474/PRAVEEN KUMAR/PUNB0123500 174199.00
68219 | [17 empty] | 78132 | 30-04-2025 NEFT/AXISP00658414393/RIUP25/0080/PRAVEEN KUMAR/PUNB0123500 78132.00
68219 | [17 empty] | 33824 | 30-04-2025 NEFT/AXISP00658414394/RIUP25/0177/PRAVEEN KUMAR/PUNB0123500 33824.00