## Sheet1
Subcontractor: | Raghuveer Singh & Sons
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Hold Amount for quantity more than DPR | GST_SD_Amount | Final_Amount |  | Total_Amount | UTR
[7 empty] | 18% |  | 2% | 5% | 10% | 10% |  | 18%
53204 | [15 empty] | 53204
53204 | Mukundpur Village Pipe laying work | 2023-01-04 | 92 | 427841 | 0 | 427841 | 77011 | 504852 | 8556.82 | 21392.05 | 42784.1 | 42784.1 | 40383 | 77011 | 271941 |  | 271941 | 17-01-2023 NEFT/AXISP00355634807/RIUP22/1823/RAGHUVEER SINGH 271941.00
53204 | Mukundpur Village Pipe laying work | 2023-02-04 | 96 | 66870 | 0 | 66870 | 12037 | 78907 | 1337.4 | 3343.5 | 6687 | 6687 | 0 | 12037 | 48815 |  | 48815 | 06-05-2023 NEFT/AXISP00388047283/SPUP23/0351/RAGHUVEER SINGH 48815.00
53204 | GST Release Note | 2023-04-20 | 92 | 77011 |  | 77011 | 0 | 77011 | 0 | 0 | 0 | 0 | 0 | 0 | 77011 |  | 89048 | 12-05-2023 NEFT/AXISP00389894140/RIUP23/199/RAGHUVEER SINGH 89048.00
53204 | GST Release Note | 2023-04-21 | 96 | 12037 |  | 12037 | 0 | 12037 | 0 | 0 |  |  |  | 0 | 12037 |  | 66644 | 05-08-2023 NEFT/AXISP00412924934/RIUP23/1381/RAGHUVEER SINGH 66644.00
53204 | Mukundpur Village Pipe laying work | 2023-05-20 | 2 | 91293 |  | 91293 | 16433 | 107726 | 1825.86 | 4564.65 | 9129.3 | 9129.3 | 0 | 16433 | 66643.89 |  | 352346 | 13-10-2023 NEFT/AXISP00434019637/RIUP23/2549/RAGHUVEER SINGH AN/UBIN0551376 3,52,346.00
53204 | Mukundpur Village Pipe laying work | 2023-10-03 | 5 | 495623.5 | 12960 | 482663.5 | 86879 | 569542.5 | 9653.27 | 24133.175 | 48266.35 | 48266.35 | 0 | 86879 | 352344 |  | 413922 | 01-11-2023 NEFT/AXISP00439227023/RIUP23/2975/RAGHUVEER SINGH AN/UBIN0551376 413922.00
53204 | Mukundpur Village Pipe laying work | 2023-10-25 | 7 | 680280.5 | 17982 | 662298.5 | 119214 | 781512.5 | 13245.97 | 33114.925 | 66229.85 | 66229.85 | 69556 | 119214 | 413922 |  | 161115 | 12-01-2024 NEFT/AXISP00462196163/RIUP23/4155/RAGHUVEER SINGH AN/UBIN0551376 161115.00
53204 | Mukundpur Village Pipe laying work | 2023-12-27 | 22 | 333209.25 | 112503.3 | 220705.95 | 39727 | 260432.95 | 4414.119 | 11035.2975 | 22070.595 | 22070.595 |  | 39727 | 161115 |  | 262254 | 06-03-2024 NEFT/AXISP00477945206/RIUP23/4759/RAGHUVEER SINGH AN/UBIN0551376 262254.00
53204 | GST Release Note |  | 2,5,7 & 22 | 262253 | [10 empty] | 262253 |  | 308199 | 16-07-2024 NEFT/AXISP00519021663/RIUP24/0974/RAGHUVEER SINGH AN/UBIN0551376 308199.00
53204 | Mukundpur Village Pipe laying work | 2024-06-15 | 5 | 457692 | 34731 | 422961 | 76133 | 499094 | 8459.22 | 21148.05 | 42296.1 | 42296.1 | 563 | 76133 | 308199 |  | 225000 | 29-08-2024 NEFT/AXISP00533102971/RIUP24/1378/RAGHUVEER SINGH AN/UBIN0551376 225000.00
53204 | Mukundpur Village Pipe laying work | 2024-07-26 | 7 | 414364.5 |  | 414364.5 | 74585.61 | 488950.11 | 8287.29 | 20718.225 | 41436.45 | 41436.45 | 70000 | 74585.61 | 232486 |  | 73500 | 20-09-2024 NEFT/AXISP00542641361/RIUP24/1873/RAGHUVEER SINGH AN/UBIN0551376 73500.00
53204 | GST Release Note |  | 5 | 76133 | [10 empty] | 76133 |  | 150719 | 10-02-2025 NEFT/AXISP00613794875/RIUP24/2210/RAGHUVEER SINGH AN/UBIN0551376 150719.00
53204 | GST Release Note |  | 7 | 74585.61 | [10 empty] | 74585.61
52438 | [15 empty] | 52438
52438 | Mohammadpur Madan Village Pipe laying work | 2022-09-30 | 89 | 533389 | 0 | 533389 | 96010 | 629399 | 10667.78 | 26669.45 | 26669.45 | 53338.9 | 76520 | 96010 | 339523 |  | 245000 | 14-09-2022 NEFT/AXISP00320017433/RIUP22/737/RAGHUVEER SINGH 245000.00
52438 | GST Release Note | 2022-11-18 | 89 | 96010 |  | 96010 | 0 | 96010 | 0 | 0 |  |  |  | 0 | 96010 |  | 94523 | 20-10-2022 NEFT/AXISP00330179782/RIUP22/1049/RAGHUVEER SINGH 94523.00
52438 | Mohammadpur Madan Village Pipe laying work | 2023-02-04 | 97 | 540589 |  | 540589 | 97306 | 637895 | 10811.78 | 27029.45 | 54058.9 | 54058.9 |  | 97306 | 394629.97 |  | 96010 | 19-11-2022 NEFT/AXISP00339152072/RIUP22/1302/RAGHUVEER SINGH 96010.00
52438 | GST Release Note | 2023-04-20 | 97 | 97306 |  | 97306 | 0 | 97306 | 0 | 0 |  |  |  | 0 | 97306 |  | 98000 | 23-01-2023 NEFT/AXISP00356620192/RIUP22/1936/RAGHUVEER SINGH ₹ 98,000.00
52438 | Mohammadpur Madan Village Pipe laying work | 2023-05-20 | 3 | 19748 |  | 19748 | 3555 | 23303 | 394.96 | 987.4 | 1974.8 | 1974.8 | 12217 | 3555 | 2199 |  | 294000 | 09-03-2023 NEFT/AXISP00370113978/RIUP22/2539/RAGHUVEER SINGH 294000.00
52438 | Mohammadpur Madan Village Pipe laying work | 2023-12-07 | 10 | 691074 |  | 691074 | 124393.32 | 815467.32 | 13821.48 | 34553.7 | 69107.4 | 69107.4 | 0 | 124393.32 | 504484.02 |  | 2630 | 06-05-2023 NEFT/AXISP00388049691/SPUP23/0352/RAGHUVEER SINGH 2630.00
52438 | Mohammadpur Madan Village Pipe laying work | 2023-12-27 | 13 | 716042.25 |  | 716042.25 | 128887.605 | 844929.855 | 14320.845 | 35802.1125 | 71604.225 | 71604.225 | 0 | 128887.605 | 522710.8425 |  | 97306 | 12-05-2023 NEFT/AXISP00389894117/RIUP23/200/RAGHUVEER SINGH 97306.00
52438 | GST Release Note |  | 3, 10 ,13 | 256835.925 | [10 empty] | 256835.925 |  | 2199 | 01-07-2023 NEFT/AXISP00402764253/RIUP23/970/RAGHUVEER SINGH 2199.00
52438 | Mohammadpur Madan Village Pipe laying work | 2024-09-19 | 9 | 515890 | 330484 | 185406 | 33373.08 | 218779.08 | 3708.12 | 9270.3 | 18540.6 | 18540.6 | 73494 | 33373.08 | 61852.38 |  | 504485 | 18-12-2023 NEFT/AXISP00453898735/RIMP23/3779/RAGHUVEER SINGHAN/UBIN0551376 504485.00
52438 | GST Release Note |  | 9 | 33373.08 | [10 empty] | 33373.08 |  | 522711 | 06-01-2024 NEFT/AXISP00460284752/RIUP23/4092/RAGHUVEER SINGH AN/UBIN0551376 5,22,711.00
52438 | [16 empty] | 256836 | 06-03-2024 NEFT/AXISP00477945207/RIUP23/4758/RAGHUVEER SINGH AN/UBIN0551376 256836.00
52438 | [16 empty] | 61852 | 20-09-2024 NEFT/AXISP00542641360/RIUP24/1866/RAGHUVEER SINGH AN/UBIN0551376 61852.00
52438 | [16 empty] | 33373 | 30-01-2025 NEFT/AXISP00606020249/RIUP24/2967/RAGHUVEER SINGH AN/UBIN0551376 33373.00
51759 | [15 empty] | 51759
51759 | Mandi Village Pipe laying work | 2022-09-30 | 88 | 1242338 | 0 | 1242338 | 223620.84 | 1465958.84 | 24846.76 | 62116.9 | 62116.9 | 124233.8 | 109689 | 223620.84 | 859334.64 |  | 294000 | 14-09-2022 NEFT/AXISP00320017432/RIUP22/736/RAGHUVEER SINGH 294000.00
51759 | GST Release Note | 2022-10-31 | 88 | 223621 | 0 | 223621 | 0 | 223621 | 0 | 0 | 0 | 0 | 0 | 0 | 223621 |  | 490000 | 12-10-2022 NEFT/AXISP00327753846/RIUP22/973/RAGHUVEER SINGH 490000.00
51759 | Mandi Village Pipe laying work | 2022-12-18 | 91 | 525849 | 0 | 525849 | 94653 | 620502 | 10516.98 | 26292 | 52585 | 52585 | 64237 | 94653 | 319633 |  | 75333 | 20-10-2022 NEFT/AXISP00330179776/RIUP22/1003/RAGHUVEER SINGH 75333.00
51759 | GST Release Note | 2023-01-24 | 91 | 94653 | 0 | 94653 | 0 | 94653 | 0 | 0 | 0 | 0 | 0 | 0 | 94653 |  | 196000 | 18-11-2022 NEFT/AXISP00338948738/RIUP22/1296/RAGHUVEER SINGH 196000.00
51759 | Mandi Village Pipe laying work | 2023-02-04 | 95 | 108010 | 0 | 108010 | 19442 | 127452 | 2160.2 | 5401 | 10801 | 10801 | 0 | 19442 | 78847 |  | 223621 | 18-11-2022 NEFT/AXISP00338948740/RIUP22/1297/RAGHUVEER SINGH 223621.00
51759 | GST Release Note | 2023-04-20 | 95 | 19442 | 0 | 19442 | 0 | 19442 | 0 | 0 | 0 | 0 | 0 | 0 | 19442 |  | 196000 | 21-12-2022 NEFT/AXISP00347873505/RIUP22/1587/RAGHUVEER SINGH 196000.00
51759 | Mandi Village Pipe laying work | 2023-05-11 | 1 | 151502 | 0 | 151502 | 27270 | 178772 | 3030.04 | 7575 | 15150 | 15150 | 0 | 27270 | 110597 |  | 147000 | 04-01-2023 NEFT/AXISP00351745739/RIUP22/1783/RAGHUVEER SINGH ₹ 1,47,000.00
51759 | Mandi Village Pipe laying work | 17.01-2024 | 23 | 1322071 | 10800 | 1311271 | 236028.78 | 1547299.78 | 26225.42 | 65563.55 | 131127.1 | 131127.1 | 38170 | 236028.78 | 919057.83 |  | 19442 | 26-04-2023 26-04-2023 NEFT/AXISP00384433559/SPUP23/0282/RAGHUVEER SINGH 19442.00
51759 | GST Release Note |  | 1 | 27270 | [10 empty] | 27270 |  | 64731 | 29-05-2023 NEFT/AXISP00393029882/RIUP23/261/RAGHUVEER SINGH 64731.00
51759 | GST Release Note |  | 23 | 236028.78 | [10 empty] | 236028.78 |  | 919058 | 30-01-2024 NEFT/AXISP00465687466/RIUP23/4368/RAGHUVEER SINGH AN/UBIN0551376 9,19,058.00
51759 | Mandi Village Pipe laying work | 2024-05-15 | 3 | 275542 |  | 275542 | 49597.56 | 325139.56 | 5510.84 | 13777.1 | 27554.2 | 27554.2 | 66092 | 49597.56 | 135053.66 |  | 27270 | 22-03-2024 NEFT/AXISP00483612629/RIUP23/4757/RAGHUVEER SINGH AN/UBIN0551376 27270.00
51759 | GST Release Note |  | 3 | 49597.56 | [10 empty] | 49597.56 |  | 200000 | 21-06-2024 NEFT/AXISP00510912036/RIUP24/0597/RAGHUVEER SINGH AN/UBIN0551376 200000.00
51759 | [16 empty] | 135054 | 05-07-2024 NEFT/AXISP00515811475/RIUP24/0598/RAGHUVEER SINGH AN/UBIN0551376 135054.00
51759 | [16 empty] | 36029 | 05-07-2024 NEFT/AXISP00515811476/RIUP24/1061/RAGHUVEER SINGH AN/UBIN0551376 36029.00
51759 | [16 empty] | 98000 | 13-09-2024 NEFT/AXISP00540414541/RIUP24/1789/RAGHUVEER SINGH AN/UBIN0551376 98000.00
51759 | [16 empty] | 98000 | 20-09-2024 NEFT/AXISP00542641362/RIUP24/1874/RAGHUVEER SINGH AN/UBIN0551376 98000.00
51759 | [16 empty] | 49598 | 07-02-2025 NEFT/AXISP00612495137/RIUP24/2206/RAGHUVEER SINGH AN/UBIN0551376 49598.00
58618 | [15 empty] | 58618
58618 | MOHAMMADPUR MADAN Village OHT 200KL 12M staging work | 2023-07-27 | 4 | 712500 | 313556 | 398944 | 71809.92 | 470753.92 | 7978.88 | 19947.2 | 39894.4 |  | 0 | 71809.92 | 331123.52 |  | 331124 | 02-08-2023 NEFT/AXISP00412149931/RIUP23/1353/RAGHUVEER SINGH 331124.00
58618 | MOHAMMADPUR MADAN Village OHT 200KL 12M staging work | 2023-12-08 | 11 | 855000 |  | 855000 | 153900 | 1008900 | 17100 | 42750 | 85500 |  | 0 | 153900 | 709650 |  | 196000 | 22-09-2023 NEFT/AXISP00426907980/RIUP23/2211/RAGHUVEER SINGH AN/UBIN0551376 196000.00
58618 | GST Release Note |  | 4 , 11 | 225709.92 | [10 empty] | 225709.92 |  | 513650 | 14-12-2023 NEFT/AXISP00452996800/RIUP23/3685/RAGHUVEER SINGHAN/UBIN0551376 513650.00
58618 | MOHAMMADPUR MADAN Village OHT 200KL 12M staging work | 2024-03-08 | 27 | 8792.7 |  | 8792.7 | 1582.686 | 10375.386 | 175.854 | 439.635 |  |  | 0 | 1582.686 | 8177.211 |  | 225710 | 27-02-2024 NEFT/AXISP00474275529/RIUP23/4760/RAGHUVEER SINGH AN/UBIN0551376 225710.00
58618 | GST Release Note |  | 27 | 1582.686 | [10 empty] | 1582.686 |  | 397575 | 26-03-2024 NEFT/AXISP00484218144/RIUP23/5283/RAGHUVEER SINGHAN/UBIN0551376 397575.00
58618 | MOHAMMADPUR MADAN Village OHT 200KL 12M at work | 2024-05-05 | 4 | 2930.9 |  | 2930.9 | 527.562 | 3458.462 | 58.618 | 146.545 |  |  | 0 | 527.562 | 2725.737 |  | 132525 | 31-07-2024 NEFT/AXISP00522966385/RIUP24/0665/RAGHUVEER SINGH AN/UBIN0551376 132525.00
58618 | GST Release Note |  | 4 | 527.562 | [10 empty] | 527.562 |  | 76950 | 31-07-2024 NEFT/AXISP00522966387/RIUP24/1160/RAGHUVEER SINGH AN/UBIN0551376 76950.00
58618 | [16 empty] | 25650 | 30-01-2025 NEFT/AXISP00606020245/RIUP24/2207/RAGHUVEER SINGH AN/UBIN0551376 25650.00
60112 | [15 empty] | 60112
60112 | Mandi villahe OHT work | 2023-11-07 | 8 | 796875 | 225613 | 571262 | 102827.16 | 674089.16 | 11425.24 | 28563.1 | 0 |  |  | 102827.16 | 531273.66 |  | 245000 | 09-11-2023 NEFT/AXISP00442779071/RIUP23/3206/RAGHUVEER SINGH AN/UBIN0551376 245000.0
60112 | Mandi villahe OHT work | 2024-02-08 | 24 | 1062500 | 70000 | 992500 | 178650 | 1171150 | 19850 | 49625 | 0 |  |  | 178650 | 923025 |  | 286275 | 06-12-2023 NEFT/AXISP00450305027/RIUP23/3467/RAGHUVEER SINGH AN/UBIN0551376 286275.00
60112 | GST Release Note |  | 8 | 102827.16 | [10 empty] | 102827.16 |  | 923025 | 15-02-2024 NEFT/AXISP00471706641/RIUP23/4687/RAGHUVEER SINGH AN/UBIN0551376 923025.00
60112 | GST Release Note |  | 24 | 178650 | [10 empty] | 178650 |  | 102827 | 07-03-2024 NEFT/AXISP00478081326/RIUP23/4761/RAGHUVEER SINGH AN/UBIN0551376 1,02,827.00
60112 | Mandi villahe OHT work | 2024-12-13 | 12 | 398438 | 0 | 398438 | 71718.84 | 470156.84 | 7968.76 | 19921.9 | 0 |  |  | 71718.84 | 370547.34 |  | 178650 | 31-07-2024 NEFT/AXISP00522966388/RIUP24/1157/RAGHUVEER SINGH AN/UBIN0551376 178650.00
60112 | GST Release Note |  | 12 | 71718.84 | [10 empty] | 71718.84 |  | 147000 | 06-09-2024 NEFT/AXISP00537489920/RIUP24/1688/RAGHUVEER SINGH AN/UBIN0551376 147000.00
60112 | Mandi villahe OHT work | 2025-03-26 | 16 | 796875 | 35208 | 761667 | 137100.06 | 898767.06 | 15233.34 | 38083.35 | 0 |  |  | 137100.06 | 708350.31 |  | 196000 | 26-12-2024 Debit N/RIUP24/2793/RAGHUVEER SING/INDBN26123786880 196000.0
60112 | Gst releae note |  | 16 | 137100.06 | [10 empty] | 137100.06 |  | 71719 | 30-01-2025 NEFT/AXISP00606020250/RIUP24/2970/RAGHUVEER SINGH AN/UBIN0551376 71719.00
60112 | [16 empty] | 200000 | 09-04-2025 NEFT/AXISP00648889490/RIUP24/3515/RAGHUVEER SINGH AN/UBIN0551376 200000.00
60112 | [16 empty] | 200000 | 25-04-2025 NEFT/AXISP00656241457/RIUP25/0147/RAGHUVEER SINGH AN/UBIN0551376 200000.00
60112 | [16 empty] | 200000 | 30-04-2025 NEFT/AXISP00658414396/RIUP25/0180/RAGHUVEER SINGH AN/UBIN0551376 200000.00
60332 | [15 empty] | 60332
60332 | Mukundpur village OHT work | 2023-11-27 | 9 | 472500 | 104671 | 367829 | 66209.22 | 434038.22 | 7356.58 | 18391.45 | 0 | 36782.9 | 225148 | 66209.22 | 80150.07 |  | 80150 | 06-12-2023 NEFT/AXISP00450230202/RIUP23/3554/RAGHUVEER SINGH AN/UBIN0551376 80150.00
60332 | Hold amount release |  | 9 | 225148 | [10 empty] | 225148 |  | 225148 | 26-12-2023 NEFT/AXISP00455532162/RIUP23/3870A/RAGHUVEER SINGH AN/UBIN0551376 225148.00
60332 | Gst releae note |  | 9 | 66209.22 | [10 empty] | 66209.22 |  | 66209 | 27-02-2024 NEFT/AXISP00474275528/RIUP23/4756/RAGHUVEER SINGH AN/UBIN0551376 ₹ 66,209.00
60332 | Mukundpur village OHT work | 2024-03-08 | 28 | 9049.8 | 92933 | -83883.2 | -15098.976 | -98982.176 | -1677.664 | -4194.16 | 0 |  |  | -15098.976 | -78011.376 |  | 250000 | 26-04-2024 NEFT/AXISP00494041782/RIUP23/5240/RAGHUVEER SINGH AN/UBIN0551376 250000.00
60332 | Gst releae note |  | 28 | -15098.976 | [10 empty] | -15098.976 |  | 102997 | 21-06-2024 NEFT/AXISP00510912035/RIUP24/0937/RAGHUVEER SINGHAN/UBIN0551376 102998.00
60332 | Mukundpur village OHT work | 2024-12-13 | 13 | 630000 | 217000 | 413000 | 74340 | 487340 | 8260 | 20650 | 0 |  |  | 74340 | 384090 |  | 68322 | 31-07-2024 NEFT/AXISP00522966386/RIUP24/1158/RAGHUVEER SINGH AN/UBIN0551376 68322.00
60332 | Gst releae note |  | 13 | 74340 | [10 empty] | 74340 |  | 98000 | 13-09-2024 NEFT/AXISP00540414542/RIUP24/1790/RAGHUVEER SINGH AN/UBIN0551376 98000.00
60332 | Mukundpur village OHT work | 2025-02-22 | 15 | 787500 | 0 | 787500 | 141750 | 929250 | 15750 | 39375 | 0 |  |  | 141750 | 732375 |  | 196000 | 23-12-2024 NEFT/AXISP00587800983/RIUP24/2794/RAGHUVEER SINGH AN/UBIN0551376 196000.00
60332 | Gst releae note |  | 15 | 141750 | [10 empty] | 141750 |  | 74340 | 11-02-2025 NEFT/AXISP00614452336/RIUP24/2971/RAGHUVEER SINGH AN/UBIN0551376 74340.00
60332 | [16 empty] | 625000 | 12-03-2025 NEFT/AXISP00632214332/RIUP24/3238/RAGHUVEER SINGH AN/UBIN0551376 625000.00
60332 | [16 empty] | 197465 | 09-04-2025 NEFT/AXISP00648889488/RIUP25/0069/RAGHUVEER SINGH AN/UBIN0551376 197465.00
60332 | [16 empty] | 98000 | 25-04-2025 NEFT/AXISP00656241459/RIUP25/0149/RAGHUVEER SINGH AN/UBIN0551376 98000.00
63746 | [15 empty] | 63746
63746 | ALIPUR KHURD VILLAGE,BALANCE OHT 150KL 12 M WORK | 2024-05-13 | 2 | 742500 | 85139 | 657361 | 118324.98 | 775685.98 | 13147.22 | 32868.05 | 0 | 0 | 0 | 118324.98 | 611345.73 |  | 450000 | 07-06-2024 NEFT/AXISP00507505915/RIUP24/0561/RAGHUVEER SINGH AN/UBIN0551376 450000.00
63746 | Gst releae note |  | 2 | 118324.98 | [10 empty] | 118324.98 |  | 161346 | 21-06-2024 NEFT/AXISP00510912032/RIUP24/0936/RAGHUVEER SINGHAN/UBIN0551376 161346.00
63746 | [16 empty] | 118325 | 07-02-2025 NEFT/AXISP00612495136/RIUP24/2205/RAGHUVEER SINGH AN/UBIN0551376 118325.00
65055 | [15 empty] | 65055
65055 | Atali Village OHT at work | 2024-07-24 | 6 | 540000 | 272211.14 | 267788.86 | 48201.9948 | 315990.8548 | 5355.7772 | 13389.443 | 0 | 0 | 0 | 48201.9948 | 249043.6398 |  | 249044 | 19-08-2024 NEFT/AXISP00529670921/RIUP24/1380/RAGHUVEER SINGH AN/UBIN0551376 249044.00
65055 | Gst releae note |  | 6 | 48201.9948 | [10 empty] | 48201.9948 |  | 48202 | 30-01-2025 NEFT/AXISP00606020246/RIUP24/2208/RAGHUVEER SINGH AN/UBIN0551376 48202.00
65055 | Atali Villlage OHT Work | 2025-02-22 | 14 | 180009 | 32430 | 147579 | 26564.22 | 174143.22 | 2951.58 | 7378.95 | 0 | 0 | 0 | 26564.22 | 137248.47 |  | 137248 | 28-03-2025 NEFT/AXISP00641455059/RIUP24/3237/RAGHUVEER SINGH AN/UBIN0551376 137248.00
65055 | Gst releae note |  | 14 | 26564.22 | [10 empty] | 26564.22
65189 | [15 empty] | 65189
65189 | DHOLARIBAL Village ANCE PIPE LAYING (CC ROAD RESTORATION) AT work | 2024-07-26 | 8 | 304705 | 78492 | 226213 | 40718.34 | 266931.34 | 4524.26 | 11310.65 | 22621.3 | 22621.3 | 339682 | 40718.34 | -174546.51 |  | 147000 | 13-09-2024 NEFT/AXISP00540414543/RIUP24/1791/RAGHUVEER SINGH AN/UBIN0551376 147000.00
65189 | Gst releae note |  | 8 | 40718.34 | [10 empty] | 40718.34 |  | 40718 | 30-01-2025 NEFT/AXISP00606020247/RIUP24/2209/RAGHUVEER SINGH AN/UBIN0551376 40718.00
66504 | [15 empty] | 66504
66504 | AMIRNAGAR VILLAGE 325KL 12M BLOCK - BAGHRA at work | 2024-10-29 | 10 | 497656 |  | 497656 | 89578.08 | 587234.08 | 9953.12 | 24882.8 |  |  |  | 89578.08 | 462820.08 |  | 441000 | 30-10-2024 NEFT/AXISP00561390210/RIUP24/2353/RAGHUVEER SINGH AN/UBIN0551376 441000.00
66504 | GST release note |  | 10 | 89578.08 | [10 empty] | 89578.08 |  | 89578 | 11-02-2025 NEFT/AXISP00614452335/RIUP24/2968/RAGHUVEER SINGH AN/UBIN0551376 89578.00
66504 | AMIRNAGAR VILLAGE 325KL 12M at work | 2025-03-27 | 17 | 398125 | 17604 | 380521 | 68493.78 | 449014.78 | 7610.42 | 19026.05 |  |  |  | 68493.78 | 353884.53 |  | 200000 | 09-04-2025 NEFT/AXISP00648889489/RIUP24/3514/RAGHUVEER SINGH AN/UBIN0551376 200000.00
66504 | GST release note |  | 17 | 68493.78 | [10 empty] | 68493.78 |  | 100000 | 25-04-2025 NEFT/AXISP00656241458/RIUP25/0148/RAGHUVEER SINGH AN/UBIN0551376 100000.00
66504 | AMIRNAGAR VILLAGE 325KL 12M at work | 2025-04-25 | 1 | 497656 | 0 | 497656 | 89578.08 | 587234.08 | 9953.12 | 24882.8 |  |  |  | 89578.08 | 462820.08 |  | 200000 | 08-05-2025 NEFT/AXISP00662656519/RIUP25/0217/RAGHUVEER SINGH AN/UBIN0551376 200000.00
66504 | [16 empty] | 250000 | 21-05-2025 NEFT/AXISP00668416305/RIUP25/0297/RAGHUVEER SINGH AN/UBIN0551376 250000.00
66504 | [16 empty] | 147000 | 21-05-2025 NEFT/AXISP00668416306/RIUP25/0298/RAGHUVEER SINGH AN/UBIN0551376 147000.00
66505 | [15 empty] | 66505
66505 | ALIPUR KHURD Village RR at work | 2024-10-29 | 11 | 405553 | 277945 | 127608 | 22969.44 | 150577.44 | 2552.16 | 6380.4 | 12760.8 | 12760.8 |  | 22969.44 | 93153.84 |  | 88200 | 30-10-2024 NEFT/AXISP00561390209/RIUP24/2352/RAGHUVEER SINGH AN/UBIN0551376 88200.00
66505 | GST release note |  | 11 | 22969.44 | [10 empty] | 22969.44 |  | 22970 | 06-03-2025 NEFT/AXISP00628995534/RIUP24/2969/RAGHUVEER SINGH AN/UBIN0551376 22970.00

## TMT
| BILL NO/BILL DATE | PURCHASE FROM | 8MM | 10MM | 12MM | 16MM | 20MM | Date Of Issue | Issue Slip No | Name of Party | SIZE (IN MM) | QTY (TON) |  |  | GST (18%) | Amount (In Rs.) | ISSUE | DEBIT NOTE NO. | CONTRACTOR INVOICE DETAIL
370 | [7 empty] | 26.05.2023 | 3581 | Raghuveer Singh & Sons | 8MM | 0.080425 | 63950 | 5143.1762 | 925.7717 | 6068.9479 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
371 | [7 empty] | 26.05.2023 | 3581 | Raghuveer Singh & Sons | 10MM | 0.10349 | 62450 | 6462.8256 | 1163.3086 | 7626.1342 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
372 | [7 empty] | 26.05.2023 | 3581 | Raghuveer Singh & Sons | 12MM | 0.12773 | 62450 | 7976.9733 | 1435.8552 | 9412.8285 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
373 | [7 empty] | 26.05.2023 | 3581 | Raghuveer Singh & Sons | 16MM | 1.0029 | 61450 | 61631.0661 | 11093.5919 | 72724.658 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
379 | [7 empty] | 26.05.2023 | 3866 | Raghuveer Singh & Sons | 8MM | 0.094618 | 63950 | 6050.7955 | 1089.1432 | 7139.9387 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
380 | [7 empty] | 26.05.2023 | 3866 | Raghuveer Singh & Sons | 10MM | 0.70224 | 62450 | 43854.888 | 7893.8798 | 51748.7678 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
381 | [7 empty] | 26.05.2023 | 3866 | Raghuveer Singh & Sons | 12MM | 0.74511 | 62450 | 46532.3443 | 8375.822 | 54908.1663 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
382 | [7 empty] | 26.05.2023 | 3866 | Raghuveer Singh & Sons | 16MM | 0.37847 | 61450 | 23257.0061 | 4186.2611 | 27443.2672 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023
415 | [7 empty] | 16.06.2023 | 3448 | Raghuveer Singh & Sons | 8MM | 0.648 | 63950 | 41439.6 | 7459.128 | 48898.728 | Mukundpur VILLAGE | 848/ 30.10.2023 | BILL MUKUNDPUR 30.10.2023
433 | [7 empty] | 17.06.2023 | 4298 | Raghuveer Singh & Sons | 10MM | 0.75398 | 62450 | 47086.3008 | 8475.5341 | 55561.8349 | Mukundpur VILLAGE | 848/ 30.10.2023 | BILL MUKUNDPUR 30.10.2023
434 | [7 empty] | 17.06.2023 | 4298 | Raghuveer Singh & Sons | 12MM | 0.53222 | 62450 | 33237.3888 | 5982.73 | 39220.1188 | Mukundpur VILLAGE | 847/ 30.10.2023 | BILL MANDI 30.10.2023
435 | [7 empty] | 17.06.2023 | 4298 | Raghuveer Singh & Sons | 16MM | 1.3814 | 61450 | 84888.0722 | 15279.853 | 100167.9252 | Mukundpur VILLAGE | 847/ 30.10.2023 | BILL MANDI 30.10.2023
436 | [7 empty] | 17.06.2023 | 4298 | Raghuveer Singh & Sons | 20MM | 1.1827 | 61450 | 72678.144 | 13082.0659 | 85760.2099 | Mukundpur VILLAGE | 847/ 30.10.2023 | BILL MANDI 30.10.2023

## cement
| Date Of Issue | Issue Slip No | Name of Party | QTY (BAG) | IN TON | RATE (PER TON) |  | GST (28%) | Amount (In Rs.) | ISSUE FOR | DEBIT NOTE NO. | CONTRACTOR INVOICE DETAIL
288 | 31.05.2023 | 4029 | RAGHUNATH SINGH & SONS | 200 | 10 | 5859.38 | 58593.8 | 16406.264 | 75000.064 | MOHAMMADPUR MADAN VILLAGE | 537/27.06.2023

## Diesel
S.NO. | Date Of Issue | Issue Slip No | Name of Party | FUEL (In Ltr) | Petrol Pump Slip No. | Latest Rate | Amount (In Rs.) | Vehicle No. | Remarks | ISSUE FOR | DEBIT NOTE NO. | Tax Invocies On PMC
1427 | 02.08.2023 | 3641 | RAGHUVEER SINGH & SONS | 200 | 1734 | 89.91 | 17982 |  | DEBIT TO RAGHUVEER SINGH & SONS | MOHMMADPUR MARDAN | 834/ 23.10.2023 | BILL MUKUNDPUR 23.10.2023