## Sheet1
Subcontractor: | Rakesh Kumar
State: | Uttar Pradesh |  | Rakesh Kumar |  |  | Pump House work
District: | Shamli
Block: | Shamli | [15 empty] | 2024-10-30
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Advance Given At Site | Hold Amount (Excess work against DPR ) | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18% | [6 empty] | 1%
58065
58065 | Jalalpur village Pump House work | 2023-07-05 | 1 | 43450 | 0 | 43450 |  | 43450 | 435 | 2173 | 4345 | 4345 | 0 |  | 0 | 32152 |  | RIUP23/1169 | 32152 | 0 | 32152 | 24-07-2023 NEFT/AXISP00408846966/RIUP23/1169/RAKESH KUMAR 32152.00 | 29016
58065 | Jalalpur village Pump House work | 2023-10-12 | 4 | 72610 | 0 | 72610 |  | 72610 | 726 | 3631 | 7261 | 7261 | 0 |  | 22000 | 31731 |  | RIUP23/2862 | 31731 | 0 | 31731 | 25-10-2023 NEFT/AXISP00436928373/RIUP23/2862/RAKESH KUMAR/PUNB0SUPGB5 31731.00
58065 | withheld amt - SD HT OC |  | 1 & 4 | 29016 | [11 empty] | 29016
58872
58872 | Dhanena village Pump House work | 2023-08-14 | 3 | 19680 | 0 | 19680 | 0 | 19680 | 197 | 984 | 1968 | 1968 | 0 |  |  | 14563 |  |  |  |  | 15000 | Adv at site | 4483
58872 | withheld amt - SD HT OC |  | 3 | 4920 | [11 empty] | 4920
58758
58758 | Mahavatapur Village Pump house work | 2023-08-06 | 2 | 9600 | 0 | 9600 | 0 | 9600 | 96 | 480 | 960 | 960 | 0 | 0 | 0 | 7104 |  | RIUP23/1824 |  |  | 7104 | 04-09-2023 NEFT/AXISP00421476872/RIUP23/1824/RAKESH KUMAR/PUNB0SUPGB5 7104.00 | 2400
58758 | withheld amt - SD HT OC |  | 2 | 2400 | [11 empty] | 2400
59340
59340 | Jaferpur Village Pipeline work | 2024-03-31 | 6 | 74380 | 6305 | 68075 | 0 | 68075 | 680.75 | 3403.75 |  |  | 0 | 0 | 0 | 63990.5 |  | RIUP23/2162 |  |  | 19800 | 20-09-2023 NEFT/AXISP00426184645/RIUP23/2162/RAKESH KUMAR/PUNB0SUPGB5 19800.00 | 14490.5
[18 empty] | RIUP23/3062 |  |  | 29700 | 03-11-2023 NEFT/AXISP00440155799/RIUP23/3062/RAKESH KUMAR/PUNB0SUPGB5 29700.00
61351
61351 | Akapur Village Pipeline work | 2023-12-25 | 5 | 137954.16 | 0 | 137954.16 |  | 137954.16 | 1379.5416 | 6897.708 | 13795.416 | 13795.416 | 0 | 0 | 0 | 102086.0784 |  | RIUP23/4190 |  |  | 102086 | 11-01-2024 NEFT/AXISP00461589008/RIUP23/4190/RAKESH KUMAR/PUNB0SUPGB5 102086.00 | 63327.5184
61351 | Akapur Village Pipeline work | 2024-03-31 | 7 | 175506 | 0 | 175506 |  | 175506 | 1755.06 | 8775.3 | 17550.6 | 17550.6 | 0 | 0 | 1035 | 128839.44 |  |  |  |  | 50000 | 13-09-2024 NEFT/AXISP00540414549/RIUP24/0815/RAKESH KUMAR/PUNB0SUPGB5 50000.00
61351 | withheld amt - SD HT OC |  | 5 | 34488 | [11 empty] | 34488 |  |  |  |  | 50000 | 21-12-2024 NEFT/AXISP00587304761/RIUP24/2777/RAKESH KUMAR/PUNB0SUPGB5 50000.00
[9 empty] | 5269.3516 | 26344.758 | 45880.016 | 45880.016 | 0 | 0 | Total Payable Amount Rs. - | 451290.0184 |  | Total Paid Amount Rs. - |  |  | 337573 |  | 113717.0184
[10 empty] | 12179.05 | 17550.6 | 17550.6 |  |  | 23035
[18 empty] | Balance Payable Amount Rs. - |  |  | 113717.0184
Rakesh Kumar
2024-12-23
[16 empty] | Total Hold | 47280.25
[16 empty] | DPR Excess | 23035
[16 empty] | GST | URD
[16 empty] | Advance / Surplus | 113717.0184