## Sheet1
Subcontractor: | M/s SM Bharat construction co.
State: | Uttar Pradesh |  | M/s SM Bharat construction co. |  |  |  |  | Pipe Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Hold the Amount because the Qty. is more then the DPR | Aadhar Card recovery | GST_SD_Amount | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 5% | 10% |  |  | 18% |  |  |  |  | 2% | 5%
55626
55626 | Bhandaura Village Pipe laying work | 2023-03-20 | 1 | 511389.9 | 0 | 511389.9 | 92050 | 603439.9 | 5114 | 25569 | 25569 | 51139 | 97520.4 |  | 92050 | 306479 |  | RIUP22/2763 | 306479 | 0 |  |  | 306479 | 29-03-2023 NEFT/AXISP00376153232/RIUP22/2763/SM BHARAT CONST 306479.00
55626 | Bhandaura Village Pipe laying work | 2023-04-19 | 2 | 422000.9 | 0 | 422000.9 | 75960 | 497960.9 | 4220 | 21100 | 21100 | 42200 | 0 |  | 75960 | 333381 |  | RIUP22/2772 | 97520 | 0 |  |  | 97520 | 30-03-2023 NEFT/AXISP00376411976/RIUP22/2772/SM BHARAT CONST 97520.00
55626 | Hold Amount Release |  | 1 | 97520 | [11 empty] | 97520 |  | SPUP23/0317 | 333380 | 0 | 0 | 0 | 333380 | 29-04-2023 29-04-2023 NEFT/AXISP00385662368/SPUP23/0317/SM BHARAT CONST 333380.00
55626 | GST Release note | 2023-09-08 | 1 | 92050 | [11 empty] | 92050 |  | RIUP23/2028 | 92050 |  | 0 | 0 | 92050 | 15-09-2023 NEFT/AXISP00425358567/RIUP23/2028/SM BHARAT CONSTRUC/HDFC0009249 92050.00
55626 | GST Release note | 2023-09-14 | 2 | 75960 | [11 empty] | 75960 | [6 empty] | 75960 | 26-10-2023 NEFT/AXISP00437006013/RIUP23/2760/SM BHARAT CONSTRUC/HDFC0009249 75960.00
[17 empty] | 54424 |  |  | 0 | 0 | 0 | 0 |  | 1
54424 | Athia village Pipe line work | 2023-08-05 | 3 | 857040.79 | 0 | 857040.79 | 154267 | 1011307.79 | 8570 | 42852 | 42852 | 85704 | 131246 | 4000 | 154267 | 541817 |  | RIUP23/265 | 100000 | 1000 | 0 | 0 | 99000 | 16-05-2023 NEFT/AXISP00390411255/RIUP23/265/SM BHARAT CONSTR 99000.00
54424 | GST Release note |  | 3 | 154267 | [11 empty] | 154267 | [6 empty] | 168000 | 11-09-2023 NEFT/AXISP00423685733/RIUP23/1464/SM BHARAT CONSTRUC/HDFC0009249 168000.00
54424 | [22 empty] | 274817 | 02-11-2023 NEFT/AXISP00439799509/RIUP23/3043/SM BHARAT CONSTRUC/HDFC0009249 274817.00
54424 | [24 empty] | 154267
[10 empty] | 89521 | 89521 | 179043 | 228766.4 | 4000 | 322277 | 1601474 |  |  |  | Total Paid Amount Rs. - |  |  | 1447206
[20 empty] | Balance Payable Amount Rs. - |  |  | 154268
Updated as on- 01-07-2024
[14 empty] | Advance / Surplus | 154268