## Sheet1
Subcontractor: | SR Enterprises
State: | Uttar Pradesh |  | SR Enterprises |  |  |  | Pipeline Laying work
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 5% & 10% | 10% | [6 empty] | 1%
54116
54116 | Barnabi Village Pipeline laying work | 2022-12-17 | 2 | 1092397.59 | 99077 | 993320.59 | 178797.7062 | 1172118 | 9933 | 49666.0295 | 99332.059 | 99332.059 | 178797.7062 | 78458 | 656599 |  | RIUP22/1706 | 656599 | 0 | 656599 | 31-12-2022 IFT/IFT22365031241/RIUP22/1706/S R ENTERPRISES 656599.00
54116 | Barnabi Village Pipeline laying work | 2023-01-21 | 3 | 823956 | 126098 | 697858 | 125614.44 | 823472 | 6979 | 34892.9 | 69785.8 | 69785.8 | 125614.44 | 90602 | 425812 |  | RIUP22/2054 | 425811 | 0 | 425811 | 31-01-2023 IFT/IFT23031169043/RIUP22/2054/S R ENTERPRISES ₹ 4,25,811.00
54116 | GST release note | 2023-02-03 | 2 | 178797.7062 |  | 178797.7062 |  | 178797.7062 | [6 empty] | 178797.7062 |  | RIUP22/2153 | 178798 | 0 | 178798 | 10-02-2023 IFT/IFT23041057326/RIUP22/2153/S R ENTERPRISES ₹ 1,78,798.00
54116 | Barnabi Village Pipeline laying work | 2023-02-28 | 5 | 759934.24 | 36028 | 723906.24 | 130303.1232 | 854209.3632 | 7239.0624 | 36195.312 | 72390.624 | 72390.624 | 130303.1232 | 267482 | 268209 |  | RIUP22/2212 | 99000 | 0 | 99000 | 17-02-2023 IFT/IFT23048032051/RIUP22/2212/S R ENTERPRISES 99000.00
54116 | GST release note | 2023-03-31 | 3 | 125614.44 | [5 empty] | 0 |  |  |  |  | 125614.44 |  | RIUP22/2593/ | 346500 |  | 346500 | 15-03-2023 IFT/IFT23074020149/RIUP22/2593/S R ENTERPRISES 346500.00
54116 | GST release note | 2023-09-05 | 5 | 130303 | [10 empty] | 130303 |  | RIUP22/2747 | 99000 |  | 99000 | 27-03-2023 IFT/IFT23086032016/RIUP22/2747/S R ENTERPRISES 99000.00
54116 | [17 empty] | 125614 |  | 125614 | 2023 April 05 -------- S R Enterprises ---------- IFT23095076372/ ------------ Rs. 1,25,614
54116 | [16 empty] | RIUP23/2182 | 121492 | 0 | 121492 | 21-09-2023 IFT/IFT23264016659/RIUP23/2182/S R ENTERPRISES 121492.00
54116
[16 empty] | 52849 | [5 empty] | -267478.8538
52849 | Mandawar Village Pipeline laying work | 20/10/23 | 1 | 462347.6 | 54042 | 408306 | 73495 | 481801 | 4083 | 20415 | 20415 | 40831 | 73495 | 39688 | 282874 |  | RIUP22/1150 | 282873 | 0 | 282873 | 05-11-2022 IFT/IFT22309020146/RIUP22/1150/S R ENTERPRISES 282873.00
52849 | Mandawar Village Pipeline laying work | 2023-01-21 | 4 | 478185 | 45035 | 433150 | 77967 | 511117 | 4331.5 | 21657.5 | 21657.5 | 43315 | 77967 | 163321 | 178868 |  | RIUP22/2058 | 178868 | 0 | 178868 | 31-01-2023 IFT/IFT23031182443/RIUP22/2058/S R ENTERPRISES 178868.00
52849 | GST release note | 2023-02-03 | 1 | 73495 | 0 | 73495 | 0 | 73495 | 0 | [5 empty] | 73495 |  | RIUP22/2152 | 73495 | 0 | 73495 | 13-02-2023 IFT/IFT23044011788/RIUP22/2152/S R ENTERPRISES 73495.00
52849 | GST release note | 2023-03-31 | 4 | 77967 | 0 | 77967 | 0 | 77967 | 0 | 0 |  |  | 0 |  | 77967 |  | RIUP22/2246 | 99000 |  | 99000 | 21-02-2023 NEFT/AXISP00364387949/RIUP22/2246/S R ENTERPRISES 99000.00
52849 | Mandawar Village Pipeline laying work | 2024-05-02 | 3 | 291460 | 9007 | 282453 | 50841.54 | 333295 | 2825 | 14122.65 | 28245.3 | 28245.3 | 50841.54 | 83664 | 125351 |  |  | 77967 |  | 77967 | 2023 April 05 ----------- S R Enterprises ------------- IFT23095076374 ------------ Rs. 77,967
52849 | Mandawar Village Pipeline laying work | 2024-06-14 | 4 | 953948 | 940531 | 13417 | 2415.06 | 15832 | 134 | 670.85 | 1341.7 | 1341.7 | 2415.06 |  | 9929 |  |  |  |  | 26350 | 14-08-2024 IFT/IFT24227020859/RIUP24/1123/S R ENTERPRISES 26350.00
52849 | GST release note | 2024-05-02 | 3 | 50841.54 | [10 empty] | 50841.54
52849 | GST release note | 2024-06-14 | 4 | 2415.06 | [10 empty] | 2415.06
52849
[16 empty] | 56697 | [5 empty] | 63187.6
56697 | KHERI KARMU Village Pipe Line & RR work | 2023-04-11 | 1 | 839876 | 81063 | 758813 | 136586.34 | 895399.34 | 7588.13 | 37940.65 | 75881.3 | 75881.3 | 136586.34 | 103207 | 458314.62 |  |  |  |  | 297000 | 21-04-2023 IFT/IFT23111033829/RIUP23/053/S R ENTERPRISES 297000.00
56697 | KHERI KARMU Village Pipe Line & RR work | 2023-06-04 | 3 | 355512 | 139521.75 | 215990.25 | 38878.245 | 254868.495 | 2159.9025 | 10799.5125 | 21599.025 | 21599.025 | 38878.245 |  | 159832.785 |  |  |  |  | 161314 | 16-05-2023 NEFT/AXISP00342589632/RIUP23/266/SR ENTERPRISE 161314.00
56697 | GST release note |  | 1 | 136586.34 | 0 |  |  |  | 0 | [5 empty] | 136586.34 |  |  |  |  | 99000 | 22-06-2023 IFT/IFT23173012783/RIUP23/804/S R ENTERPRISES 99000.00
56697 | GST release note |  | 3 | 38878.245 | 0 |  |  |  | 0 | 0 |  |  | 0 |  | 38878.245 |  |  |  |  | 60832 | 28-06-2023 IFT/IFT23179012455/RIUP23/812/S R ENTERPRISES 60832.00
56697 | KHERI KARMU Village Pipe Line & RR work | 2024-04-24 | 1 | 850837 | 1 | 850836 | 153150.48 | 1003986.48 | 8508.36 | 42541.8 | 85083.6 | 85083.6 | 153150.48 |  | 629618.64 |  |  |  |  | 175464 | 26-10-2023 IFT/IFT231790156356/RIUP23/2746/S R ENTERPRISES 175464.00
56697 | GST release note |  | 1 | 153150.48 | [10 empty] | 153150.48 |  |  |  |  | 49500 | 10-01-2024 IFT/IFT24010022786/RIUP23/4208/S R ENTERPRISES 49500.00
56697 | KHERI KARMU Village Pipe Line & RR work | 2025-01-25 | 6 | 477184 | 70456 | 406728 | 73211.04 | 479939.04 | 4067.28 | 20336.4 | 40672.8 | 40672.8 | 73211.04 | 2682 | 298296.72 |  |  |  |  | 300000 | 10-07-2024 IFT/IFT24192050168/RIUP24/0559/S R ENTERPRISES 300000.00
56697 | GST release note |  | 6 | 73211.04 | [10 empty] | 73211.04 |  |  |  |  | 153150 | 14-08-2024 IFT/IFT24227020864/RIUP24/1132/S R ENTERPRISES 153150.00
56697 | [19 empty] | 150000 | 11-02-2025 IFT/IFT25042036793/RIUP24/3083/S R ENTERPRISES 150000.00
56697 | [19 empty] | 73211 | 25-02-2025 IFT/IFT25056028442/RIUP24/3190/S R ENTERPRISES 73211.00
56697 | [19 empty] | 250000 | 19-03-2025 IFT/IFT25078029434/RIUP24/3082/S R ENTERPRISES 250000.00
[16 empty] | 57951 | [5 empty] | 178417.87
57951 | Panjet village pipe line work | 2023-06-14 | 2 | 551925 | 190498 | 361427 | 65056.86 | 426484 | 3614 | 18071.35 | 36142.7 | 36142.7 | 65056.86 | 24819 | 242637.39 |  | RIUP23/855 | 242637 |  | 242637 | 27-06-2023 IFT/IFT23178008662/RIUP23/855/S R ENTERPRISES 242637.00
57951 | Panjet village pipe line work | 2023-08-02 | 4 | 604078.62 | 130601.5 | 473477.12 | 85225.8816 | 558703 | 4735 | 23673.856 | 47347.712 | 47347.712 | 85225.8816 | 36737 | 313635.8384 |  | RIUP23/1703 | 313633 |  | 313633 | 27-09-2023 IFT/IFT23270029213/RIUP23/1703/S R ENTERPRISES 313633.00
57951 | Panjet village pipe line work | 2023-10-26 | 5 | 489735 | 130601.5 | 359133.5 | 64644.03 | 423778 | 3591 | 17956.675 | 35913.35 | 35913.35 | 64644.03 | 21754 | 244005.595 |  | RIUP23/3144 | 244006 |  | 244006 | 09-11-2023 IFT/IFT23313042824/RIUP23/3144/S R ENTERPRISES 244006.00
57951 | GST |  | 2 | 65056.86 | [10 empty] | 65056.86 |  |  |  |  | 149870 | 22-02-2024 IFT/IFT24053029352/RIUP23/4696/S R ENTERPRISES 149870.00
57951 | GST |  | 4 & 5 | 149869.9116 | [10 empty] | 149869.9116 |  |  |  |  | 65057 | 22-03-2024 IFT/IFT24082070378/RIUP23/4844/S R ENTERPRISES 65057.00
57951 | Panjet village pipe line work | 2025-03-07 | 8 | 264607 | 17626 | 246981 | 44456.58 | 291438 | 2470 | 12349.05 | 24698.1 | 24698.1 | 44456.58 | 1764 | 181002.17
57951 | GST |  | 8 | 44456.58 | [10 empty] | 44456.58
[16 empty] | 59090 | [5 empty] | 225461.345
59090 | MAMAUR VILLAGE Pipeline Work | 2023-10-26 | 6 | 515789 | 139609 | 376180 | 67712.4 | 443892.4 | 3761.8 | 18809 | 37618 | 37618 | 67712.4 | 180937 | 97436.2 |  | RIUP23/3150 | 97439 |  | 97439 | 09-11-2023 IFT/IFT23313076730/RIUP23/3150/S R ENTERPRISES 97439.00
59090 | GST |  | 6 | 67712.4 | [10 empty] | 67712.4 |  | RIUP23/3847 | 150000 | 1500 | 148500 | 18-12-2023 IFT/IFT23352039792/RIUP23/3847/S R ENTERPRISES 148500.00
59090 | [19 empty] | 67713 | 22-02-2024 IFT/IFT24053032839/RIUP23/4695/S R ENTERPRISES 67713.00
[16 empty] | 60140 | [5 empty] | -148503.4
60140 | KHERA KURTAN VILLAGE PIPE LINE WORK | [15 empty] | RIUP23/855 | 100000 | 1000 | 99000 | 10-11-2023 IFT/IFT23314104253/RIUP23/3254/S R ENTERPRISES 99000.00
60140 | [19 empty] | 49500 | 12-01-2024 IFT/IFT24012010539/RIUP23/4243/S R ENTERPRISES 49500.00
-148500
[9 empty] | 76020.0349 | 380098.535 | 718124.57 | 760198.07 | 1368355.726 | 1095115 | 5940777.5612 |  | Total Paid Amount Rs. - |  |  | 6038193 |  | -97415.4388
[17 empty] | Balance Payable Amount Rs. - |  |  | -97415.4388
SR Enterprises
Updated On 02-05-2025
[10 empty] | Total Hold |  | 1858421.175
[10 empty] | Advance / Surplus |  | -97415.4388
[10 empty] | GST Remaining |  | 44456.7032
[10 empty] | Extra Hold |  | 1095115

## Sheet2
PMC NO. 54116
SR Enterprises
Sr. No. | HDPE PIPE Dia. In mm | Unit | Work done qty. |  | Received Qty. | Balance | As per DPR Qty.
|  |  | RA Bill No.01 | RA Bill No.02
1 | 63 | Rmt. | 2798.1 |  | 7222 | 4423.9
2 | 75 | Rmt. | 815.5 |  | 2350 | 1534.5
3 | 90 | Rmt. | 1049 |  | 2000 | 951
4 | 110 | Rmt. | 2110 |  | 2200 | 90
5 | 160 | Rmt. | 1322.6 |  | 2208 | 885.4
6 | 200 | Rmt. | 743.6 |  | 792 | 48.4