## Sheet1
Muzaffarnagar UP
| Invoice Reconcilation |  | Sangatpura Tubewell Company |  |  |  |  | Drilling work
Subcontractor: | Sangatpura TubeWell Company
State: | Uttar Pradesh
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS (1%) | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount for excess Qty. against DPR | Final_Amount | Total_Amount | UTR
[9 empty] | 1% | 5% | 0% | 0%
59389 | [14 empty] | 0
59389 | Wazidpur Khurd Village Tubewell development work | 2023-10-09 | 1 | 308263 | 0 | 308263 | 55487 | 363750 | 3082.63 | 15413 |  |  | 55487 |  | 289767.37 | 99000 | 22-09-2023 NEFT/AXISP00426907989/RIUP23/2212/SANGATPURA TUBEWEL/PUNB0347500 99000.00
59389 | GST Release Note | 2023-11-20 | 1 | 55487 | [11 empty] | 190767 | 01-11-2023 NEFT/AXISP00439227042/RIUP23/2660/SANGATPURA TUBEWEL/PUNB0347500 190767.00
59579
59579 | Anti Village Tubewell development work | 2023-10-09 | 3 | 308249.5 | 0 | 308249.5 | 55485 | 363735 | 3082 | 15412 |  |  | 55485 |  | 289756 | 289754 | 01-11-2023 NEFT/AXISP00439227041/RIUP23/2661/SANGATPURA TUBEWEL/PUNB0347500 289754.00
59579 | GST Release Note | 2023-11-20 | 3 | 55485
60000 | Fahimpur Village Tubewell development work | 2023-11-15 | 5 | 309147 | 0 | 309147 | 55646 | 364793 | 3091.47 | 15457 |  |  | 55646 |  | 290598.53 | 290599 | 30-11-2023 NEFT/AXISP00447586130/RIUP23/3473/SANGATPURA TUBEWEL/PUNB0347500 290599.00
63588 | Suaheri Village - Tubewell Work | 2024-04-25 | 1 | 406979 | 39433 | 367546 | 66158 | 433704 | 3675.46 | 18377 |  |  | 66158 |  | 345493.54 | 66158 | 03-08-2024 NEFT/AXISP00524511272/RIUP24/1152/SANGATPURA TUBEWEL/PUNB0347500 66158.00
63588 | GST Release Note |  | 1 | 66158 | [10 empty] | 66158 | 345494 | 26-12-2024 Debit N/RIUP24/0488/SANGATPURA TUB/INDBN26123786910 345494.0
63590 | Jevanpurio Village - Tubewqell Work | 2024-04-25 | 4 | 382955 |  | 382955 | 68932 | 451887 | 3829.55 | 19148 |  |  | 68932 |  | 359977.45 | 359977 | 17-05-2024 NEFT/AXISP00500883090/RIUP24/0538/SANGATPURA TUBEWEL/PUNB0347500 359977.00
| GST Release Note |  | 4 | 68932 | [10 empty] | 68932 | 68932 | 18-07-2024 NEFT/AXISP00519679547/RIUP24/1155/SANGATPURA TUBEWEL/PUNB0347500 68932.00
63591 | Moghpur Village - Tubewell Work | 2024-04-25 | 2 | 336952 |  | 336952 | 60651 | 397603 | 3369.52 | 16848 |  |  | 60651 |  | 316734.48 | 60651 | 18-07-2024 NEFT/AXISP00519679548/RIUP24/1153/SANGATPURA TUBEWEL/PUNB0347500 60651.00
63591 | GST Release Note |  | 2 | 60651 | [10 empty] | 60651 | 88618 | 13-09-2024 NEFT/AXISP00540477814/RIUP24/1408/SANGATPURA TUBEWEL/PUNB0347500 88618.00
63591 | Moghpur Village - Tubewell Work | 2024-08-01 | 22 | 94275 |  | 94275 | 16970 | 111245 | 942.75 | 4714 |  |  | 16970 |  | 88618.25 | 16970 | 30-01-2025 NEFT/AXISP00605897139/RIUP24/2857/SANGATPURA TUBEWEL/PUNB0347500 16970.00
63591 | GST Release Note |  | 22 | 16970 | [10 empty] | 16970 | 200000 | 13-03-2025 NEFT/AXISP00633037285/RIUP24/0487/SANGATPURA TUBEWEL/PUNB0347500 200000.00
63592 | Sohjani Tagan Village - Tubewell Work | 2024-04-25 | 3 | 318059 |  | 318059 | 57251 | 375310 | 3180.59 | 15903 |  |  | 57251 |  | 298975.41 | 298975 | 17-05-2024 NEFT/AXISP00500883091/RIUP24/0539/SANGATPURA TUBEWEL/PUNB0347500 298975.00
63592 | GST Release Note |  | 3 | 57251 | [10 empty] | 57251 | 57251 | 03-08-2024 NEFT/AXISP00524511273/RIUP24/1154/SANGATPURA TUBEWEL/PUNB0347500 57251.00
65221 | Nagla Rai Village - Tubewell Work | 2024-08-01 | 21 | 332499 |  | 332499 | 59850 | 392349 | 3324.99 | 16625 |  |  | 59850 |  | 312549.01 | 312549 | 13-09-2024 NEFT/AXISP00540477811/RIUP24/1405/SANGATPURA TUBEWEL/PUNB0347500 312549.00
65221 | GST Release Note |  | 21 | 59850 | [10 empty] | 59850 | 88618 | 07-02-2025 NEFT/AXISP00612495138/RIUP24/3021/SANGATPURA TUBEWEL/PUNB0347500 88618.00
65221 | Nagla Rai Village - Tubewell Work | 2025-01-25 | 22 | 94275 |  | 94275 | 16970 | 111245 | 942.75 | 4714 |  |  | 16970 |  | 88618.25 | 59850 | 06-03-2025 NEFT/AXISP00628995533/RIUP24/2856/SANGATPURA TUBEWEL/PUNB0347500 59850.00
65223 | Behrassa Village - tubewell Work | 2024-08-01 | 18 | 431029 |  | 431029 | 77585 | 508614 | 4310.29 | 21551 |  |  | 77585 |  | 405167.71 | 405168 | 14-11-2024 NEFT/AXISP00569818230/RIUP24/1404/SANGATPURA TUBEWEL/PUNB0347500 405168.00
65223 | GST Release Note |  | 18 | 77585 | [10 empty] | 77585 | 77585 | 30-01-2025 NEFT/AXISP00605897137/RIUP24/2854/SANGATPURA TUBEWEL/PUNB0347500 77585.00
65224 | Chamrawala Village - Tubewell Work | 2024-08-01 | 19 | 429238 | 74813 | 354425 | 63797 | 418222 | 3544.25 | 17721 |  |  | 63797 |  | 333159.75 | 333160 | 13-09-2024 NEFT/AXISP00540477813/RIUP24/1407/SANGATPURA TUBEWEL/PUNB0347500 333160.00
65224 | GST Release Note |  | 19 | 63797 | [10 empty] | 63797 | 63797 | 30-01-2025 NEFT/AXISP00605897138/RIUP24/2855/SANGATPURA TUBEWEL/PUNB0347500 63796.00
65225 | Lohadda Village - Tubewell Work | 2024-08-01 | 23 | 437971.5 |  | 437971.5 | 78835 | 516807 | 4379.715 | 21899 |  |  | 78835 |  | 411693.285 | 411692 | 13-09-2024 NEFT/AXISP00540477812/RIUP24/1406/SANGATPURA TUBEWEL/PUNB0347500 411692.00
65225 | GST Release Note |  | 23 | 78835 | [10 empty] | 78835 | 78835 | 30-01-2025 NEFT/AXISP00605897140/RIUP24/2858/SANGATPURA TUBEWEL/PUNB0347500 78835.00