## Sheet1
Shamli UP
| Invoice Reconcilation |  | Sarvodaya Enterprises |  |  |  |  | OHT Construction work
| Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | On Commissioning | Testing Deposit | GST SD (18%) | Hold Amount | Final Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | SD (5%) | Advance paid | Total Amount Paid | UTR
[7 empty] | 18% |  | 1% | 5% | 0% | 10% | 18% | [5 empty] | 1% | 5%
58204
58204 | Rettanagala Village OHT Work | 2023-08-05 | 2 | 371250 | 0 | 371250 | 66825 | 438075 | 3713 | 18563 | 0 | 0 | 66825 |  | 348974 |  | RIUP23/997 | 500000 | 5000 | 0 | 0 | 495000 | 03-07-2023 IFT/IFT23184234210/RIUP23/997/SARVODAYA ENTERPRIS ₹ 4,95,000.00
| GST Release Note | 2023-09-04 | 2 | 66825 |  | 66825 | 0 | 66825 | 0 | 0 | 0 | 0 | 0 |  | 66825 |  | RIUP23/2032 | 66825 | 0 | 0 | 0 | 66825 | 15-09-2023 IFT/IFT23258027568/RIUP23/2032/SARVODAYA ENTERPRI 66825.00
| Rettanagala Village OHT Work | 2024-06-24 | 1 | 371250 | 37500 | 333750 | 60075 | 393825 | 3338 | 16688 | 0 | 0 | 60075 |  | 313724
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 57543 | [7 empty] | 167698
57543 | Pipeline work at Bihari Village | 2023-07-18 | 1 | 542048 |  | 542048 | 97569 | 639617 | 5420 | 27102 | 27102.4 | 54205 | 97569 | 4718 | 423501 |  | RIUP23/655 | 300000 | 0 | 0 | 0 | 297000 | 14-06-2023 IFT/IFT23165032174/RIUP23/655/SARVODAYA ENTERPRIS ₹ 2,97,000.00
| GST release note |  |  | 97569 | [10 empty] | 97569 |  | RIUP23/1205 | 126501 | 0 | 0 | 0 | 126501 | 25-07-2023 IFT/IFT23206056301/RIUP23/1205/SARVODAYA ENTERPRI 126501.00
| BIHARI VILLAGE Pipe line work | 2023-09-05 | 3 | 702097 | 19000 | 683097 | 122957 | 806054 | 6831 | 34155 | 34154.85 | 68310 | 122957 | 79692 | 459954 |  | RIUP23/1909 | 459954 | 0 | 0 | 0 | 459954 | 08-09-2023 IFT/IFT23251034858/RIUP23/1909/SARVODAYA ENTERPRI 459954.00
| GST Release note | 2023-10-09 | 3 | 122957 |  | 122957 |  | 122957 | [6 empty] | 122957 |  | RIUP23/2031 | 97569 |  |  |  | 97569 | 15-09-2023 IFT/IFT23258018934/RIUP23/2031/SARVODAYA ENTERPRI ₹ 97,569.00
| BIHARI VILLAGE Pipe line work | 2023-11-06 | 5 | 250155 | 0 | 250155 | 45028 | 295183 | 2502 | 12508 | 25015.5 | 25016 | 45028 | 45053 | 140061 |  | RIUP23/2764 | 122957 |  |  |  | 122957 | 26-10-2023 IFT/IFT23299016807/RIUP23/2764/SARVODAYA ENTERPRI 122957.00
| GST Release note |  | 5 | 45028 |  | 45028 |  | 45028 | [6 empty] | 45028 |  | RIUP23/3228 | 100000 | 1000 |  |  | 99000 | 10-11-2023 IFT/IFT23314061989/RIUP23/3228/SARVODAYA ENTERPRI 99000.00
[17 empty] | RIUP23/3442 | 41060 |  |  |  | 41060 | 06-12-2023 IFT/IFT23340066367/RIUP23/3442/SARVODAYA ENTERPRI 41060.00
[17 empty] | RIUP23/3442 | 45028 |  |  |  | 45028 | 22-12-2023 IFT/IFT23356043570/RIUP23/3785/SARVODAYA ENTERPRI 45028.00
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 58205 | [7 empty] | 1
58205 | CONSTRUCTION OF OVERHEAD TANK- VILLAGE MAHRAIPUR- BLOCK- PURKAZI | [20 empty] | 495000 | 05-07-2023 IFT/IFT23186053132/RIUP23/1011/SARVODAYA ENTERPRI ₹ 4,95,000.00
[16 empty] | 55822 | [7 empty] | -495000
55822 | Madpur Village Pipe laying /work | 2023-09-11 | 4 | 485858.5 | 4360 | 481499 | 86670 | 568169 | 4815 | 24075 | 24074.95 | 48150 | 86670 | 106158 | 274226 |  | RIUP23/962 | 150000 | 0 | 0 | 0 | 148500 | 30-06-2023 IFT/IFT23181234240/RIUP23/962/SARVODAYA ENTERPRIS 148500.00
| GST Release note | 2023-10-09 | 4 | 86670 |  | 86670 |  | 86670 | [6 empty] | 86670 |  | RIUP23/1998 | 125726 | 0 | 0 | 0 | 125726 | 13-09-2023 IFT/IFT23256036659/RIUP23/1998/SARVODAYA ENTERPRI 125726.00
[17 empty] | RIUP23/2763 | 86670 |  |  |  | 86670 | 26-10-2023 IFT/IFT23299016806/RIUP23/2763/SARVODAYA ENTERPRI 86670.00
[16 empty] | 58365 | [7 empty] | 0
58365 | ROAD RESTORATION WORK IN MANDLA VILLAGE
235621
[10 empty] | 133091 | 110347.7 | 195681 | 479124 | Total Payable Amount Rs. - | 2379489 |  |  |  |  | Total Paid Amount Rs. - |  | 2706790
[20 empty] | Balance Payable Amount Rs. - |  | -327301
Sarvodaya Traders
Updated On 02-07-2024 ( By Vikash )
[9 empty] | Total Hold |  | 439119.7
[9 empty] | Advance / Surplus |  | -327301
[9 empty] | Debit |  | Nil
[9 empty] | GST Remaining |  | 105103