## Sheet1
Subcontractor: | Shri Balaji Construction
State: | Uttar Pradesh | [6 empty] | Pipeline Laying work | [8 empty] | 2024-04-26
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | Hydro Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount |  | PAYMENT NOTE No. | Amount | TDS Amount @ 1% on BASIC AMOUNT | Total_Amount | UTR | Advance Village Wise
[10 empty] | 1% | 5% | 10% | 10% | [6 empty] | 1%
53640
53640 | Nojal Nojli Village Pipeline laying work | 2022-12-01 | 4 |  | 357732 | 0 | 357732 | 64392 | 422124 | 3577 | 17887 | 35773 | 35773 | 64392 | 18743 | 245979 |  | RIUP22/1475 | 245979 | 0 | 245979 | 10-12-2022 IFT/IFT22344008545/RIUP22/1475/SHRI BALAJI CONSTR 245979.00 | -340357
53640 | Nojal Nojli Village Pipeline laying work | 2023-01-01 | 5 |  | 877768 | 0 | 877768 | 157998 | 1035766 | 8778 | 43888 | 87777 |  | 157998 | 64890 | 584658 |  | RIUP22/1803 | 584658 | 0 | 584658 | 07-01-2023 IFT/IFT23007044361/RIUP22/1803/SHRI BALAJI CONSTR 584658.00
53640 | GST release note | 2023-01-21 | 4 |  | 64392 |  | 64392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64392 |  | RIUP22/1978 | 64392 | 0 | 64392 | 24-01-2023 IFT/IFT23024007687/RIUP22/1978/SHRIBALAJI CONSTR 64392.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-01-30 | 6 |  | 545978 | 0 | 545978 | 98276 | 644254 | 5460 | 27299 | 54598 | 54598 | 98276 | 40097 | 363926 |  | RIUP22/2084 | 363926 | 0 | 363926 | 04-02-2023 IFT/IFT23035022862/RIUP22/2084/SHRI BALAJI CONSTR ₹ 3,63,926.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-03-02 | 7 |  | 555391 | 0 | 555391 | 99970 | 655361 | 5554 | 27770 | 55539 | 55539 | 99970 | 0 | 410989 |  | RIUP22/2214 | 100000 | 1000 | 99000 | 17-02-2023 IFT/IFT23048032050/RIUP22/2214/SHRI BALAJI CONSTR 99000.00
53640 | GST release note | 2023-04-05 | 5 |  | 157998 | [10 empty] | 157998 |  | RIUP22/2641 | 250000 | 2500 | 247500 | 17-03-2023 IFT/IFT23076014164/RIUP22/2641/SHRI BALAJI CONSTR 247500.00
53640 | GST release note | 2023-04-05 | 6 |  | 98276 | [10 empty] | 98276 |  | RIUP22/2748 | 100000 | 1000 | 99000 | 27-03-2023 IFT/IFT23086032017/RIUP22/2748/SHRI BALAJI CONSTR 99000.00
53640 | GST release note | 2023-04-29 | 7 |  | 99970 | [10 empty] | 99970 |  |  | 256274 |  | 256274 | 10-04-2023 IFT/IFT23100051022 /Shri Balaji Construction 2,56,274
53640 | Nojal Nojli Village Pipeline laying work | 2023-07-27 | 4 |  | 454626 | 110427.09 | 344198.91 | 61956 | 406154.91 | 3442 | 17210 | 34420 | 34420 | 61956 | 0 | 254707 |  | RIUP23/273 | 99970 |  | 99970 | 19-05-2023 IFT/IFT23139017435/RIUP23/273/SHRI BALAJI CONSTRU ₹ 99,970.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-09-05 | 6 |  | 320402 | 0 | 320402 | 57672 | 378074 | 3204 | 16020 | 32040 | 32040 | 57672 | 0 | 237098 |  | RIUP23/1404 | 220197 |  | 220197 | 08-08-2023 IFT/IFT23220049166/RIUP23/1404/SHRI BALAJI CONSTR 220197.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-09-26 | 8 |  | 175450 | 0 | 175450 | 31581 | 207031 | 1755 | 8773 | 17545 | 17545 | 31581 | 0 | 129832 |  | RIUP23/1717 | 50000 | 500 | 49500 | 25-08-2023 IFT/IFT23237043051/RIUP23/1717/SHRI BALAJI CONSTR 49500.00
53640 | Nojal Nojli Village Pipeline laying work | 2023-10-20 | 11 |  | 671125 | 0 | 671125 | 120803 | 791928 | 6711 | 33556 | 67113 | 67113 | 120803 | 28618 | 468014 |  | RIUP23/2080 | 187599 | 0 | 187599 | 18-09-2023 IFT/IFT23261006068/RIUP23/2080/SHRI BALAJI CONSTR 187599.00
53640 | GST release note |  | 4 |  | 61956 | [10 empty] | 61956 |  | RIUP23/2466 | 129832 |  | 129832 | 04-10-2023 IFT/IFT23277053670/RIUP23/2466/SHRI BALAJI CONSTR 129832.00
53640 | GST release note |  | 6 & 8 |  | 89253 | [10 empty] | 89253 |  | RIUP23/2854 | 150000 | 1500 | 148500 | 25-10-2023 IFT/IFT23298013281/RIUP23/2854/SHRI BALAJI CONSTR 148500.00
53640 | GST release note |  | 11 |  | 120803 | [10 empty] | 120803 |  | RIUP23/3011 | 319514 |  | 319514 | 08-11-2023 IFT/IFT23312068903/RIUP23/3011/SHRI BALAJI CONSTR 319514.00
53640 | Nojal Nojli Village Pipeline laying work | 2024-03-09 | 14 |  | 205283 | 19075 | 186208 | 33517 | 219725 | 1862 | 9310 | 18621 | 18621 | 33517 | 103330 | 34464 |  | RIUP23/3365 | 61956 |  | 61956 | 24-11-2023 IFT/IFT23328055355/RIUP23/3365/SHRI BALAJI CONSTR 61956.00
53640 | GST release note |  | 14 |  | 33517 | [10 empty] | 33517 |  | RIUP23/3768 | 150000 | 1500 | 148500 | 15-12-2023 IFT/IFT23349026038/RIUP23/3768/SHRI BALAJI CONSTR 148500.00
53640 | Nojal Nojli Village Pipeline laying work | 2024-10-29 | 12 |  | 907318 | 221270 | 686048 | 123489 | 809537 | 6860 | 34302 | 68605 | 68605 | 123489 |  | 507676 |  | RIUP23/3775 | 89254 |  | 89254 | 27-12-2023 IFT/IFT23361009769/RIUP23/3775/SHRI BALAJI CONSTR 89254.00
53640 | GST release note |  | 12 |  | 123489 | [10 empty] | 123489 |  | RIUP23/5132 | 120803 |  | 120803 | 22-03-2024 IFT/IFT24082070375/RIUP23/5132/SHRI BALAJI CONSTR 120803.00
53640 | [17 empty] | RIUP24/2126 | 250000 | 2500 | 247500 | 05-10-2024 IFT/IFT24279099632/RIUP24/2126/SHRI BALAJI CONSTR 247500.00
53640 | [20 empty] | 247500 | 21-10-2024 IFT/IFT24295027658/RIUP24/2257/SHRI BALAJI CONSTR 247500.00
53640 | [20 empty] | 198000 | 30-10-2024 IFT/IFT24304255883/RIUP24/2364/SHRI BALAJI CONSTR 198000.00
53640 | [20 empty] | 198000 | 04-12-2024 IFT/IFT24339039524/RIUP24/2627/SHRI BALAJI CONSTR 198000.00
51737
51737 | Mantmanti Village Pipeline laying work | 2022-09-20 | 1 |  | 2107070.25 | 54042 | 2053028.25 | 369545 | 2422573.25 | 20530.2825 | 205302.825 |  | 205302.825 | 369545 | 314949 | 1306943.3175 |  | RIUP22/412 | 200000 | 2000 | 198000 | 28-07-2022 IFT/IFT22209020738/RIUP22/412/SHRI BALAJI CONSTRU 198000.00 | -823659.3645
51737 | Mantmanti Village Pipeline laying work | 2022-10-13 | 2 |  | 231800.2 | 0 | 231800.2 | 41724 | 273524.2 | 2318.002 | 23180.02 |  | 23180.02 | 41724 |  | 183122.158 |  | RIUP22/554 | 200000 | 2000 | 198000 | 20-08-2022 IFT/IFT22232005689/RIUP22/554/SHRI BALAJI CONSTRU 198000.00
51737 | GST release note |  | 1 |  | 369545 | 0 | 369545 | 0 | 369545 | 0 | [5 empty] | 369545 |  | RIUP22/586 | 150000 | 1500 | 148500 | 22-08-2022 IFT/IFT22234028107/RIUP22/586/SHRI BALAJI CONSTRU 148500.00
51737 | GST release note |  | 2 |  | 41724 | 0 | 41724 | 0 | 41724 | 0 | 0 |  |  |  | 0 | 41724 |  | RIUP22/884 | 600000 | 6000 | 594000 | 03-10-2022 IFT/IFT22276009534/RIUP22/884/SHRI BALAJI CONSTRU 594000.00
51737 | Mantmanti Village Pipeline laying work | 2023-10-19 | 10 |  | 270086 | 0 | 270086 | 48615.48 | 318701.48 | 2700.86 | 13504.3 | 27008.6 | 27008.6 | 48615.48 | 0 | 199863.64 |  | RIUP22/1078 | 300000 | 3000 | 297000 | 21-10-2022 IFT/IFT22294059834/RIUP22/1078/SHRI BALAJI CONSTR 297000.00
51737 | Mantmanti Village Pipeline laying work | 2023-11-01 | 12 |  | 316012 | 0 | 316012 | 56882.16 | 372894.16 | 3160.12 | 15800.6 | 31601.2 | 31601.2 | 56882.16 | 0 | 233848.88 |  | RIUP22/1181 | 54565 | 0 | 54565 | 05-11-2022 IFT/IFT22309031468/RIUP22/1181/SHRI BALAJI CONSTR 54565.00
51737 | GST release note |  | 10 |  | 48615.48 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | 48615.48 |  | RIUP22/1482 | 200000 | 0 | 200000 | 10-12-2022 IFT/IFT22344008547/RIUP22/1482/SHRI BALAJI CONSTR 200000.00
51737 | GST release note |  | 12 |  | 56882.16 | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 | 56882.16 |  | RIUP22/1632 | 369545 |  | 369545 | 27-12-2022 IFT/IFT22361012953/RIUP22/1632/SHRI BALAJI CONSTR 369545.00
51737 | [17 empty] | RIUP22/1977 | 41724 |  | 41724 | 24-01-2023 IFT/IFT23024012629/RIUP22/1977/SHRI BALAJI CONSTR ₹ 41,724.00
51737 | [17 empty] | RIUP22/2361 | 50000 | 500 | 49500 | 28-02-2023 IFT/IFT23059053147/RIUP22/2361/SHRI BALAJI CONSTR 49500.00
51737 | [17 empty] | RIUP23/2830 | 150000 | 1500 | 148500 | 23-10-2023 IFT/IFT23296024452/RIUP23/2830/SHRI BALAJI CONSTR 148500.00
51737 | [17 empty] | RIUP23/2016 | 120000 | 1200 | 118800 | 14-09-2023 IFT/IFT23257021729/RIUP23/2016/SHRI BALAJI CONSTR 118800.00
51737 | [17 empty] | RIUP23/3137 | 100000 | 1000 | 99000 | 08-11-2023 IFT/IFT23312076789/RIUP23/3137/SHRI BALAJI CONSTR 99000.00
51737 | [17 empty] | RIUP23/3641 | 17873 |  | 17873 | 07-12-2023 IFT/IFT23341087153/RIUP23/3641/SHRI BALAJI CONSTR 17873.00
51737 | [17 empty] | RIUP23/3955 | 48615 |  | 48615 | 08-01-2024 IFT/IFT24008065305/RIUP23/3955/SHRI BALAJI CONSTR ₹ 48,615.00
51737 | [17 empty] | RIUP23/4815 | 80000 | 800 | 79200 | 22-02-2024 IFT/IFT24053032838/RIUP23/4815/SHRI BALAJI CONSTR 79200.00
51737 | [20 empty] | 56882 | 26-04-2024 IFT/IFT24117006559/RIUP23/5133/SHRI BALAJI CONSTR 56882.00 682517655.06 CBB
51737 | [20 empty] | 99000 | 10-09-2024 IFT/IFT24254007340/RIUP24/1727/SHRI BALAJI CONSTR 99000.00
51737 | [20 empty] | 74250 | 17-09-2024 IFT/IFT24261027201/RIUP24/1806/SHRI BALAJI CONSTR 74250.00
51737 | [20 empty] | 74250 | 21-09-2024 IFT/IFT24265015454/RIUP24/1895/SHRI BALAJI CONSTR 74250.00
51737 | [20 empty] | 99000 | 01-10-2024 IFT/IFT24275137125/RIUP24/2011/SHRI BALAJI CONSTR 99000.00
51737 | [20 empty] | 198000 | 30-10-2024 IFT/IFT24304255885/RIUP24/2365/SHRI BALAJI CONSTR 198000.00
62993 | [16 empty] | 62993
62993 | Bhatu village pipeline work | 2024-03-12 | 15 |  | 260280 |  | 260280 | 46850.4 | 307130.4 | 2602.8 | 13014 | 26028 | 26028 | 46850.4 | 8870 | 183737.2 |  |  |  |  | 183737 | 17-05-2024 IFT/IFT24138018957/RIUP24/0143/SHRI BALAJI CONSTR 183737.00 | 46850.6
62993 | GST |  | 15 |  | 46850.4 | [10 empty] | 46850.4
62993
[11 empty] | 506816.745 | 556668.8 | 697374.645 | 1413271.04 | 579497 | 6758129.2355 |  | Total Paid Amount Rs. - |  |  | 7875295 |  | -1117165.7645
[18 empty] | Balance Payable Amount Rs. - |  |  | -1117165.7645
Shri Balaji Construction
2025-03-20
[9 empty] | Hold Amount |  | 1760860.19
[9 empty] | Advance / Surplus |  | -1117165.7645
[9 empty] | Hold Amount For Quantity excess against DPR |  | 579497
[9 empty] | Debit |  | -123987
[9 empty] | GST Remaining |  | Nil
Qty as per updated Dawing
|  |  | Dia |  | Length | CUM |  |  | ITEM | DPR | CUM | EXCESS | RATE | AMT
|  |  | 63 |  | 5175 | 4794.2 | As per updated drawing |  | 90MM | 588 | 625.9 | 37.9 | 95 | 3600.5
|  |  | 75 |  | 694 | 678.9 |  |  | j HOOK | 0 | 674 | 674 | 8 | 5392
|  |  | 90 |  | 588 | 625.9 |  | As per old DPR | BOE | 37.13 | 301.7 | 264.57 | 50 | 13228.5
|  |  | 110 |  | 434 | 421.6 | [6 empty] | hold amt | 22221
|  |  | 160 |  | 774 | 768 | [6 empty] | prev hold | #REF!
|  |  | 200 |  | 273 | 189.5 | [6 empty] | to be hold | #REF!
|  |  | Total |  | 7938