## Sheet1
Subcontractor: | VANSH CONSTRUCTION
State: | Uttar Pradesh
District: | Shamli
Block: | Shamli
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold Amount For Quantity excess against DPR | Final_Amount | PAYMENT NOTE No. | Payment_Amount | TDS_Payment_Amount | SD (5%) | Advance paid | Total_Amount | UTR
[9 empty] | 1% | 5% | 10% | 10% | [5 empty] | 1% | 5%
57226 | Khanpur village Pipeline work | 2023-06-04 | 2 | 277098 | 0 | 277098 | 49877.64 | 326975.64 | 2770.98 | 13854.9 | 27709.8 | 27709.8 | 49877.64 | 80687 | 124365.52 | RIUP23/640 | 124363 | 0 |  |  | 124363 | 16-06-2023 NEFT/AXISP00399009121/RIUP23/640/VANSH CONSTRUCTI 124363.00
57226 | GSt release note |  | 2 | 49877.64 | [10 empty] | 49877.64 | RIUP23/1130 | 49877 | 0 |  |  | 49877 | 21-07-2023 NEFT/AXISP00408446752/RIUP23/1130/VANSH CONSTRUCT 49877.00
57226 | [15 empty] | RIUP23/1253 | 40000 | 400 |  |  | 39600 | 28-07-2023 NEFT/AXISP00410054448/RIUP23/1253/VANSH CONSTRUCT 39600.00 | -39596.84
57225 | Dokpura village Pipeline work | 2023-05-20 | 1 | 566989 | 0 | 566989 | 102058 | 669047 | 5670 | 28349 | 56699 | 56699 | 102058 | 4695 | 414877 | RIUP23/218 | 414877 |  |  |  | 414877 | 12-05-2023 NEFT/AXISP00389894131/RIUP23/218/VANSH CONSTRUCTI 414877.00
57225 |  | 2023-07-03 | 3 | 361335.3 |  | 361335.5 | 65040.39 | 426375.89 | 3613.355 | 18066.775 | 36133.55 | 36133.55 | 65040.39 | 3910 | 264120 | RIUP23/1074 | 264120 |  |  |  | 264120 | 15-07-2023 NEFT/AXISP00407207182/RIUP23/1074/VANSH CONSTRUCT 264120.00
57225 | [15 empty] | RIUP23/1131 | 102058 |  |  |  | 102058 | 24-07-2023 NEFT/AXISP00408935254/RIUP23/1131/VANSH CONSTRUCT 102058.00
-102058
[10 empty] | 60270.675 | 120542.35 | 120542.35 | 216976.03 | 89292 | 853240.16 |  |  |  | Total Paid Amount Rs. - |  | 994895
[19 empty] | Balance Payable Amount Rs. - |  | -141654.84
0
|  |  |  | ITEM | DPR | CUM | EXCESS | RATE | AMT
|  |  |  | BOE | 0 | 419.54 | 419.54 | 50 | 20977
|  |  |  | R BOE | 0 | 298.55 | 298.55 | 200 | 59710
[7 empty] | HOLD AMOUNT |  | 80687